## KEY
03_02_17
TOWN ROAD IMPROVEMENT PROJECT - SURVEY LEGEND AND COST PER MILE
COLOR KEY
|  | 1 | Recently Updated, Or in Good Condition - No work planned
|  | 2 | Paved Road, repaving planned, same surface
|  | 3 | Paved Road, repaving planned, new surface
|  | 4 | Existing Gravel Road, planned upgrade to pavement
|  | 5 | Existing Gravel Road, general grading and gravel
|  | 6 | Existing Gravel Road/Fire Road - No Plans
PAVING COST PER MILE
NEW Surface
|  |  |  | EXISTING Surface | Gravel | Chip Seal | Asphalt
|  |  |  | GRAVEL | 40000 | 60000 | 197000
|  |  |  | CHIP SEAL | 40000 | 95000 | 216000
|  |  |  | ASPHALT | 40000 | 95000 | 216000
Why Are Roads Important?
They provide safe and ease of access to homes and business by residents and guests and
all types of emergency and service vehicles
NOTES:
| 1 | what about cost of markings, lines, signs?
| 2 | what about easements costs for bike lanes, turn arounds, widening?
| 3 | what about engineering costs for widening, turn arounds, general improvements
| 4 | any bridge or culvert work to include?
| 5 | need to identify roads, mileage for potential cost share
6
7
8
9
TOWN ROAD IMPROVEMENT PROJECT
SURVEY RESULTS
1. ROADS SORTED BY PRIORITY RANKING
2. ROADS SORTED BY 20% SEGMENTATION
3. ROADS SORTED BY CATEGORY TYPE
Note on I16: Greg Van Grinsven: Add $19,000 per mile to pulverize chip seal or asphalt material.
Note on I17: Greg Van Grinsven: Add $19,000 per mile to pulverize chip seal or asphalt material.

## Options
Town Road Improvement Project Options | [8 empty] | 03_02_17
2017 Updated Costs with one-time estimated $700,000 fixed costs
Option I | Do All with Asphalt Upgrades
|  | % of | Accum. |  | Cost by 20% | Finance | 75% | 6136256.25
|  | Dollars | Miles | % | Increments | Grants | 25% | 2045418.75
|  | 46.82% | 19.05 | 20 | 3503020 |  |  | 8181675 | 1877000
|  | 21.87% | 36.81 | 20 | 1636405
|  | 13.91% | 55.58 | 20 | 1040400
|  | 9.142% | 74.35 | 20 | 683950
|  | 8.259% | 92.29 | 20 | 617900 |  |  |  |  | Cost w/o H/F, Allen, Fallon
|  |  |  | 100 | 7481675 |  |  |  |  | 6959575 | 522100
Option II | Do All with Chip Seal or Stone Mastic Overlay (SMO) (Based upon two quotes, SMO and Chip Seal are almost the same cost)
|  | % of | Accum. |  | Cost by 20%
|  | Dollars | Miles | % | Increments
|  | 32.95% | 19.05 | 20 | 1846800 | Finance | 75% | 4728506.25 | 1407750
|  | 25.26% | 36.81 | 20 | 1415625 | Grants | 25% | 1576168.75 | 469250
|  | 18.56% | 55.58 | 20 | 1040400 |  |  | 6304675 | 1407750
|  | 12.2% | 74.35 | 20 | 683950 | Finance Cost Reduction |  |  | 17.21%
|  | 11.02% | 92.29 | 20 | 617900 | Total Investment Cost Reductions |  |  | 22.94%
|  |  |  | 100 | 5604675
Option III | Do All with asphalt upgrades but without Bike Trail Loop Enhancements (4 main roads will not be widened)
|  | % of | Accum. |  | Cost by 20%
|  | Dollars | Miles | % | Increments
|  | 46.82% | 19.05 | 20 | 3333180 | Finance | 75% | 5727232.5 | 409023.75
|  | 21.87% | 36.81 | 20 | 1260880 | Grants | 25% | 1909077.5 | 136341.25
|  | 13.91% | 55.58 | 20 | 1040400 |  |  | 7636310 | 409023.75
|  | 9.142% | 74.35 | 20 | 683950 | Finance Cost Reduction |  |  | 4.999%
|  | 8.259% | 92.29 | 20 | 617900 | Total Investment Cost Reductions |  |  | 6.666%
|  |  |  | 100 | 6936310
Option IV | Top 10 Roads Upgraded to Asphalt (19.05 miles) |  |  |  |  | Finance | 75% | 3152265
[6 empty] | Grants | 25% | 1050755
[8 empty] | 4203020 | 2983991.25
[6 empty] | Finance Cost Reduction |  |  | 36.47%
[6 empty] | Total Investment Cost Reductions |  |  | 48.63%
Option V | Top 10 Roads Chip Seal or Stone Mastic Overlay (19.05 miles) |  |  |  |  | Finance | 75% | 1910100
[6 empty] | Grants | 25% | 636700
[8 empty] | 2546800 | 4226156.25
[6 empty] | Finance Cost Reduction |  |  | 51.65%
[6 empty] | Total Investment Cost Reductions |  |  | 68.87%
Option VI | Staggered Investment e.g. $1m/every year for 8 years or $2.5m every five years for 15 years.
|  | 2018 |  | 2023 |  | 2028 |  | Sub Total | Total
| Bond | 2000000 |  | 2000000 |  | 2000000 |  | 6000000 | 7500000
| Grant | 500000 |  | 500000 |  | 500000 |  | 1500000 | 136256.25
Option VII | Fixed amount of increase in the annual budget. e.g. $298,000 for 2017
250000
500000
1000000
2000000
Option VIII | Continue Maintenance of Existing Roads Only |  |  |  | 250000 |  |  | No Immediate Increase In Taxes
|  |  |  | Loan Amount | Difference | Tax Impact
Option I | Do All with Asphalt Upgrade |  | 8181675 | 6136256.25 | 0 | TBD
Option II | Do All with Chip Seal |  | 6304675 | 4728506.25 | 1407750 | TBD
Option III | Do All - Asphalt - No Widening |  | 7636310 | 5727232.5 | 409023.75 | TBD
Option IV | Do Top Ten W/ Asphalt |  | 4203020 | 3152265 | 2983991.25 | TBD
Option V | Do Top Ten W/ Chip Seal |  | 2546800 | 1910100 | 4226156.25 | TBD
Option VI | Staggered Investment |  |  | 6000000 | 136256.25 | TBD
Option VII | Annual Budget Increase |  | 278000 | 0 |  | TBD
Option VIII | No Loan / No Increase in Budget |  | 250000 | 0 |  | 0
ASSUMPTIONS
No Change to the current annual road maintenance budget
25% of the total cost will be covered by grants
Note on B67: Greg Van Grinsven: 7 out of the top 10 roads were to be upgraded to Asphalt
Note on B68: Greg Van Grinsven: 7 out of the top ten roads would remain chip sealed
Note on B70: Greg Van Grinsven: Only the top ten roads would be done now, approx. 20 miles of roads.
Note on B71: Greg Van Grinsven: Only the top ten roads would be done now, approx. 20 miles of roads.

## Pros & Cons
Town Road Improvement Pros & Cons |  |  |  | 03_02_17
Option I | Do All with Asphalt Upgrades as originally proposed
| Pros | Every road needing repair will be addressed immediately
Provides most equitable safety, emergency and fire access for all tax payers
Expands the base of bidders possibly providing more competitive bids
Provides the highest wearable, durable, and longest lasting road surface
Provides a road surface that will withstand logging and other large commercial vehicles
The top 4 highest used, highest occupancy, and poorest condition roads would be less susceptible to damage
by logging and other large commercial vehicles.
If the roads are maintained properly the long term investment will also provide a longer life expectancy
| Cons | Highest dollar amount investment option as compared to the other options.
Should be supported by increased annual road maintenance budget to protect the investment
May be hard to execute as proper drainage required to support an asphalt road may not be achievable
May require new aprons / culvert for driveways which may not be fully represented in the cost estimate
If all of the roads are done at the same time, as opposed to a staggered schedule, the town will face a complete overhaul at the
same time down the road
Option II | Do All with Chip Seal or Stone Mastic Overlay (SMO) (Based upon two quotes, SMO and Chip Seal are almost the same cost)
| Pros | Every road needing repair will be addressed immediately
Less expensive financing cost as compared to Option I ($4.7m investment cost vs. $6.1m )
Provides most equitable safety, emergency and fire access for all tax payers
Combines best possible wear surface with low cost
Provides the option of Chip Seal where road structure needs to be improved and SMO where it doesn't
Expands the base of bidders possibly providing more competitive bids
A higher maintenance budget may not be needed to support these surface improvements
| Cons | Sacrificing the long term wearability of asphalt resulting in higher maintenance costs and earlier replacement need
Road surface is more susceptible to damage by logging and other large commercial vehicles.
Option III | Do All with asphalt upgrades but without Bike Trail Loop Enhancements (4 main roads will not be widened)
| Pros | Less expensive financing cost as compared to Option I ($5.7m investment cost vs. $6.1m )
| Cons | Does not provide passing zone for bicyclists
Does not take advantage of the cost benefit provided when done in conjunction with the road upgrade
Does not enable the creation of a additional bicycle loops as a competitive tourist advantage
Eliminates the ability to increase the possibility of grant money for increasing tourism. Unable to utilize Room Tax Savings dollars
to increase tourism
Option IV | Top 10 Roads Upgraded to Asphalt (19.05 miles)
| Pros | Less expensive financing cost as compared to Option I ($3.1m investment cost vs. $6.1m )
Provides immediate improvement to the highest traffic, highest occupancy, worst condition roads.
Provides most durable, wearable and longest lasting road surface
| Cons | May not get the best bids as total miles of roads to be done are reduced by 70% (19 miles vs. 64 miles)
May limit the base of bidders
May limit the number of the planned enhancements (more loops) to the bike trail system.
Some of these roads do not necessarily need Asphalt increasing cost unnecessarily
Option V | Top 10 Roads Remain Chip Seal or Stone Mastic Overlay (19.05 miles)
| Pros | Less expensive financing cost as compared to Option I ($1.9m investment cost vs. $6.1m )
Provides immediate improvement to the highest traffic, highest occupancy, worst condition roads.
| Cons | Sacrificing the long term wearability of asphalt resulting in higher maintenance costs and earlier replacement need
May not get the best bids as total miles of roads to be done are reduced by 70% (19 miles vs. 64 miles)
May limit the base of bidders
May limit the number of the planned enhancements (more loops) to the bike trail system.
Option VI | Staggered Investment e.g. $1m/every year for 8 years or $2.5m every five years for 15 years.
| Pros | A staggered approach allows for long term planning, fixing the worst of the worst first and a plan moving forward with a eases
staggered investment and tax increases
| Cons | Going to be more expensive than any option because project and financing costs are assumed to go up over time.
Will require more administrative costs because engineering and finance costs will be repeated every year or every 5 years
The number of contractors submitting bids would be reduced as a result of a smaller project
Option VII | Fixed amount of increase in the annual budget. e.g. $298,000 for 2017
| Pros | Some high priority roads will be addressed on an annual basis
I see no benefit to this approach
| Cons | A very small number and total miles of road could be improved in any given year
Average cost per mile may be higher because of the loss of competitive bids from non-local companies
Business as usual, what you see is what you get and the most expensive approach for replacing and maintaining town roads
The illusion that this would be the most economical approach but extremely short sighted approach
Option VIII | Continue Maintenance of Existing Roads Only
| Pros | Tax increase may be needed in any given year to fix roads that have failed or are near failing
| Cons | Roads will get replaced only on an emergency basis
When roads fail, we run the risk of potentially higher replacement costs as compared to a planned replacement
Reduces the speed at which emergency service providers can respond
Increased liability for accidents and EMS services as well as liability for vehicle repairs due to failing road infrastructure
Property values will decrease due to the lack of sound road infrastructure
Economic development will continue to decline
Businesses will seek other places to open a business or move their business
If we are not improving our infrastructure the residential and business climate will likely decline and Boulder would be a less
desirable destination to live and work
Taxes will continue to increase just to patch and repair what is falling apart
To Do: | Make sure the projected costs are updated to reflect the work scheduled for completion in 2017. High / Fishtrap Lake Road and Stiloski Lane
Find a way to display financing costs
Complete Pros / Cons Analysis
Review 2017 road improvement proposal by DR
Create simple investment options for Barb
One-time budget increase
Bonds

## Roads-Alpha Priority Ranking
03_02_17 | PLAN |  |  |  | Length |  |  | SURFACE TYPE |  |  |  | RATING |  |  |  |  | RESURFACE PLAN |  |  | RESURFACE |  | Work Scope |  | Extra Work
TYPE | CAT | ROAD NAME | Primary Access Road | Secondary Access Road | Miles | Accum. | Gravel | Chip | Asphalt | Seal Coated or Resurfaced |  | Traffic | Occupancy | Condition | Priority | Weighted | Gravel | Chip | Asphalt | COST EST | Surface | Engrg | Extra | Description | COMMENTS
TR | 3 | Allen Road | CTY M North | High Lake Road | 0.68 | 0.68 |  | 0.68 |  | 1975, 1990 |  | 5 | 5 | 5 | 15 | 125 |  | 0 | 0.68 | 220320 |  |  |  |  | upgrade to asphalt, widen 8' for Bike lanes (White Deer Loop)
TR | 3 | Fishtrap Lake Road | CTY M North, High-FT Lake Rd | XX | 2.04 | 2.72 |  | 2.04 |  | 72,73,75,82,86 |  | 5 | 5 | 5 | 15 | 125 |  | 0.64 | 1.4 | 340800 |  |  |  |  | Do we want all or % as Asphalt??? Shown with asphalt to trail corner
TR | 3 | Newcomb Lane | CTY K West | XX | 3.5 | 6.22 |  | 3.5 |  | 78,80,83,88,92 |  | 5 | 5 | 5 | 15 | 125 |  |  | 3.5 | 756000 |  |  |  |  | Why Asphalt? Not a high population area like Fishtrap Lake Rd.
TR | 3 | North Creek Road | CTY M South | CTY H | 4.57 | 10.79 |  | 4.57 |  | 75, 76, 87, 92 |  | 5 | 5 | 5 | 15 | 125 |  |  | 4.57 | 987120 |  |  |  |  | Possible width increase for Bike Route, Cost share with DNR
TR | 3 | Fallon Road | CTY K West | XX | 2.08 | 12.87 |  | 2.08 |  | 1984, 1986 |  | 5 | 5 | 4 | 14 | 100 |  |  | 2.08 | 449280
TR | 2 | Island Lake Road | US 51 North | XX | 1.28 | 14.15 |  | 1.28 |  | 1987 |  | 4 | 5 | 4 | 13 | 80 |  | 1.28 |  | 121600
TR | 2 | High-Fishtrap Lake Road | CTY M North | XX | 1.1 | 15.25 |  | 1.1 |  |  |  | 5 | 5 | 3 | 13 | 75 |  |  | 1.1 | 356400 |  |  |  |  | asphalt for loop, add 8' to width
TR | 4 | Big Muskellunge Road | CTY M South | XX | 2.7 | 17.95 | 1.2 | 1 | 0.5 | 1976 |  | 5 | 3 | 4 | 12 | 60 |  | 2.2 |  | 167000
TR | 2 | Kern Lane | CTY m South | North Creek Road | 1.1 | 19.05 |  | 1.1 |  |  |  | 3 | 4 | 5 | 12 | 60 |  | 1.1 |  | 104500
TR | 4 | Airport Road (paved) | CTY M North | Dairymen's Road | 2.45 | 21.5 |  |  | 1.45 | 1969, 1984 |  | 5 | 5 | 2 | 12 | 50 |  |  | 0 | 0
TR | 2 | Shamrock Lane | CTY K West | Highland Drive | 0.4 | 21.9 |  | 0.4 |  |  |  | 3 | 4 | 4 | 11 | 48 |  | 0.4 |  | 38000
TR | 2 | Concora Road | Old K | XX | 0.8 | 22.7 |  | 0.8 |  |  |  | 3 | 3 | 5 | 11 | 45 |  | 0.8 |  | 76000
TR | 2 | High Lake Road |  |  | 3.8 | 26.5 |  | 1.3 |  |  |  | 3 | 3 | 5 | 11 | 45 |  | 1.1 | 0.7 | 331300 |  |  |  |  | Between Allen and Ridge is okay, Chip ridge to end, asphalt loop leg
TR | 2 | Old K Road | CTY M, Main Street | CTYK East | 2.79 | 29.29 |  | 2.79 |  | 1969, 1991 |  | 3 | 3 | 5 | 11 | 45 |  | 2.79 |  | 397575 |  |  |  |  | widen 8' for bike loop (Asphalt??)
TR | 3 | Dairymens Road | CTY M North | XX | 1.55 | 30.84 |  | 1.55 |  | 1973, 1988 |  | 4 | 5 | 2 | 11 | 40 |  |  | 1.55 | 502200 |  |  |  |  | Asphalt to benefit Dairymens and Bike loop, widen 8'
TR | 1 | Oswego-Fishtrap Lake Road | CTY M North, High-FT Lake Rd | Fishtrap Road | 1.9 | 32.74 |  | 1.9 |  |  |  | 4 | 5 | 2 | 11 | 40 |  | 0 |  | 0
TR | 1 | South Town Line | US 51 North | XX | 1.36 | 34.1 |  | 1.36 |  | 1976, 1988 |  | 4 | 5 | 2 | 11 | 40 |  | 0 |  | 0
TR | 2 | Bakken Road (East) | CTY H | HWY 51 N | 1.07 | 35.17 |  | 1.07 |  | 67,68 |  | 3 | 3 | 4 | 10 | 36 |  | 1.07 |  | 101650 |  |  |  |  | Asphalt upgrade??
TR | 3 | Highland Drive | CTY K West | CTY M North | 0.28 | 35.45 |  | 0.28 |  | 1976, 1990 |  | 3 | 3 | 4 | 10 | 36 |  |  | 0.28 | 60480 |  |  |  |  | Upgrade for Bike Loop and Event Bypass support
TR | 2 | Rudolph Lake Lane | CTY H | XX | 0.6 | 36.05 |  | 0.6 |  |  |  | 3 | 4 | 3 | 10 | 36 |  | 0.6 |  | 57000
TR | 2 | Wool Lake Lane | CTY K West | XX | 0.76 | 36.81 |  | 0.76 |  | 1967, 1972, 1983 |  | 3 | 3 | 4 | 10 | 36 |  | 0.76 |  | 72200
TR | 1 | North Town Line Rd (Town Road 116) | US 51 North | Le Fave Rd, Island Lake Rd | 1 | 37.81 |  | 1 |  | 1991 |  | 4 | 4 | 2 | 10 | 32 |  | 0 |  | 0
TR | 2 | Harmony Point Lane | US 51 North | between M and H | 0.6 | 38.41 |  | 0.6 |  | 1974, 1982 |  | 2 | 3 | 5 | 10 | 30 |  | 0.6 |  | 57000 |  |  |  |  | narrow road
TR | 2 | Shore Drive | CTY K West | Newcomb Lane | 1.03 | 39.44 |  | 1.03 |  | 1991 |  | 2 | 3 | 5 | 10 | 30 |  | 1.03 |  | 97850
TR | 1 | Bakken Road (West) | CTY H | HWY 51 N | 2.15 | 41.59 |  | 2.15 |  |  |  | 3 | 3 | 3 | 9 | 27 |  | 0 |  | 0
TR | 2 | La Fave Road | US 51 North | Island Lake Road | 1.24 | 42.83 |  | 1.24 |  | 1970 |  | 3 | 3 | 3 | 9 | 27 |  | 0.25 |  | 23750 |  |  |  |  | Northwest segment only
TR | 1 | Ben Bendrick Drive (Lake Shore Drive) | CTY M South | XX | 1.7 | 44.53 |  |  | 1.7 |  |  | 4 | 3 | 2 | 9 | 24 |  |  | 0 | 0
TR | 2 | Green Street | CTY M | Old K | 0.27 | 44.8 |  | 0.27 |  |  |  | 4 | 2 | 3 | 9 | 24 |  | 0.27 |  | 25650
TR | 2 | High Pines Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln | 1.1 | 45.9 |  | 1.1 |  | 1978 |  | 3 | 4 | 2 | 9 | 24 |  | 1.1 |  | 104500 |  |  |  |  | needs improved turn around area
TR | 2 | Lucas Lane | CTY K West | XX | 0.15 | 46.05 |  | 0.15 |  | 1971 |  | 2 | 2 | 5 | 9 | 20 |  | 0.15 |  | 14250 |  |  |  |  | paved to start of campground
TR | 2 | Arrowhead Drive | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road | 0.6 | 46.65 | 0.15 | 0.45 |  | 82, 88 |  | 2 | 3 | 3 | 8 | 18 |  | 0.6 |  | 51750 |  |  |  |  | turn around work
TR | 2 | Evergreen Lane | CTY K West | XX | 1.98 | 48.63 |  | 1.98 |  | 1974 |  | 3 | 2 | 3 | 8 | 18 |  | 1.98 |  | 188100 |  |  |  |  | check condition
TR | 2 | Mann Lake Road | CTY M South | XX | 0.75 | 49.38 |  | 0.75 |  | 1973, 1990 |  | 2 | 3 | 3 | 8 | 18 |  | 0.65 |  | 61750 |  |  |  |  | first .1m ok, no turn around
TR | 2 | Middle Gresham Lane | US 51 North (near H) | XX | 0.43 | 49.81 |  | 0.43 |  |  |  | 2 | 3 | 3 | 8 | 18 |  | 0.43 |  | 40850
TR | 2 | Keego Road | CTY K West | XX | 1.25 | 51.06 |  | 1.25 |  | 1984 |  | 2 | 2 | 4 | 8 | 16 | 0 | 1.25 |  | 118750
TR | 2 | Little Rice Lane | CTY M North | XX | 0.28 | 51.34 |  | 0.28 |  |  |  | 2 | 2 | 4 | 8 | 16 |  | 0.28 |  | 26600
TR | 2 | Rintlemen | CTY K West | Fallon Road | 0.6 | 51.94 |  | 0.6 |  |  |  | 2 | 2 | 4 | 8 | 16 |  | 0.6 |  | 57000
TR | 2 | Boulder Lane | CTY M North | XX | 0.4 | 52.34 |  | 0.4 |  |  |  | 1 | 3 | 4 | 8 | 12 |  | 0.4 |  | 38000
TR | 4 | Camp Manitowish Lane (East) | CTY K West | XX | 0.5 | 52.84 | 0.5 |  |  |  |  | 2 | 2 | 3 | 7 | 12 |  | 0.5 |  | 30000 |  |  |  |  | pave it since CMW will be carrying big tax bill
TR | 6 | Clear View Drive | CTY K West | Fallon Road | 0.34 | 53.18 | 0.34 |  |  |  |  | 3 | 2 | 2 | 7 | 12 | 0 |  |  | 0 |  |  |  |  | good condition, consider paving all or part
TR | 4 | Grahl Lane | CTY H | XX | 0.43 | 53.61 | 0.43 |  |  |  |  | 3 | 2 | 2 | 7 | 12 |  | 0.43 |  | 25800
TR | 5 | Nebish lake Road | CTY K West | XX | 1.97 | 55.58 | 1.97 |  |  |  |  | 4 | 1 | 3 | 8 | 12 | 1.97 |  |  | 78800
TR | 5 | Old 51 Road (Bakken Rd - Island Lake Rd) | CTY H, Bakken Rd (east) | US 51 N, Island Lake Rd | 1.8 | 57.38 | 1.8 |  |  | 1980 |  | 2 | 2 | 3 | 7 | 12 | 1.8 |  |  | 72000 |  |  |  |  | snowmobile %
TR | 5 | Ridge Lane | CTY M North, High-FT Lake Rd | High Lake Rd | 1.2 | 58.58 | 0.3 | 0.9 |  | 1983 |  | 3 | 4 | 1 | 8 | 12 | 0.3 | 0 |  | 12000
TR | 1 | Bear Lake Road | CTY K West | XX | 3.26 | 61.84 |  |  | 3.26 | 1971, 1974, 1986 | 2015 | 3 | 3 | 1 | 7 | 9 |  |  | 0 | 0 |  |  |  |  | repaved with asphalt in 2015
TR | 5 | Dam Road | CTY M North | High-Fishtrap Lake Road | 0.8 | 62.64 | 0.8 |  |  |  |  | 3 | 1 | 3 | 7 | 9 | 0.8 |  |  | 32000
TR | 2 | Glen Lake Road | CTY K West | Shamrock Road | 0.25 | 62.89 |  | 0.25 |  | 1988 |  | 1 | 3 | 3 | 7 | 9 |  | 0.25 |  | 23750
TR | 5 | Nixon Lake Road | CTY K East | XX | 2.6 | 65.49 | 2.6 |  |  |  |  | 3 | 1 | 3 | 7 | 9 | 2.6 |  |  | 104000 |  |  |  |  | Seek cost share with DNR
TR | 1 | Old 51 Road (Town Line - Island Lake Rd) | US 51 North | Town Line Rd, Island lake Rd | 1.07 | 66.56 |  | 1.07 |  |  |  | 3 | 1 | 3 | 7 | 9 |  | 0 |  | 0
TR | 1 | Rustic Colony Lane | CTY M North | Airport Road | 0.27 | 66.83 |  | 0.27 |  |  |  | 1 | 3 | 3 | 7 | 9 | 0 | 0 |  | 0
TR | 4 | Airport Road (gravel) |  |  | 1 | 67.83 | 1 |  |  |  |  | 2 | 1 | 4 | 7 | 8 | 0 | 1 | 0 | 60000 |  |  |  |  | Pave one mike of gravel to complete bike trail loop
TR | 1 | Camp Manitowish Lane (West) | CTY K West | XX | 0.5 | 68.33 |  | 0.5 |  |  |  | 2 | 2 | 2 | 6 | 8 |  | 0 |  | 0
TR | 4 | Platinum Lane | CTY H | Grahl Lane | 0.23 | 68.56 | 0.23 |  |  |  |  | 2 | 2 | 2 | 6 | 8 |  | 0.23 |  | 13800
TR | 1 | Rocky Reef Lane | CTY M South | CTY N West | 0.54 | 69.1 |  | 0.54 |  | 1982, 1992 |  | 2 | 2 | 2 | 6 | 8 |  | 0 |  | 0 |  |  |  |  | poor turn around area
TR | 2 | Stiloski Lane | CTY M North, High-FT Lake Rd | Fishtrap Road | 0.37 | 69.47 |  | 0.37 |  | 1975 |  | 1 | 2 | 4 | 7 | 8 |  | 0.37 |  | 35150
TR | 4 | Sunset Lane | CTY M South, North Creek Rd | Kern lane, Trout lane | 0.3 | 69.77 | 0.3 |  |  |  |  | 1 | 2 | 4 | 7 | 8 | 0 | 0.3 |  | 18000 |  |  |  |  | gravel, is this a town road? Pave it??
TR |  | Town Road 119 (Clear View) | CTY K West, Fallon Rd | Clear View Drive | 0.14 | 69.91 | 0.25 |  |  |  |  | 2 | 2 | 2 | 6 | 8 |  |  | 0 | 0
TR | 2 | Trout Lane | CTY M South, North Creek Rd | Kern lane | 0.2 | 70.11 |  | 0.2 |  |  |  | 1 | 2 | 4 | 7 | 8 |  | 0.2 |  | 19000
TR | 2 | Whitney Lake Road | CTY K West | XX | 1 | 71.11 | 0.1 | 0.9 |  |  |  | 1 | 2 | 4 | 7 | 8 |  | 1 |  | 91500
TR | 1 | Nichols Lake Lane | CTY H | CTY K West | 0.63 | 71.74 |  | 0.63 |  |  |  | 2 | 1 | 3 | 6 | 6 |  | 0 |  | 0
TR | 2 | Pine Lane | US 51 North | Bakken Road (west) | 0.45 | 72.19 |  | 0.45 |  | 1984 |  | 1 | 2 | 3 | 6 | 6 |  | 0.45 |  | 42750 |  |  |  |  | no turn around
TR | 6 | Point Lane | CTY K West | Fallon Rd, Rintleman Rd | 0.25 | 72.44 | 0.25 |  |  |  |  | 1 | 2 | 3 | 6 | 6 | 0 |  |  | 0 |  |  |  |  | Good condition, Consider Paving?
TR | 4 | South Shore Bay Lane | US 51 North | Island Lake Road | 0.15 | 72.59 | 0.15 |  |  |  |  | 1 | 2 | 3 | 6 | 6 |  | 0.15 |  | 6000
TR | 2 | Cattail Cove Lane | CTY K West | XX | 0.75 | 73.34 |  | 0.75 |  | 1992 |  | 1 | 1 | 5 | 7 | 5 |  | 0.75 |  | 71250
TR | 2 | Major Road | CTY M North | Dairymen's Road | 0.5 | 73.84 |  | 0.5 |  | 1973 |  | 1 | 1 | 5 | 7 | 5 |  | 0.5 |  | 47500 |  |  |  |  | road to nowhere, pave only if benefit to Dairymen's
0 | 5 | North Oswego Lake Road | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road | 0.24 | 74.08 | 0.24 |  |  | 1991 |  | 1 | 1 | 5 | 7 | 5 | 0.24 |  |  | 9600
TR | 2 | Sherry Drive | CTY M North, High-FT Lake Rd | High Lake Road | 0.05 | 74.13 |  | 0.05 |  |  |  | 1 | 1 | 5 | 7 | 5 |  | 0.05 |  | 4750
TR | 2 | Spruce Drive | CTY M North, High-FT Lake Rd | High Lake Road | 0.22 | 74.35 |  | 0.22 |  |  |  | 1 | 1 | 5 | 7 | 5 |  | 0.22 |  | 20900 |  |  |  |  | create turn-arounds at each end
TR | 2 | Allequash Lake Road | CTY M South | XX | 0.94 | 75.29 |  | 0.94 |  |  |  | 2 | 0.5 | 4 | 6.5 | 4 |  | 0.94 |  | 89300
TR | 2 | Annes Place | Old K | Green Street | 0.14 | 75.43 |  | 0.14 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0.14 |  | 13300
TR | 1 | Birchwood Lane | CTY M North | Airport Road | 0.36 | 75.79 |  | 0.36 |  | 1984 |  | 1 | 2 | 2 | 5 | 4 |  | 0 |  | 0
TR | 4 | Blue Heron Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead | 0.12 | 75.91 | 0.12 |  |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.12 |  | 7200
TR | 1 | Blueberry Lane | Main Street, CTY K West | Center Street | 0.25 | 76.16 |  | 0.25 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0 |  | 0
TR | 2 | Campo Fiesta Lane | CTY M South | North Creek Road | 0.13 | 76.29 |  | 0.13 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.13 |  | 12350
TR | 1 | Center Street | CTY M South, Park Street | Marsh Rd, Ada, Blueberry | 0.31 | 76.6 |  | 0.31 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0 |  | 0
TR | 2 | Church Street | Old K | Green Street | 0.14 | 76.74 |  | 0.14 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0.14 |  | 13300
TR | 2 | Dolittle Road | CTY M North | Boulder Lane | 0.15 | 76.89 |  | 0.15 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.15 |  | 14250 |  |  |  |  | make widening part of agreement with owners, doable
TR | 2 | East Fitzgerald Lane | US 51 N, Island lake Rd | Fitzgerald Lane | 0.11 | 77 |  | 0.11 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.11 |  | 10450
TR | 2 | Fitzgerald Lane | US 51 North | Island Lake Road | 0.2 | 77.2 |  | 0.2 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.2 |  | 19000
TR | 4 | Little Crooked Lane | CTY K West | Bear Lake Road | 0.38 | 77.58 | 0.38 |  |  |  |  | 1 | 2 | 2 | 5 | 4 |  | 0.38 |  | 22800
TR | 1 | Town Hall Road | Around Community Building |  | 0.12 | 77.7 |  |  | 0.12 | 1987 |  | 4 | 1 | 1 | 6 | 4 |  |  |  | 0
TR | 4 | White Deer Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead | 0.12 | 77.82 | 0.12 |  |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.12 |  | 4800
TR | 4 | Balsam Lane | US 51 North | Bakken Road (west) | 0.35 | 78.17 | 0.35 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.35 |  | 21000 |  |  |  |  | no turn around
TR | 5 | Bass Lake Road | CTY K West | Bear Lake Road | 0.41 | 78.58 | 0.41 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.41 |  |  | 16400
TR | 5 | Birch Point Lane | CTY K West | Bear Lake Road | 0.19 | 78.77 | 0.19 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.19 |  |  | 7600
TR | 2 | Charlotte Place Lane | US 51 North | XX | 0.25 | 79.02 |  | 0.25 |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.25 |  | 23750
TR | 4 | En-Dah Win Lane | CTY K East | XX | 0.15 | 79.17 | 0.15 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.1 |  | 6000 |  |  |  |  | only pave to T
TR | 5 | Halverson Lane | CTY M South | XX | 0.12 | 79.29 | 0.12 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.12 |  |  | 4800
TR | 1 | Kassien Lane | US 51 North | Island Lake Road | 0.54 | 79.83 |  | 0.54 |  |  |  | 1 | 1 | 3 | 5 | 3 |  |  |  | 0
TR | 4 | Partridge Lane | CTY M North, High-FT Lake Rd | High Lake Road | 1.1 | 80.93 | 1.1 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 1.1 |  | 66000
TR | 4 | Perch Lane | CTY M South (by N) |  | 0.23 | 81.16 | 0.23 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.23 |  | 21850 |  |  |  |  | no turn around
TR | 5 | Pine Shores Lane | US 51 North | Bakken Road (west) | 0.06 | 81.22 | 0.06 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.06 |  |  | 2400
TR | 4 | Pinewood Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln | 0.12 | 81.34 | 0.12 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.12 |  | 7200
TR | 2 | Red Fox Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead | 0.09 | 81.43 |  | 0.09 |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.09 |  | 8550
TR | 1 | Senior Drive | CTY M, Park Street | Green Street | 0.2 | 81.63 |  | 0.2 |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0 |  | 0
TR | 6 | Street Lake Lane | CTY H | XX | 0.65 | 82.28 | 0.65 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  |  |  | 0 |  |  |  |  | do we want to pave??
TR | 5 | White Birch Lane | CTY M North, High-FT Lake Rd | Osewgo-FT Lake Road | 0.45 | 82.73 | 0.45 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.45 |  |  | 18000
TR | 6 | Keego Road East | CTY K West, Bear lake Road | Keego Road | 1.31 | 84.04 | 1.31 |  |  |  |  | 1 | 0.5 | 5 | 6.5 | 2.5 |  | 0 |  | 0
TR | 6 | Old Flambeau Road | CTY H?? | Bakken Rd ?? | 0.74 | 84.78 | 0.74 |  |  |  |  | 0.5 | 1 | 5 | 6.5 | 2.5 | 0 |  |  | 0 |  |  |  |  | No signs, looks like snowmobile trail, barely a road
TR | 1 | Ada Street | CTY M | Main Street | 0.25 | 85.03 |  | 0.25 |  |  | <10 | 1 | 1 | 2 | 4 | 2 |  | 0 |  | 0
TR | 6 | Birch Drive | CTY M North, High-FT Lake Rd | High Lake Road | 0.25 | 85.28 | 0.25 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 0 |  |  | 0
TR | 1 | Blaisdell Street | Main Street, CTY K West | Ada, Blueberry | 0.17 | 85.45 |  | 0.17 |  |  |  | 1 | 1 | 2 | 4 | 2 |  | 0 |  | 0
TR | 1 | Community Street | CTY K West | Blaisdell Street | 0.2 | 85.65 |  | 0.2 |  |  |  | 1 | 1 | 2 | 4 | 2 |  | 0 |  | 0
TR | 5 | Maple Lake Road | CTY K West | XX | 0.35 | 86 | 0.35 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 0.35 |  |  | 14000
TR | 2 | Reible Court | Old K | XX | 0.12 | 86.12 |  | 0.12 |  |  |  | 1 | 1 | 2 | 4 | 2 |  | 0.12 |  | 11400
TR | 6 | River lane | CTY K West | XX | 0.2 | 86.32 | 0.2 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 0 |  |  | 0
TR | 6 | South Rudolph Lake Lane | CTY H | Rudolph Lake Lane | 0.26 | 86.58 | 0.26 |  |  | 1987 |  | 1 | 1 | 2 | 4 | 2 |  |  |  | 0
TR | 5 | West Big Lake Road (lane) | CTY K West | XX | 1.04 | 87.62 | 1.04 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 1.04 |  |  | 41600 |  |  |  |  | one house, why is this a town road?
TR | 5 | Boat Landing Road (Island lake) | US 51 North | Island Lake Road | 0.5 | 88.12 | 0.5 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 0.5 |  |  | 20000
TR | 1 | Day Lake Landing Road | Day Lake Road | XXX | 0.22 | 88.34 | 0.22 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 0 |  |  | 0
TR | 5 | Day Lake Road | North Creek Road | US 51 North | 2.91 | 91.25 | 2.91 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 2.91 |  |  | 58200 |  |  |  |  | Basic work, not full gravel work up
TR | 4 | Marsh Road | CTY M South | CTY K West | 1.04 | 92.29 | 1.04 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 |  | 1.04 |  | 62400 |  |  |  |  | Create Bike bypass for through riders, better use of events
TR | 6 | Vandercook Road | CTY M South | XX | 0.08 | 92.37 | 0.08 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 0 |  |  | 0 |  |  |  |  | trapped between Arbor Vitae roads, snowmobile trail 100%
TR | 1 | Good Life Lane | CTY M North | Airport Road | 0.44 | 92.81 |  |  | 0.44 |  |  | 1 | 1 | 1 | 3 | 1 |  |  | 0 | 0
TR | 6 | Jag Lake Road | CTY H | XX | 0.08 | 92.89 | 0.08 |  |  |  |  | 1 | 0.5 | 2 | 3.5 | 1 |  | 0 |  | 0 |  |  |  |  | boat landing
TR | 1 | Round Lake Road | CTY K West | Bear Lake Road | 0.1 | 92.99 |  | 0.1 |  |  |  | 1 | 0.5 | 2 | 3.5 | 1 |  | 0 |  | 0
TR | 1 | Cemetary Road | CTY K West | XX | 0.18 | 93.17 |  | 0.18 |  |  |  | 1 | 0.5 | 1 | 2.5 | 0.5 |  | 0 |  | 0
TR | 0 | Old 51 East Hoffman Road |  | 0.26 | [10 empty] | 0
TR | 0 | Old 51 Old H |  | 1.17 | [10 empty] | 0
TR | 1 | Round Lake Road (Presque Isle) | CTY K West | Bear Lake Road | 1.25 |  |  | 1.25 | [6 empty] | 0 |  |  | 0 |  | 0
TR |  | Town Road 127 |  |  | 0.1 | [9 empty] | 0
TR |  | Town Road 133 |  |  | 0.15 | [9 empty] | 0
[5 empty] | 93.17 |  | 26.04 | 56.27 | 7.47 | [7 empty] | 13.74 | 34.56 | 15.86 | 7481675 |  |  |  |  | TOTAL ESTIMATED COST
[8 empty] | Town Road Mileage | 89.78 | [7 empty] | Improvement Mileage |  | 64.16
[17 empty] | Percent of Total Mileage |  | 71.46%
COLOR KEY
[7 empty] | 1 | Recently Updated, Or in Good Condition - No work planned
[7 empty] | 2 | Paved Road, repaving planned, same surface
[7 empty] | 3 | Paved Road, repaving planned, new surface
[7 empty] | 4 | Existing Gravel Road, planned upgrade to pavement
[7 empty] | 5 | Existing Gravel Road, general grading and gravel
[7 empty] | 6 | Existing Gravel Road/Fire Road - No Plans
PAVING COST PER MILE
|  |  |  | Existing Surface | Gravel | Chip Seal | Asphalt
|  | Gravel |  | GRAVEL | 40000 | 60000 | 197000
|  | Chip Seal |  | CHIP SEAL | 40000 | 95000 | 216000
|  | Asphalt |  | ASPHALT | 40000 | 95000 | 216000
Note on H146: Greg Van Grinsven: Add $19,000 per mile to pulverize chip seal or asphalt material.
Note on H147: Greg Van Grinsven: Add $19,000 per mile to pulverize chip seal or asphalt material.

## Roads-CatPavementType
03_02_17 | PLAN |  |  |  | Length |  |  | SURFACE TYPE |  |  |  | RATING |  |  |  |  | RESURFACE PLAN |  |  | RESURFACE |  | Work Scope |  | Extra Work | Category
TYPE | CAT | ROAD NAME | Primary Access Road | Secondary Access Road | Miles | Accum. | Gravel | Chip | Asphalt | Seal Coated or Resurfaced |  | Traffic | Occupancy | Condition | Priority | Weighted | Gravel | Chip | Asphalt | COST EST | Surface | Engrg | Extra | Description | Cost | COMMENTS
TR | 1 | Airport Road (paved) | CTY M North | Dairymen's Road | 2.45 | 2.45 |  |  | 1.45 | 1969, 1984 |  | 5 | 5 | 2 | 12 | 50 |  |  | 0 | 0
TR | 1 | Oswego-Fishtrap Lake Road | CTY M North, High-FT Lake Rd | Fishtrap Road | 1.9 | 4.35 |  | 1.9 |  |  |  | 4 | 5 | 2 | 11 | 40 |  | 0 |  | 0
TR | 1 | South Town Line | US 51 North | XX | 1.36 | 5.71 |  | 1.36 |  | 1976, 1988 |  | 4 | 5 | 2 | 11 | 40 |  | 0 |  | 0
TR | 1 | North Town Line Rd (Town Road 116) | US 51 North | Le Fave Rd, Island Lake Rd | 1 | 6.71 |  | 1 |  | 1991 |  | 4 | 4 | 2 | 10 | 32 |  | 0 |  | 0
TR | 1 | Bakken Road (West) | CTY H | HWY 51 N | 2.15 | 8.86 |  | 2.15 |  |  |  | 3 | 3 | 3 | 9 | 27 |  | 0 |  | 0
TR | 1 | Ben Bendrick Drive (Lake Shore Drive) | CTY M South | XX | 1.7 | 10.56 |  |  | 1.7 |  |  | 4 | 3 | 2 | 9 | 24 |  |  | 0 | 0
TR | 1 | Bear Lake Road | CTY K West | XX | 3.26 | 13.82 |  |  | 3.26 | 1971, 1974, 1986 | 2015 | 3 | 3 | 1 | 7 | 9 |  |  | 0 | 0 | [5 empty] | repaved with asphalt in 2015
TR | 1 | Old 51 Road (Town Line - Island Lake Rd) | US 51 North | Town Line Rd, Island lake Rd | 1.07 | 14.89 |  | 1.07 |  |  |  | 3 | 1 | 3 | 7 | 9 |  | 0 |  | 0
TR | 1 | Rustic Colony Lane | CTY M North | Airport Road | 0.27 | 15.16 |  | 0.27 |  |  |  | 1 | 3 | 3 | 7 | 9 |  | 0 |  | 0
TR | 1 | Camp Manitowish Lane (West) | CTY K West | XX | 0.5 | 15.66 |  | 0.5 |  |  |  | 2 | 2 | 2 | 6 | 8 |  | 0 |  | 0
TR | 1 | Rocky Reef Lane | CTY M South | CTY N West | 0.54 | 16.2 |  | 0.54 |  | 1982, 1992 |  | 2 | 2 | 2 | 6 | 8 |  | 0 |  | 0 | [5 empty] | poor turn around area
TR | 1 | Nichols Lake Lane | CTY H | CTY K West | 0.63 | 16.83 |  | 0.63 |  |  |  | 2 | 1 | 3 | 6 | 6 |  | 0 |  | 0
TR | 1 | Town Hall Road | Around Community Building |  | 0.12 | 16.95 |  |  | 0.12 | 1987 |  | 4 | 1 | 1 | 6 | 4 |  |  |  | 0
TR | 1 | Birchwood Lane | CTY M North | Airport Road | 0.36 | 17.31 |  | 0.36 |  | 1984 |  | 1 | 2 | 2 | 5 | 4 |  | 0 |  | 0
TR | 1 | Blueberry Lane | Main Street, CTY K West | Center Street | 0.25 | 17.56 |  | 0.25 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0 |  | 0
TR | 1 | Center Street | CTY M South, Park Street | Marsh Rd, Ada, Blueberry | 0.31 | 17.87 |  | 0.31 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0 |  | 0
TR | 1 | Kassien Lane | US 51 North | Island Lake Road | 0.54 | 18.41 |  | 0.54 |  |  |  | 1 | 1 | 3 | 5 | 3 |  |  |  | 0
TR | 1 | Senior Drive | CTY M, Park Street | Green Street | 0.2 | 18.61 |  | 0.2 |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0 |  | 0
TR | 1 | Day Lake Landing Road | Day Lake Road | XXX | 0.22 | 18.83 | 0.22 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 0 |  |  | 0
TR | 1 | Ada Street | CTY M | Main Street | 0.25 | 19.08 |  | 0.25 |  |  | <10 | 1 | 1 | 2 | 4 | 2 |  | 0 |  | 0
TR | 1 | Blaisdell Street | Main Street, CTY K West | Ada, Blueberry | 0.17 | 19.25 |  | 0.17 |  |  |  | 1 | 1 | 2 | 4 | 2 |  | 0 |  | 0
TR | 1 | Community Street | CTY K West | Blaisdell Street | 0.2 | 19.45 |  | 0.2 |  |  |  | 1 | 1 | 2 | 4 | 2 |  | 0 |  | 0
TR | 1 | Round Lake Road | CTY K West | Bear Lake Road | 0.1 | 19.55 |  | 0.1 |  |  |  | 1 | 0.5 | 2 | 3.5 | 1 |  | 0 |  | 0
TR | 1 | Good Life Lane | CTY M North | Airport Road | 0.44 | 19.99 |  |  | 0.44 |  |  | 1 | 1 | 1 | 3 | 1 |  |  | 0 | 0
TR | 1 | Cemetary Road | CTY K West | XX | 0.18 | 20.17 |  | 0.18 |  |  |  | 1 | 0.5 | 1 | 2.5 | 0.5 |  | 0 |  | 0
| Current | 20.17
TR | 2 | Island Lake Road | US 51 North | XX | 1.28 | 21.45 |  | 1.28 |  | 1987 |  | 4 | 5 | 4 | 13 | 80 |  | 1.28 |  | 121600
TR | 2 | Kern Lane | CTY m South | North Creek Road | 1.1 | 22.55 |  | 1.1 |  |  |  | 3 | 4 | 5 | 12 | 60 |  | 1.1 |  | 104500
TR | 2 | Shamrock Lane | CTY K West | Highland Drive | 0.4 | 22.95 |  | 0.4 |  |  |  | 3 | 4 | 4 | 11 | 48 |  | 0.4 |  | 38000
TR | 2 | Concora Road | Old K | XX | 0.8 | 23.75 |  | 0.8 |  |  |  | 3 | 3 | 5 | 11 | 45 |  | 0.8 |  | 76000
TR | 2 | Old K Road | CTY M, Main Street | CTYK East | 2.79 | 26.54 |  | 2.79 |  | 1969, 1991 |  | 3 | 3 | 5 | 11 | 45 |  | 2.79 |  | 397575 | [5 empty] | widen 8' for bike loop (Asphalt??)
TR | 2 | Bakken Road (East) | CTY H | HWY 51 N | 1.07 | 27.61 |  | 1.07 |  | 67,68 |  | 3 | 3 | 4 | 10 | 36 |  | 1.07 |  | 101650 | [5 empty] | Asphalt upgrade??
TR | 2 | Rudolph Lake Lane | CTY H | XX | 0.6 | 28.21 |  | 0.6 |  |  |  | 3 | 4 | 3 | 10 | 36 |  | 0.6 |  | 57000
TR | 2 | Wool Lake Lane | CTY K West | XX | 0.76 | 28.97 |  | 0.76 |  | 1967, 1972, 1983 |  | 3 | 3 | 4 | 10 | 36 |  | 0.76 |  | 72200
TR | 2 | Harmony Point Lane | US 51 North | between M and H | 0.6 | 29.57 |  | 0.6 |  | 1974, 1982 |  | 2 | 3 | 5 | 10 | 30 |  | 0.6 |  | 57000 | [5 empty] | narrow road
TR | 2 | Shore Drive | CTY K West | Newcomb Lane | 1.03 | 30.6 |  | 1.03 |  | 1991 |  | 2 | 3 | 5 | 10 | 30 |  | 1.03 |  | 97850
TR | 2 | La Fave Road | US 51 North | Island Lake Road | 1.24 | 31.84 |  | 1.24 |  | 1970 |  | 3 | 3 | 3 | 9 | 27 |  | 0.25 |  | 23750 | [5 empty] | Northwest segment only
TR | 2 | Green Street | CTY M | Old K | 0.27 | 32.11 |  | 0.27 |  |  |  | 4 | 2 | 3 | 9 | 24 |  | 0.27 |  | 25650
TR | 2 | High Pines Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln | 1.1 | 33.21 |  | 1.1 |  | 1978 |  | 3 | 4 | 2 | 9 | 24 |  | 1.1 |  | 104500 | [5 empty] | needs improved turn around area
TR | 2 | Lucas Lane | CTY K West | XX | 0.15 | 33.36 |  | 0.15 |  | 1971 |  | 2 | 2 | 5 | 9 | 20 |  | 0.15 |  | 14250 | [5 empty] | paved to start of campground
TR | 2 | Arrowhead Drive | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road | 0.6 | 33.96 | 0.15 | 0.45 |  | 82, 88 |  | 2 | 3 | 3 | 8 | 18 |  | 0.6 |  | 51750 | [5 empty] | turn around work
TR | 2 | Evergreen Lane | CTY K West | XX | 1.98 | 35.94 |  | 1.98 |  | 1974 |  | 3 | 2 | 3 | 8 | 18 |  | 1.98 |  | 188100 | [5 empty] | check condition
TR | 2 | Mann Lake Road | CTY M South | XX | 0.75 | 36.69 |  | 0.75 |  | 1973, 1990 |  | 2 | 3 | 3 | 8 | 18 |  | 0.65 |  | 61750 | [5 empty] | first .1m ok, no turn around
TR | 2 | Middle Gresham Lane | US 51 North (near H) | XX | 0.43 | 37.12 |  | 0.43 |  |  |  | 2 | 3 | 3 | 8 | 18 |  | 0.43 |  | 40850
TR | 2 | Keego Road | CTY K West | XX | 1.25 | 38.37 |  | 1.25 |  | 1984 |  | 2 | 2 | 4 | 8 | 16 |  | 1.25 |  | 118750
TR | 2 | Little Rice Lane | CTY M North | XX | 0.28 | 38.65 |  | 0.28 |  |  |  | 2 | 2 | 4 | 8 | 16 |  | 0.28 |  | 26600
TR | 2 | Rintlemen | CTY K West | Fallon Road | 0.6 | 39.25 |  | 0.6 |  |  |  | 2 | 2 | 4 | 8 | 16 |  | 0.6 |  | 57000
TR | 2 | Boulder Lane | CTY M North | XX | 0.4 | 39.65 |  | 0.4 |  |  |  | 1 | 3 | 4 | 8 | 12 |  | 0.4 |  | 38000
TR | 2 | Glen Lake Road | CTY K West | Shamrock Road | 0.25 | 39.9 |  | 0.25 |  | 1988 |  | 1 | 3 | 3 | 7 | 9 |  | 0.25 |  | 23750
TR | 2 | Stiloski Lane | CTY M North, High-FT Lake Rd | Fishtrap Road | 0.37 | 40.27 |  | 0.37 |  | 1975 |  | 1 | 2 | 4 | 7 | 8 |  | 0.37 |  | 35150
TR | 2 | Trout Lane | CTY M South, North Creek Rd | Kern lane | 0.2 | 40.47 |  | 0.2 |  |  |  | 1 | 2 | 4 | 7 | 8 |  | 0.2 |  | 19000
TR | 2 | Whitney Lake Road | CTY K West | XX | 1 | 41.47 | 0.1 | 0.9 |  |  |  | 1 | 2 | 4 | 7 | 8 |  | 1 |  | 91500
TR | 2 | Cattail Cove Lane | CTY K West | XX | 0.75 | 42.22 |  | 0.75 |  | 1992 |  | 1 | 1 | 5 | 7 | 5 |  | 0.75 |  | 71250
TR | 2 | Major Road | CTY M North | Dairymen's Road | 0.5 | 42.72 |  | 0.5 |  | 1973 |  | 1 | 1 | 5 | 7 | 5 |  | 0.5 |  | 47500 | [5 empty] | road to nowhere, pave only if benefit to Dairymen's
TR | 2 | Sherry Drive | CTY M North, High-FT Lake Rd | High Lake Road | 0.05 | 42.77 |  | 0.05 |  |  |  | 1 | 1 | 5 | 7 | 5 |  | 0.05 |  | 4750
TR | 2 | Spruce Drive | CTY M North, High-FT Lake Rd | High Lake Road | 0.22 | 42.99 |  | 0.22 |  |  |  | 1 | 1 | 5 | 7 | 5 |  | 0.22 |  | 20900 | [5 empty] | create turn-arounds at each end
TR | 2 | Allequash Lake Road | CTY M South | XX | 0.94 | 43.93 |  | 0.94 |  |  |  | 2 | 0.5 | 4 | 6.5 | 4 |  | 0.94 |  | 89300
TR | 2 | Pine Lane | US 51 North | Bakken Road (west) | 0.45 | 44.38 |  | 0.45 |  | 1984 |  | 1 | 2 | 3 | 6 | 6 |  | 0.45 |  | 42750 | [5 empty] | no turn around
TR | 2 | Campo Fiesta Lane | CTY M South | North Creek Road | 0.13 | 44.51 |  | 0.13 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.13 |  | 12350
TR | 2 | Dolittle Road | CTY M North | Boulder Lane | 0.15 | 44.66 |  | 0.15 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.15 |  | 14250 | [5 empty] | make widening part of agreement with owners, doable
TR | 2 | East Fitzgerald Lane | US 51 N, Island lake Rd | Fitzgerald Lane | 0.11 | 44.77 |  | 0.11 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.11 |  | 10450
TR | 2 | Fitzgerald Lane | US 51 North | Island Lake Road | 0.2 | 44.97 |  | 0.2 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.2 |  | 19000
TR | 2 | Annes Place | Old K | Green Street | 0.14 | 45.11 |  | 0.14 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0.14 |  | 13300
TR | 2 | Church Street | Old K | Green Street | 0.14 | 45.25 |  | 0.14 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0.14 |  | 13300
TR | 2 | Charlotte Place Lane | US 51 North | XX | 0.25 | 45.5 |  | 0.25 |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.25 |  | 23750
TR | 2 | Red Fox Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead | 0.09 | 45.59 |  | 0.09 |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.09 |  | 8550
TR | 2 | Reible Court | Old K | XX | 0.12 | 45.71 |  | 0.12 |  |  |  | 1 | 1 | 2 | 4 | 2 |  | 0.12 |  | 11400
| C&S | 25.54 | [22 empty] | 2446525
TR | 3 | Allen Road | CTY M North | High Lake Road | 0.68 | 46.39 |  | 0.68 |  | 1975, 1990 |  | 5 | 5 | 5 | 15 | 125 |  | 0 | 0.68 | 220320 | [5 empty] | upgrade to asphalt, widen 8' for Bike lanes (White Deer Loop)
TR | 3 | Fishtrap Lake Road | CTY M North, High-FT Lake Rd | XX | 2.04 | 48.43 |  | 2.04 |  | 72,73,75,82,86 |  | 5 | 5 | 5 | 15 | 125 |  | 0.64 | 1.4 | 340800 | [5 empty] | Do we want all or % as Asphalt??? Shown with asphalt to trail corner
TR | 3 | Newcomb Lane | CTY K West | XX | 3.5 | 51.93 |  | 3.5 |  | 78,80,83,88,92 |  | 5 | 5 | 5 | 15 | 125 |  |  | 3.5 | 756000 | [5 empty] | Why Asphalt? Not a high population area like Fishtrap Lake Rd.
TR | 3 | North Creek Road | CTY M South | CTY H | 4.57 | 56.5 |  | 4.57 |  | 75, 76, 87, 92 |  | 5 | 5 | 5 | 15 | 125 |  |  | 4.57 | 987120 | [5 empty] | Possible width increase for Bike Route, Cost share with DNR
TR | 3 | Fallon Road | CTY K West | XX | 2.08 | 58.58 |  | 2.08 |  | 1984, 1986 |  | 5 | 5 | 4 | 14 | 100 |  |  | 2.08 | 449280
TR | 3 | High-Fishtrap Lake Road | CTY M North | XX | 1.1 | 59.68 |  |  | 1.1 |  |  | 5 | 5 | 3 | 13 | 75 |  |  | 1.1 | 356400 | [5 empty] | asphalt for loop, add 8' to width
TR | 3 | High Lake Road |  |  | 3.8 | 63.48 |  | 1.3 |  |  |  | 3 | 3 | 5 | 11 | 45 |  | 1.1 | 0.7 | 331300 | [5 empty] | Between Allen and Ridge is okay, Chip ridge to end, asphalt loop leg
TR | 3 | Dairymens Road | CTY M North | XX | 1.55 | 65.03 |  | 1.55 |  | 1973, 1988 |  | 4 | 5 | 2 | 11 | 40 |  |  | 1.55 | 502200 | [5 empty] | Asphalt to benefit Dairymens and Bike loop, widen 8'
TR | 3 | Highland Drive | CTY K West | CTY M North | 0.28 | 65.31 |  | 0.28 |  | 1976, 1990 |  | 3 | 3 | 4 | 10 | 36 |  |  | 0.28 | 60480 | [5 empty] | Upgrade for Bike Loop and Event Bypass support
| Asphalt | 19.6 | [22 empty] | 4003900
TR | 4 | Big Muskellunge Road | CTY M South | XX | 2.7 | 68.01 | 1.2 | 1 | 0.5 | 1976 |  | 5 | 3 | 4 | 12 | 60 |  | 2.2 |  | 167000
TR | 4 | Grahl Lane | CTY H | XX | 0.43 | 68.44 | 0.43 |  |  |  |  | 3 | 2 | 2 | 7 | 12 |  | 0.43 |  | 25800
TR | 4 | Camp Manitowish Lane (East) | CTY K West | XX | 0.5 | 68.94 | 0.5 |  |  |  |  | 2 | 2 | 3 | 7 | 12 |  | 0.5 |  | 30000 | [5 empty] | pave it since CMW will be carrying big tax bill
TR | 4 | Airport Road (gravel) |  |  | 1 | 69.94 | 1 |  |  |  |  | 2 | 1 | 4 | 7 | 8 |  | 1 |  | 60000 | [5 empty] | Pave one mike of gravel to complete bike trail loop
TR | 4 | Sunset Lane | CTY M South, North Creek Rd | Kern lane, Trout lane | 0.3 | 70.24 | 0.3 |  |  |  |  | 1 | 2 | 4 | 7 | 8 |  | 0.3 |  | 18000 | [5 empty] | gravel, is this a town road? Pave it??
TR | 4 | Platinum Lane | CTY H | Grahl Lane | 0.23 | 70.47 | 0.23 |  |  |  |  | 2 | 2 | 2 | 6 | 8 |  | 0.23 |  | 13800
TR | 4 | South Shore Bay Lane | US 51 North | Island Lake Road | 0.15 | 70.62 | 0.15 |  |  |  |  | 1 | 2 | 3 | 6 | 6 |  | 0.15 |  | 9000
TR | 4 | Blue Heron Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead | 0.12 | 70.74 | 0.12 |  |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.12 |  | 7200
TR | 4 | White Deer Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead | 0.12 | 70.86 | 0.12 |  |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.12 |  | 7200
TR | 4 | Little Crooked Lane | CTY K West | Bear Lake Road | 0.38 | 71.24 | 0.38 |  |  |  |  | 1 | 2 | 2 | 5 | 4 |  | 0.38 |  | 22800
TR | 4 | Balsam Lane | US 51 North | Bakken Road (west) | 0.35 | 71.59 | 0.35 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.35 |  | 21000 | [5 empty] | no turn around
TR | 4 | En-Dah Win Lane | CTY K East | XX | 0.15 | 71.74 | 0.15 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.1 |  | 6000 | [5 empty] | only pave to T
TR | 4 | Partridge Lane | CTY M North, High-FT Lake Rd | High Lake Road | 1.1 | 72.84 | 1.1 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 1.1 |  | 66000
TR | 4 | Perch Lane | CTY M South (by N) |  | 0.23 | 73.07 | 0.23 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.23 |  | 13800 | [5 empty] | no turn around
TR | 4 | Pinewood Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln | 0.12 | 73.19 | 0.12 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.12 |  | 7200
TR | 4 | Marsh Road | CTY M South | CTY K West | 1.04 | 74.23 | 1.04 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 |  | 1.04 |  | 62400 | [5 empty] | Create Bike bypass for through riders, better use of events
| G to C&S | 8.92 | [22 empty] | 537200
TR | 5 | Ridge Lane | CTY M North, High-FT Lake Rd | High Lake Rd | 1.2 | 75.43 | 0.3 | 0.9 |  | 1983 |  | 3 | 4 | 1 | 8 | 12 | 0.3 | 0 |  | 12000 | [5 empty] | Leave .3 gravel to Walt & Donna's, Chip Sealed in 2012
TR | 5 | Nebish lake Road | CTY K West | XX | 1.97 | 77.4 | 1.97 |  |  |  |  | 4 | 1 | 3 | 8 | 12 | 1.97 |  |  | 78800
TR | 5 | Old 51 Road (Bakken Rd - Island Lake Rd) | CTY H, Bakken Rd (east) | US 51 N, Island Lake Rd | 1.8 | 79.2 | 1.8 |  |  | 1980 |  | 2 | 2 | 3 | 7 | 12 | 1.8 |  |  | 72000 | [5 empty] | snowmobile %
TR | 5 | Dam Road | CTY M North | High-Fishtrap Lake Road | 0.8 | 80 | 0.8 |  |  |  |  | 3 | 1 | 3 | 7 | 9 | 0.8 |  |  | 32000
TR | 5 | Nixon Lake Road | CTY K East | XX | 2.6 | 82.6 | 2.6 |  |  |  |  | 3 | 1 | 3 | 7 | 9 | 2.6 |  |  | 104000 | [5 empty] | Seek cost share with DNR
TR | 5 | North Oswego Lake Road | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road | 0.24 | 82.84 | 0.24 |  |  | 1991 |  | 1 | 1 | 5 | 7 | 5 | 0.24 |  |  | 9600
TR | 5 | Bass Lake Road | CTY K West | Bear Lake Road | 0.41 | 83.25 | 0.41 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.41 |  |  | 16400
TR | 5 | Birch Point Lane | CTY K West | Bear Lake Road | 0.19 | 83.44 | 0.19 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.19 |  |  | 7600
TR | 5 | Halverson Lane | CTY M South | XX | 0.12 | 83.56 | 0.12 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.12 |  |  | 4800
TR | 5 | Pine Shores Lane | US 51 North | Bakken Road (west) | 0.06 | 83.62 | 0.06 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.06 |  |  | 2400
TR | 5 | White Birch Lane | CTY M North, High-FT Lake Rd | Osewgo-FT Lake Road | 0.45 | 84.07 | 0.45 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.45 |  |  | 18000
TR | 5 | Boat Landing Road (Island lake) | US 51 North | Island Lake Road | 0.5 | 84.57 | 0.5 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 0.5 |  |  | 20000
TR | 5 | Day Lake Road | North Creek Road | US 51 North | 2.91 | 87.48 | 2.91 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 2.91 |  |  | 58200 | [5 empty] | Basic work, not full gravel work up
TR | 5 | Maple Lake Road | CTY K West | XX | 0.35 | 87.83 | 0.35 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 0.35 |  |  | 14000
TR | 5 | West Big Lake Road (lane) | CTY K West | XX | 1.04 | 88.87 | 1.04 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 1.04 |  |  | 41600 | [5 empty] | one house, why is this a town road?
| Gravel | 14.64 | [22 empty] | 491400
TR | 6 | Clear View Drive | CTY K West | Fallon Road | 0.34 | 89.21 | 0.34 |  |  |  |  | 3 | 2 | 2 | 7 | 12 |  |  |  | 0 | [5 empty] | good condition, consider paving all or part
TR | 6 | Keego Road East | CTY K West, Bear lake Road | Keego Road | 1.31 | 90.52 | 1.31 |  |  |  |  | 1 | 0.5 | 5 | 6.5 | 2.5 |  |  |  | 0
TR | 6 | Old Flambeau Road | CTY H?? | Bakken Rd ?? | 0.74 | 91.26 | 0.74 |  |  |  |  | 0.5 | 1 | 5 | 6.5 | 2.5 |  |  |  | 0 | [5 empty] | No signs, looks like snowmobile trail, barely a road
TR | 6 | Point Lane | CTY K West | Fallon Rd, Rintleman Rd | 0.25 | 91.51 | 0.25 |  |  |  |  | 1 | 2 | 3 | 6 | 6 |  |  |  | 0 | [5 empty] | Good condition, Consider Paving?
TR | 6 | Street Lake Lane | CTY H | XX | 0.65 | 92.16 | 0.65 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  |  |  | 0 | [5 empty] | do we want to pave??
TR | 6 | Vandercook Road | CTY M South | XX | 0.08 | 92.24 | 0.08 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 |  |  |  | 0 | [5 empty] | trapped between Arbor Vitae roads, snowmobile trail 100%
TR | 6 | Birch Drive | CTY M North, High-FT Lake Rd | High Lake Road | 0.25 | 92.49 | 0.25 |  |  |  |  | 1 | 1 | 2 | 4 | 2 |  |  |  | 0
TR | 6 | River lane | CTY K West | XX | 0.2 | 92.69 | 0.2 |  |  |  |  | 1 | 1 | 2 | 4 | 2 |  |  |  | 0
TR | 6 | South Rudolph Lake Lane | CTY H | Rudolph Lake Lane | 0.26 | 92.95 | 0.26 |  |  | 1987 |  | 1 | 1 | 2 | 4 | 2 |  |  |  | 0
TR | 6 | Jag Lake Road | CTY H | XX | 0.08 | 93.03 | 0.08 |  |  |  |  | 1 | 0.5 | 2 | 3.5 | 1 |  |  |  | 0 | [5 empty] | boat landing
TR |  | Town Road 119 (Clear View) | CTY K West, Fallon Rd | Clear View Drive | 0.14 | 93.17 | 0.25 |  |  |  |  | 2 | 2 | 2 | 6 | 8
TR | 0 | Old 51 East Hoffman Road |  | 0.26 | [10 empty] | 0
TR | 0 | Old 51 Old H |  | 1.17 | [10 empty] | 0
TR | 1 | Round Lake Road (Presque Isle) | CTY K West | Bear Lake Road | 1.25 |  |  | 1.25 | [6 empty] | 0 |  |  | 0 |  | 0
TR |  | Town Road 127 |  |  | 0.1 | [9 empty] | 0
TR |  | Town Road 133 |  |  | 0.15 | [9 empty] | 0
Gravel | No Plans | 5.8 | [22 empty] | 0
|  | Town Road Mileage |  |  | 93.17 |  | 26.04 | 55.17 | 8.57 | [7 empty] | 13.74 | 34.56 | 15.86 | 7481675 | [5 empty] | TOTAL ESTIMATED COST
[8 empty] | Town Road Plan Mileage | 89.78 | [5 empty] | Total Improvement Mileage |  |  |  | 64.16
[15 empty] | Percent of Total Mileage |  |  |  | 71.46%
TOWN ROAD IMPROVEMENT SUMMARY
[7 empty] | COLOR KEY | [10 empty] | Miles |  | Cost |  |  |  |  | Cost / Mile
[6 empty] | 1 | Recently Updated, Or in Good Condition - No work planned | [10 empty] | 20.17 |  | 0
[6 empty] | 2 | Paved Road, repaving planned, same surface | [10 empty] | 25.54 |  | 2446525 |  |  |  |  | 95791.8951
[6 empty] | 3 | Paved Road, repaving planned, new surface | [10 empty] | 19.6 |  | 4003900 |  |  |  |  | 204280.6122
[6 empty] | 4 | Existing Gravel Road, planned upgrade to pavement | [10 empty] | 8.92 |  | 537200 |  |  |  |  | 60224.2152
[6 empty] | 5 | Existing Gravel Road, general grading and gravel | [10 empty] | 14.64 |  | 491400 |  |  |  |  | 33565.5738
[6 empty] | 6 | Existing Gravel Road/Fire Road - No Plans | [10 empty] | 4.3 |  | 0
[17 empty] | Total | 93.17 |  | 7481675 |  |  |  |  | 80301.3309
PAVING COST PER MILE
|  |  |  | Existing Surface | Gravel | Chip Seal | Asphalt
|  | Gravel |  | GRAVEL | 40000 | 60000 | 197000
|  | Chip Seal |  | CHIP SEAL | 40000 | 95000 | 216000
|  | Asphalt |  | ASPHALT | 40000 | 95000 | 216000
Note on H157: Greg Van Grinsven: Add $19,000 per mile to pulverize chip seal or asphalt material.
Note on H158: Greg Van Grinsven: Add $19,000 per mile to pulverize chip seal or asphalt material.

## Roads-Priority Groupings
03_02_17 | PLAN |  |  |  | Length |  |  | SURFACE TYPE |  |  |  | RATING |  |  |  |  | RESURFACE PLAN |  |  |  | RESURFACE |  | Work Scope |  | Extra Work | ACCUM.
TYPE | CAT | ROAD NAME | Primary Access Road | Secondary Access Road | Miles | Accum. | Gravel | Chip | Asphalt | Seal Coated or Resurfaced |  | Traffic | Occupancy | Condition | Priority | Weighted | Gravel | Chip | Asphalt | Alt 1 | COST EST | Surface | Engrg | Extra | Description | COST EST |  | COMMENTS
TR | 3 | Allen Road | CTY M North | High Lake Road | 0.68 | 0.68 |  | 0.68 |  | 1975, 1990 |  | 5 | 5 | 5 | 15 | 125 |  | 0 | 0.68 |  | 220320 |  |  |  |  | 220320 |  | upgrade to asphalt, widen 8' for Bike lanes (White Deer Loop)
TR | 3 | Fishtrap Lake Road | CTY M North, High-FT Lake Rd | XX | 2.04 | 2.72 |  | 2.04 |  | 72,73,75,82,86 |  | 5 | 5 | 5 | 15 | 125 |  | 0.64 | 1.4 |  | 340800 |  |  |  |  | 561120 |  | Do we want all or % as Asphalt??? Shown with asphalt to trail corner
TR | 3 | Newcomb Lane | CTY K West | XX | 3.5 | 6.22 |  | 3.5 |  | 78,80,83,88,92 |  | 5 | 5 | 5 | 15 | 125 |  |  | 3.5 |  | 756000 |  |  |  |  | 1317120 |  | Why Asphalt? Not a high population area like Fishtrap Lake Rd.
TR | 3 | North Creek Road | CTY M South | CTY H | 4.57 | 10.79 |  | 4.57 |  | 75, 76, 87, 92 |  | 5 | 5 | 5 | 15 | 125 |  |  | 4.57 |  | 987120 |  |  |  |  | 2304240 |  | Possible width increase for Bike Route, Cost share with DNR
TR | 3 | Fallon Road | CTY K West | XX | 2.08 | 12.87 |  | 2.08 |  | 1984, 1986 |  | 5 | 5 | 4 | 14 | 100 |  |  | 2.08 |  | 449280 |  |  |  |  | 2753520 |  |  | 0.13945
TR | 2 | Island Lake Road | US 51 North | XX | 1.28 | 14.15 |  | 1.28 |  | 1987 |  | 4 | 5 | 4 | 13 | 80 |  | 1.28 |  |  | 121600 |  |  |  |  | 2875120
TR | 2 | High-Fishtrap Lake Road | CTY M North | XX | 1.1 | 15.25 |  |  | 1.1 |  |  | 5 | 5 | 3 | 13 | 75 |  |  | 1.1 |  | 356400 |  |  |  |  | 3231520 |  | asphalt for loop, add 8' to width
TR | 4 | Big Muskellunge Road | CTY M South | XX | 2.7 | 17.95 | 1.2 | 1 | 0.5 | 1976 |  | 5 | 3 | 4 | 12 | 60 |  | 2.2 |  |  | 167000 |  |  |  |  | 3398520
TR | 2 | Kern Lane | CTY m South | North Creek Road | 1.1 | 19.05 |  | 1.1 |  |  |  | 3 | 4 | 5 | 12 | 60 |  | 1.1 |  |  | 104500 |  |  |  |  | 3503020 |  |  | 0.20641
TR | 4 | Airport Road (paved) | CTY M North | Dairymen's Road | 2.45 | 21.5 |  | 1.45 |  | 1969, 1984 |  | 5 | 5 | 2 | 12 | 50 |  | 0 |  |  | 0 |  |  |  |  | 3503020
|  | 20% | [24 empty] | 3503020
TR | 2 | High Lake Road |  |  | 3.8 | 26.5 |  | 1.3 |  |  |  | 3 | 3 | 5 | 11 | 45 |  | 1.1 | 0.7 |  | 331300 |  |  |  |  | 3834320 |  | Between Allen and Ridge is okay, Chip ridge to end, asphalt loop leg
TR | 2 | Shamrock Lane | CTY K West | Highland Drive | 0.4 | 21.9 |  | 0.4 |  |  |  | 3 | 4 | 4 | 11 | 48 |  | 0.4 |  |  | 38000 |  |  |  |  | 3872320
TR | 2 | Concora Road | Old K | XX | 0.8 | 22.7 |  | 0.8 |  |  |  | 3 | 3 | 5 | 11 | 45 |  | 0.8 |  |  | 76000 |  |  |  |  | 3948320
TR | 2 | Old K Road | CTY M, Main Street | CTYK East | 2.79 | 29.29 |  | 2.79 |  | 1969, 1991 |  | 3 | 3 | 5 | 11 | 45 |  | 2.79 |  |  | 397575 |  |  |  |  | 4345895 |  | widen 8' for bike loop (Asphalt??)
TR | 3 | Dairymens Road | CTY M North | XX | 1.55 | 30.84 |  | 1.55 |  | 1973, 1988 |  | 4 | 5 | 2 | 11 | 40 |  |  | 1.55 |  | 502200 |  |  |  |  | 4848095 |  | Asphalt to benefit Dairymens and Bike loop, widen 8'
TR | 1 | Oswego-Fishtrap Lake Road | CTY M North, High-FT Lake Rd | Fishtrap Road | 1.9 | 32.74 |  | 1.9 |  |  |  | 4 | 5 | 2 | 11 | 40 |  | 0 |  |  | 0 |  |  |  |  | 4848095
TR | 1 | South Town Line | US 51 North | XX | 1.36 | 34.1 |  | 1.36 |  | 1976, 1988 |  | 4 | 5 | 2 | 11 | 40 |  | 0 |  |  | 0 |  |  |  |  | 4848095
TR | 2 | Bakken Road (East) | CTY H | HWY 51 N | 1.07 | 35.17 |  | 1.07 |  | 67,68 |  | 3 | 3 | 4 | 10 | 36 |  | 1.07 |  |  | 101650 |  |  |  |  | 4949745 |  | Asphalt upgrade??
TR | 3 | Highland Drive | CTY K West | CTY M North | 0.28 | 35.45 |  | 0.28 |  | 1976, 1990 |  | 3 | 3 | 4 | 10 | 36 |  |  | 0.28 |  | 60480 |  |  |  |  | 5010225 |  | Upgrade for Bike Loop and Event Bypass support
TR | 2 | Rudolph Lake Lane | CTY H | XX | 0.6 | 36.05 |  | 0.6 |  |  |  | 3 | 4 | 3 | 10 | 36 |  | 0.6 |  |  | 57000 |  |  |  |  | 5067225
TR | 2 | Wool Lake Lane | CTY K West | XX | 0.76 | 36.81 |  | 0.76 |  | 1967, 1972, 1983 |  | 3 | 3 | 4 | 10 | 36 |  | 0.76 | 11.7 |  | 72200 |  |  |  |  | 5139425 |  |  | 0.39885
TR | 1 | North Town Line Rd (Town Road 116) | US 51 North | Le Fave Rd, Island Lake Rd | 1 | 37.81 |  | 1 |  | 1991 |  | 4 | 4 | 2 | 10 | 32 |  | 0 |  |  | 0 |  |  |  |  | 5139425 |  |  | #DIV/0!
|  | 20% | [24 empty] | 1636405
TR | 2 | Harmony Point Lane | US 51 North | between M and H | 0.6 | 38.41 |  | 0.6 |  | 1974, 1982 |  | 2 | 3 | 5 | 10 | 30 |  | 0.6 |  |  | 57000 |  |  |  |  | 5196425 |  | narrow road | 0.42093
TR | 2 | Shore Drive | CTY K West | Newcomb Lane | 1.03 | 39.44 |  | 1.03 |  | 1991 |  | 2 | 3 | 5 | 10 | 30 |  | 1.03 |  |  | 97850 |  |  |  |  | 5294275
TR | 1 | Bakken Road (West) | CTY H | HWY 51 N | 2.15 | 41.59 |  | 2.15 |  |  |  | 3 | 3 | 3 | 9 | 27 |  | 0 |  |  | 0
TR | 2 | La Fave Road | US 51 North | Island Lake Road | 1.24 | 42.83 |  | 1.24 |  | 1970 |  | 3 | 3 | 3 | 9 | 27 |  | 0.25 |  |  | 23750 |  |  |  |  | 5318025 |  | Northwest segment only
TR | 1 | Ben Bendrick Drive (Lake Shore Drive) | CTY M South | XX | 1.7 | 44.53 |  |  | 1.7 |  |  | 4 | 3 | 2 | 9 | 24 |  |  | 0 |  | 0 |  |  |  |  | 5318025
TR | 2 | Green Street | CTY M | Old K | 0.27 | 44.8 |  | 0.27 |  |  |  | 4 | 2 | 3 | 9 | 24 |  | 0.27 |  |  | 25650 |  |  |  |  | 5343675
TR | 2 | High Pines Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln | 1.1 | 45.9 |  | 1.1 |  | 1978 |  | 3 | 4 | 2 | 9 | 24 |  | 1.1 |  |  | 104500 |  |  |  |  | 5448175 |  | needs improved turn around area
TR | 2 | Lucas Lane | CTY K West | XX | 0.15 | 46.05 |  | 0.15 |  | 1971 |  | 2 | 2 | 5 | 9 | 20 |  | 0.15 |  |  | 14250 |  |  |  |  | 5462425 |  | paved to start of campground
TR | 2 | Arrowhead Drive | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road | 0.6 | 46.65 | 0.15 | 0.45 |  | 82, 88 |  | 2 | 3 | 3 | 8 | 18 |  | 0.6 |  |  | 51750 |  |  |  |  | 5514175 |  | turn around work
TR | 2 | Evergreen Lane | CTY K West | XX | 1.98 | 48.63 |  | 1.98 |  | 1974 |  | 3 | 2 | 3 | 8 | 18 |  | 1.98 |  |  | 188100 |  |  |  |  | 5702275 |  | check condition
TR | 2 | Mann Lake Road | CTY M South | XX | 0.75 | 49.38 |  | 0.75 |  | 1973, 1990 |  | 2 | 3 | 3 | 8 | 18 |  | 0.65 |  |  | 61750 |  |  |  |  | 5764025 |  | first .1m ok, no turn around
TR | 2 | Middle Gresham Lane | US 51 North (near H) | XX | 0.43 | 49.81 |  | 0.43 |  |  |  | 2 | 3 | 3 | 8 | 18 |  | 0.43 |  |  | 40850 |  |  |  |  | 5804875
TR | 2 | Keego Road | CTY K West | XX | 1.25 | 51.06 |  | 1.25 |  | 1984 |  | 2 | 2 | 4 | 8 | 16 | 0 | 1.25 |  |  | 118750 |  |  |  |  | 5923625
TR | 2 | Little Rice Lane | CTY M North | XX | 0.28 | 51.34 |  | 0.28 |  |  |  | 2 | 2 | 4 | 8 | 16 |  | 0.28 |  |  | 26600 |  |  |  |  | 5950225
TR | 2 | Rintlemen | CTY K West | Fallon Road | 0.6 | 51.94 |  | 0.6 |  |  |  | 2 | 2 | 4 | 8 | 16 |  | 0.6 |  |  | 57000 |  |  |  |  | 6007225
TR | 2 | Boulder Lane | CTY M North | XX | 0.4 | 52.34 |  | 0.4 |  |  |  | 1 | 3 | 4 | 8 | 12 |  | 0.4 |  |  | 38000 |  |  |  |  | 6045225
TR | 4 | Camp Manitowish Lane (East) | CTY K West | XX | 0.5 | 52.84 | 0.5 |  |  |  |  | 2 | 2 | 3 | 7 | 12 |  | 0.5 |  |  | 30000 |  |  |  |  | 6075225 |  | pave it since CMW will be carrying big tax bill
TR | 6 | Clear View Drive | CTY K West | Fallon Road | 0.34 | 53.18 | 0.34 |  |  |  |  | 3 | 2 | 2 | 7 | 12 | 0 |  |  |  | 0 |  |  |  |  | 6075225 |  | good condition, consider paving all or part
TR | 3 | Grahl Lane | CTY H | XX | 0.43 | 53.61 | 0.43 |  |  |  |  | 3 | 2 | 2 | 7 | 12 |  | 0.43 |  |  | 25800 |  |  |  |  | 6101025
TR | 5 | Nebish lake Road | CTY K West | XX | 1.97 | 55.58 | 1.97 |  |  |  |  | 4 | 1 | 3 | 8 | 12 | 1.97 |  |  |  | 78800 |  |  |  |  | 6179825 |  |  | 0.60223
|  | 20% | [24 empty] | 1040400
TR | 5 | Old 51 Road (Bakken Rd - Island Lake Rd) | CTY H, Bakken Rd (east) | US 51 N, Island Lake Rd | 1.8 | 57.38 | 1.8 |  |  | 1980 |  | 2 | 2 | 3 | 7 | 12 | 1.8 |  |  |  | 72000 |  |  |  |  | 6251825 |  | snowmobile % | 0.62174
TR | 5 | Ridge Lane | CTY M North, High-FT Lake Rd | High Lake Rd | 1.2 | 58.58 | 0.3 | 0.9 |  | 1983 |  | 3 | 4 | 1 | 8 | 12 | 0.3 | 0 |  |  | 12000 |  |  |  |  | 6263825
TR | 1 | Bear Lake Road | CTY K West | XX | 3.26 | 61.84 |  |  | 3.26 | 1971, 1974, 1986 | 2015 | 3 | 3 | 1 | 7 | 9 |  |  | 0 |  | 0 | [6 empty] | repaved with asphalt in 2015
TR | 5 | Dam Road | CTY M North | High-Fishtrap Lake Road | 0.8 | 62.64 | 0.8 |  |  |  |  | 3 | 1 | 3 | 7 | 9 | 0.8 |  |  |  | 32000 |  |  |  |  | 32000
TR | 2 | Glen Lake Road | CTY K West | Shamrock Road | 0.25 | 62.89 |  | 0.25 |  | 1988 |  | 1 | 3 | 3 | 7 | 9 |  | 0.25 |  |  | 23750 |  |  |  |  | 55750
TR | 5 | Nixon Lake Road | CTY K East | XX | 2.6 | 65.49 | 2.6 |  |  |  |  | 3 | 1 | 3 | 7 | 9 | 2.6 |  |  |  | 104000 |  |  |  |  | 159750 |  | Seek cost share with DNR
TR | 1 | Old 51 Road (Town Line - Island Lake Rd) | US 51 North | Town Line Rd, Island lake Rd | 1.07 | 66.56 |  | 1.07 |  |  |  | 3 | 1 | 3 | 7 | 9 |  | 0 |  |  | 0 |  |  |  |  | 159750
TR | 1 | Rustic Colony Lane | CTY M North | Airport Road | 0.27 | 66.83 |  | 0.27 |  |  |  | 1 | 3 | 3 | 7 | 9 | 0 | 0 |  |  | 0 |  |  |  |  | 159750
TR | 4 | Airport Road (gravel) |  |  | 1 | 67.83 | 1 |  |  |  |  | 2 | 1 | 4 | 7 | 8 | 0 | 1 | 0 |  | 60000 |  |  |  |  | 219750 |  | Pave one mike of gravel to complete bike trail loop
TR | 1 | Camp Manitowish Lane (West) | CTY K West | XX | 0.5 | 68.33 |  | 0.5 |  |  |  | 2 | 2 | 2 | 6 | 8 |  | 0 |  |  | 0 |  |  |  |  | 219750
TR | 4 | Platinum Lane | CTY H | Grahl Lane | 0.23 | 68.56 | 0.23 |  |  |  |  | 2 | 2 | 2 | 6 | 8 |  | 0.23 |  |  | 13800 |  |  |  |  | 233550
TR | 1 | Rocky Reef Lane | CTY M South | CTY N West | 0.54 | 69.1 |  | 0.54 |  | 1982, 1992 |  | 2 | 2 | 2 | 6 | 8 |  | 0 |  |  | 0 |  |  |  |  | 233550 |  | poor turn around area
TR | 2 | Stiloski Lane | CTY M North, High-FT Lake Rd | Fishtrap Road | 0.37 | 69.47 |  | 0.37 |  | 1975 |  | 1 | 2 | 4 | 7 | 8 |  | 0.37 |  |  | 35150 |  |  |  |  | 268700
TR | 4 | Sunset Lane | CTY M South, North Creek Rd | Kern lane, Trout lane | 0.3 | 69.77 | 0.3 |  |  |  |  | 1 | 2 | 4 | 7 | 8 | 0 | 0.3 |  |  | 18000 |  |  |  |  | 286700 |  | gravel, is this a town road? Pave it??
TR |  | Town Road 119 (Clear View) | CTY K West, Fallon Rd | Clear View Drive | 0.14 | 69.91 | 0.25 |  |  |  |  | 2 | 2 | 2 | 6 | 8 |  |  | 0 |  | 0 |  |  |  |  | 286700
TR | 2 | Trout Lane | CTY M South, North Creek Rd | Kern lane | 0.2 | 70.11 |  | 0.2 |  |  |  | 1 | 2 | 4 | 7 | 8 |  | 0.2 |  |  | 19000 |  |  |  |  | 305700
TR | 2 | Whitney Lake Road | CTY K West | XX | 1 | 71.11 | 0.1 | 0.9 |  |  |  | 1 | 2 | 4 | 7 | 8 |  | 1 |  |  | 91500 |  |  |  |  | 397200
TR | 1 | Nichols Lake Lane | CTY H | CTY K West | 0.63 | 71.74 |  | 0.63 |  |  |  | 2 | 1 | 3 | 6 | 6 |  | 0 |  |  | 0 |  |  |  |  | 397200
TR | 2 | Pine Lane | US 51 North | Bakken Road (west) | 0.45 | 72.19 |  | 0.45 |  | 1984 |  | 1 | 2 | 3 | 6 | 6 |  | 0.45 |  |  | 42750 |  |  |  |  | 439950 |  | no turn around
TR | 6 | Point Lane | CTY K West | Fallon Rd, Rintleman Rd | 0.25 | 72.44 | 0.25 |  |  |  |  | 1 | 2 | 3 | 6 | 6 | 0 |  |  |  | 0 |  |  |  |  | 439950 |  | Good condition, Consider Paving?
TR | 4 | South Shore Bay Lane | US 51 North | Island Lake Road | 0.15 | 72.59 | 0.15 |  |  |  |  | 1 | 2 | 3 | 6 | 6 |  | 0.15 |  |  | 6000 |  |  |  |  | 445950
TR | 2 | Cattail Cove Lane | CTY K West | XX | 0.75 | 73.34 |  | 0.75 |  | 1992 |  | 1 | 1 | 5 | 7 | 5 |  | 0.75 |  |  | 71250 |  |  |  |  | 517200
TR | 2 | Major Road | CTY M North | Dairymen's Road | 0.5 | 73.84 |  | 0.5 |  | 1973 |  | 1 | 1 | 5 | 7 | 5 |  | 0.5 |  |  | 47500 |  |  |  |  | 564700 |  | road to nowhere, pave only if benefit to Dairymen's
0 | 5 | North Oswego Lake Road | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road | 0.24 | 74.08 | 0.24 |  |  | 1991 |  | 1 | 1 | 5 | 7 | 5 | 0.24 |  |  |  | 9600 |  |  |  |  | 574300
TR | 2 | Sherry Drive | CTY M North, High-FT Lake Rd | High Lake Road | 0.05 | 74.13 |  | 0.05 |  |  |  | 1 | 1 | 5 | 7 | 5 |  | 0.05 |  |  | 4750 |  |  |  |  | 579050
TR | 2 | Spruce Drive | CTY M North, High-FT Lake Rd | High Lake Road | 0.22 | 74.35 |  | 0.22 |  |  |  | 1 | 1 | 5 | 7 | 5 |  | 0.22 |  |  | 20900 |  |  |  |  | 599950 |  | create turn-arounds at each end | 0.80561
|  | 20% | [24 empty] | 683950
TR | 2 | Allequash Lake Road | CTY M South | XX | 0.94 | 75.29 |  | 0.94 |  |  |  | 2 | 0.5 | 4 | 6.5 | 4 |  | 0.94 |  |  | 89300 |  |  |  |  | 689250 |  |  | 0.8158
TR | 2 | Annes Place | Old K | Green Street | 0.14 | 75.43 |  | 0.14 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0.14 |  |  | 13300 |  |  |  |  | 702550
TR | 1 | Birchwood Lane | CTY M North | Airport Road | 0.36 | 75.79 |  | 0.36 |  | 1984 |  | 1 | 2 | 2 | 5 | 4 |  | 0 |  |  | 0
TR | 4 | Blue Heron Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead | 0.12 | 75.91 | 0.12 |  |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.12 |  |  | 7200 |  |  |  |  | 709750
TR | 1 | Blueberry Lane | Main Street, CTY K West | Center Street | 0.25 | 76.16 |  | 0.25 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0 |  |  | 0 |  |  |  |  | 709750
TR | 2 | Campo Fiesta Lane | CTY M South | North Creek Road | 0.13 | 76.29 |  | 0.13 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.13 |  |  | 12350 |  |  |  |  | 722100
TR | 1 | Center Street | CTY M South, Park Street | Marsh Rd, Ada, Blueberry | 0.31 | 76.6 |  | 0.31 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0 |  |  | 0 |  |  |  |  | 722100
TR | 2 | Church Street | Old K | Green Street | 0.14 | 76.74 |  | 0.14 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0.14 |  |  | 13300 |  |  |  |  | 735400
TR | 2 | Dolittle Road | CTY M North | Boulder Lane | 0.15 | 76.89 |  | 0.15 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.15 |  |  | 14250 |  |  |  |  | 749650 |  | make widening part of agreement with owners, doable
TR | 2 | East Fitzgerald Lane | US 51 N, Island lake Rd | Fitzgerald Lane | 0.11 | 77 |  | 0.11 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.11 |  |  | 10450 |  |  |  |  | 760100
TR | 2 | Fitzgerald Lane | US 51 North | Island Lake Road | 0.2 | 77.2 |  | 0.2 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.2 |  |  | 19000 |  |  |  |  | 779100
TR | 4 | Little Crooked Lane | CTY K West | Bear Lake Road | 0.38 | 77.58 | 0.38 |  |  |  |  | 1 | 2 | 2 | 5 | 4 |  | 0.38 |  |  | 22800 |  |  |  |  | 801900
TR | 1 | Town Hall Road | Around Community Building |  | 0.12 | 77.7 |  |  | 0.12 | 1987 |  | 4 | 1 | 1 | 6 | 4 |  |  |  |  | 0 |  |  |  |  | 801900
TR | 4 | White Deer Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead | 0.12 | 77.82 | 0.12 |  |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.12 |  |  | 4800 |  |  |  |  | 806700
TR | 4 | Balsam Lane | US 51 North | Bakken Road (west) | 0.35 | 78.17 | 0.35 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.35 |  |  | 21000 |  |  |  |  | 827700 |  | no turn around
TR | 5 | Bass Lake Road | CTY K West | Bear Lake Road | 0.41 | 78.58 | 0.41 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.41 |  |  |  | 16400 |  |  |  |  | 844100
TR | 5 | Birch Point Lane | CTY K West | Bear Lake Road | 0.19 | 78.77 | 0.19 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.19 |  |  |  | 7600 |  |  |  |  | 851700
TR | 2 | Charlotte Place Lane | US 51 North | XX | 0.25 | 79.02 |  | 0.25 |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.25 |  |  | 23750 |  |  |  |  | 875450
TR | 4 | En-Dah Win Lane | CTY K East | XX | 0.15 | 79.17 | 0.15 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.1 |  |  | 6000 |  |  |  |  | 881450 |  | only pave to T
TR | 5 | Halverson Lane | CTY M South | XX | 0.12 | 79.29 | 0.12 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.12 |  |  |  | 4800 |  |  |  |  | 886250
TR | 1 | Kassien Lane | US 51 North | Island Lake Road | 0.54 | 79.83 |  | 0.54 |  |  |  | 1 | 1 | 3 | 5 | 3 |  |  |  |  | 0 |  |  |  |  | 886250
TR | 4 | Partridge Lane | CTY M North, High-FT Lake Rd | High Lake Road | 1.1 | 80.93 | 1.1 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 1.1 |  |  | 66000 |  |  |  |  | 952250
TR | 4 | Perch Lane | CTY M South (by N) |  | 0.23 | 81.16 | 0.23 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.23 |  |  | 21850 |  |  |  |  | 974100 |  | no turn around
TR | 5 | Pine Shores Lane | US 51 North | Bakken Road (west) | 0.06 | 81.22 | 0.06 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.06 |  |  |  | 2400 |  |  |  |  | 976500
TR | 4 | Pinewood Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln | 0.12 | 81.34 | 0.12 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.12 |  |  | 7200 |  |  |  |  | 983700
TR | 2 | Red Fox Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead | 0.09 | 81.43 |  | 0.09 |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.09 |  |  | 8550 |  |  |  |  | 992250
TR | 1 | Senior Drive | CTY M, Park Street | Green Street | 0.2 | 81.63 |  | 0.2 |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0 |  |  | 0 |  |  |  |  | 992250
TR | 6 | Street Lake Lane | CTY H | XX | 0.65 | 82.28 | 0.65 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  |  |  |  | 0 |  |  |  |  | 992250 |  | do we want to pave??
TR | 5 | White Birch Lane | CTY M North, High-FT Lake Rd | Osewgo-FT Lake Road | 0.45 | 82.73 | 0.45 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.45 |  |  |  | 18000 |  |  |  |  | 1010250
TR | 6 | Keego Road East | CTY K West, Bear lake Road | Keego Road | 1.31 | 84.04 | 1.31 |  |  |  |  | 1 | 0.5 | 5 | 6.5 | 2.5 |  | 0 |  |  | 0 |  |  |  |  | 1010250
TR | 6 | Old Flambeau Road | CTY H?? | Bakken Rd ?? | 0.74 | 84.78 | 0.74 |  |  |  |  | 0.5 | 1 | 5 | 6.5 | 2.5 | 0 |  |  |  | 0 |  |  |  |  | 1010250 |  | No signs, looks like snowmobile trail, barely a road
TR | 1 | Ada Street | CTY M | Main Street | 0.25 | 85.03 |  | 0.25 |  |  | <10 | 1 | 1 | 2 | 4 | 2 |  | 0 |  |  | 0 |  |  |  |  | 1010250
TR | 6 | Birch Drive | CTY M North, High-FT Lake Rd | High Lake Road | 0.25 | 85.28 | 0.25 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 0 |  |  |  | 0 |  |  |  |  | 1010250
TR | 1 | Blaisdell Street | Main Street, CTY K West | Ada, Blueberry | 0.17 | 85.45 |  | 0.17 |  |  |  | 1 | 1 | 2 | 4 | 2 |  | 0 |  |  | 0 |  |  |  |  | 1010250
TR | 1 | Community Street | CTY K West | Blaisdell Street | 0.2 | 85.65 |  | 0.2 |  |  |  | 1 | 1 | 2 | 4 | 2 |  | 0 |  |  | 0 |  |  |  |  | 1010250
TR | 5 | Maple Lake Road | CTY K West | XX | 0.35 | 86 | 0.35 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 0.35 |  |  |  | 14000 |  |  |  |  | 1024250
TR | 2 | Reible Court | Old K | XX | 0.12 | 86.12 |  | 0.12 |  |  |  | 1 | 1 | 2 | 4 | 2 |  | 0.12 |  |  | 11400 |  |  |  |  | 1035650
TR | 6 | River lane | CTY K West | XX | 0.2 | 86.32 | 0.2 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 0 |  |  |  | 0 |  |  |  |  | 1035650
TR | 6 | South Rudolph Lake Lane | CTY H | Rudolph Lake Lane | 0.26 | 86.58 | 0.26 |  |  | 1987 |  | 1 | 1 | 2 | 4 | 2 |  |  |  |  | 0 |  |  |  |  | 1035650
TR | 5 | West Big Lake Road (lane) | CTY K West | XX | 1.04 | 87.62 | 1.04 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 1.04 |  |  |  | 41600 |  |  |  |  | 1077250 |  | one house, why is this a town road?
TR | 5 | Boat Landing Road (Island lake) | US 51 North | Island Lake Road | 0.5 | 88.12 | 0.5 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 0.5 |  |  |  | 20000 |  |  |  |  | 1097250
TR | 1 | Day Lake Landing Road | Day Lake Road | XXX | 0.22 | 88.34 | 0.22 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 0 |  |  |  | 0 |  |  |  |  | 1097250
TR | 5 | Day Lake Road | North Creek Road | US 51 North | 2.91 | 91.25 | 2.91 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 2.91 |  |  |  | 58200 |  |  |  |  | 1155450 |  | Basic work, not full gravel work up
TR | 4 | Marsh Road | CTY M South | CTY K West | 1.04 | 92.29 | 1.04 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 |  | 1.04 |  |  | 62400 |  |  |  |  | 1217850 |  | Create Bike bypass for through riders, better use of events
TR | 6 | Vandercook Road | CTY M South | XX | 0.08 | 92.37 | 0.08 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 0 |  |  |  | 0 | [6 empty] | trapped between Arbor Vitae roads, snowmobile trail 100%
TR | 1 | Good Life Lane | CTY M North | Airport Road | 0.44 | 92.81 |  |  | 0.44 |  |  | 1 | 1 | 1 | 3 | 1 |  |  | 0 |  | 0
TR | 6 | Jag Lake Road | CTY H | XX | 0.08 | 92.89 | 0.08 |  |  |  |  | 1 | 0.5 | 2 | 3.5 | 1 |  | 0 |  |  | 0 | [6 empty] | boat landing
TR | 1 | Round Lake Road | CTY K West | Bear Lake Road | 0.1 | 92.99 |  | 0.1 |  |  |  | 1 | 0.5 | 2 | 3.5 | 1 |  | 0 |  |  | 0
TR | 1 | Cemetary Road | CTY K West | XX | 0.18 | 93.17 |  | 0.18 |  |  |  | 1 | 0.5 | 1 | 2.5 | 0.5 |  | 0 |  |  | 0
TR | 0 | Old 51 East Hoffman Road |  | 0.26 | 0 | 93.17 | [8 empty] | 0
TR | 0 | Old 51 Old H |  | 1.17 | 0 | 93.17 | [8 empty] | 0
TR | 1 | Round Lake Road (Presque Isle) | CTY K West | Bear Lake Road | 1.25 | 94.42 |  | 1.25 | [6 empty] | 0 |  |  | 0 |  |  | 0
TR |  | Town Road 127 |  |  | 0.1 | 94.52 | [8 empty] | 0
TR |  | Town Road 133 |  |  | 0.15 | 94.67 | [8 empty] | 0
|  | 20% | [24 empty] | 617900
[5 empty] | 93.17 |  | 26.04 | 56.62 | 7.12 | [7 empty] | 13.74 | 34.56 | 27.56 |  | 7481675 |  |  |  |  | TOTAL ESTIMATED COST
[8 empty] | Town Road Mileage | 89.78 | [7 empty] | Improvement Mileage |  | 75.86 | [7 empty] | 7481675
[17 empty] | Percent of Total Mileage |  | 84.5%
0
[17 empty] | % of | Accum. |  |  | Cost by 20%
[6 empty] | COLOR KEY | [10 empty] | Dollars | Miles | % |  | Increments
[6 empty] | 1 | Recently Updated, Or in Good Condition - No work planned | [9 empty] | 46.82% | 19.05 | 20 |  | 3503020
[6 empty] | 2 | Paved Road, repaving planned, same surface | [9 empty] | 21.87% | 36.81 | 20 |  | 1636405
[6 empty] | 3 | Paved Road, repaving planned, new surface | [9 empty] | 13.91% | 55.58 | 20 |  | 1040400
[6 empty] | 4 | Existing Gravel Road, planned upgrade to pavement | [9 empty] | 9.142% | 74.35 | 20 |  | 683950
[6 empty] | 5 | Existing Gravel Road, general grading and gravel | [9 empty] | 8.259% | 92.29 | 20 |  | 617900
[6 empty] | 6 | Existing Gravel Road/Fire Road - No Plans | [11 empty] | 100 |  | 7481675
PAVING COST PER MILE
|  |  |  | Existing Surface | Gravel | Chip Seal | Asphalt
|  | Gravel |  | GRAVEL | 40000 | 60000 | 197000
|  | Chip Seal |  | CHIP SEAL | 40000 | 95000 | 216000
|  | Asphalt |  | ASPHALT | 40000 | 95000 | 216000
Note on H147: Greg Van Grinsven: Add $19,000 per mile to pulverize chip seal or asphalt material.
Note on H148: Greg Van Grinsven: Add $19,000 per mile to pulverize chip seal or asphalt material.

## Roads- Priority Grps no bike tr
03_02_17 | PLAN |  |  |  | Length |  |  | SURFACE TYPE |  |  |  | RATING |  |  |  |  | RESURFACE PLAN |  |  | RESURFACE |  | Work Scope |  | Extra Work | ACCUM.
TYPE | CAT | ROAD NAME | Primary Access Road | Secondary Access Road | Miles | Accum. | Gravel | Chip | Asphalt | Seal Coated or Resurfaced |  | Traffic | Occupancy | Condition | Priority | Weighted | Gravel | Chip | Asphalt | COST EST | Surface | Engrg | Extra | Description | COST EST |  | COMMENTS
TR | 3 | Allen Road | CTY M North | High Lake Road | 0.68 | 0.68 |  | 0.68 |  | 1975, 1990 |  | 5 | 5 | 5 | 15 | 125 |  | 0 | 0.68 | 146880 |  |  |  |  | 146880 |  | upgrade to asphalt, widen 8' for Bike lanes (White Deer Loop)
TR | 3 | Fishtrap Lake Road | CTY M North, High-FT Lake Rd | XX | 2.04 | 2.72 |  | 2.04 |  | 72,73,75,82,86 |  | 5 | 5 | 5 | 15 | 125 |  | 0.64 | 1.4 | 363200 |  |  |  |  | 510080 |  | Do we want all or % as Asphalt??? Shown with asphalt to trail corner
TR | 3 | Newcomb Lane | CTY K West | XX | 3.5 | 6.22 |  | 3.5 |  | 78,80,83,88,92 |  | 5 | 5 | 5 | 15 | 125 |  |  | 3.5 | 756000 |  |  |  |  | 1266080 |  | Why Asphalt? Not a high population area like Fishtrap Lake Rd.
TR | 3 | North Creek Road | CTY M South | CTY H | 4.57 | 10.79 |  | 4.57 |  | 75, 76, 87, 92 |  | 5 | 5 | 5 | 15 | 125 |  |  | 4.57 | 987120 |  |  |  |  | 2253200 |  | Possible width increase for Bike Route, Cost share with DNR
TR | 3 | Fallon Road | CTY K West | XX | 2.08 | 12.87 |  | 2.08 |  | 1984, 1986 |  | 5 | 5 | 4 | 14 | 100 |  |  | 2.08 | 449280 |  |  |  |  | 2702480 |  |  | 0.13945
TR | 2 | Island Lake Road | US 51 North | XX | 1.28 | 14.15 |  | 1.28 |  | 1987 |  | 4 | 5 | 4 | 13 | 80 |  | 1.28 |  | 121600 |  |  |  |  | 2824080
TR | 2 | High-Fishtrap Lake Road | CTY M North | XX | 1.1 | 15.25 |  |  | 1.1 |  |  | 5 | 5 | 3 | 13 | 75 |  |  | 1.1 | 237600 |  |  |  |  | 3061680 |  | asphalt for loop, add 8' to width
TR | 4 | Big Muskellunge Road | CTY M South | XX | 2.7 | 17.95 | 1.2 | 1 | 0.5 | 1976 |  | 5 | 3 | 4 | 12 | 60 |  | 2.2 |  | 167000 |  |  |  |  | 3228680
TR | 2 | Kern Lane | CTY m South | North Creek Road | 1.1 | 19.05 |  | 1.1 |  |  |  | 3 | 4 | 5 | 12 | 60 |  | 1.1 |  | 104500 |  |  |  |  | 3333180 |  |  | 0.20641
TR | 4 | Airport Road (paved) | CTY M North | Dairymen's Road | 2.45 | 21.5 |  |  | 1.45 | 1969, 1984 |  | 5 | 5 | 2 | 12 | 50 |  |  | 0 | 0
|  | 20% | [23 empty] | 3333180
TR | 2 | Shamrock Lane | CTY K West | Highland Drive | 0.4 | 21.9 |  | 0.4 |  |  |  | 3 | 4 | 4 | 11 | 48 |  | 0.4 |  | 38000 |  |  |  |  | 3371180
TR | 2 | Concora Road | Old K | XX | 0.8 | 22.7 |  | 0.8 |  |  |  | 3 | 3 | 5 | 11 | 45 |  | 0.8 |  | 76000 |  |  |  |  | 3447180
TR | 2 | High Lake Road |  |  | 3.8 | 26.5 |  | 1.3 |  |  |  | 3 | 3 | 5 | 11 | 45 |  | 1.1 | 0.7 | 255700 |  |  |  |  | 3702880 |  | Between Allen and Ridge is okay, Chip ridge to end, asphalt loop leg
TR | 2 | Old K Road | CTY M, Main Street | CTYK East | 2.79 | 29.29 |  | 2.79 |  | 1969, 1991 |  | 3 | 3 | 5 | 11 | 45 |  | 2.79 |  | 265050 |  |  |  |  | 3967930 |  | widen 8' for bike loop (Asphalt??)
TR | 3 | Dairymens Road | CTY M North | XX | 1.55 | 30.84 |  | 1.55 |  | 1973, 1988 |  | 4 | 5 | 2 | 11 | 40 |  |  | 1.55 | 334800 |  |  |  |  | 4302730 |  | Asphalt to benefit Dairymens and Bike loop, widen 8'
TR | 1 | Oswego-Fishtrap Lake Road | CTY M North, High-FT Lake Rd | Fishtrap Road | 1.9 | 32.74 |  | 1.9 |  |  |  | 4 | 5 | 2 | 11 | 40 |  | 0 |  | 0 |  |  |  |  | 4302730
TR | 1 | South Town Line | US 51 North | XX | 1.36 | 34.1 |  | 1.36 |  | 1976, 1988 |  | 4 | 5 | 2 | 11 | 40 |  | 0 |  | 0 |  |  |  |  | 4302730
TR | 2 | Bakken Road (East) | CTY H | HWY 51 N | 1.07 | 35.17 |  | 1.07 |  | 67,68 |  | 3 | 3 | 4 | 10 | 36 |  | 1.07 |  | 101650 |  |  |  |  | 4404380 |  | Asphalt upgrade??
TR | 3 | Highland Drive | CTY K West | CTY M North | 0.28 | 35.45 |  | 0.28 |  | 1976, 1990 |  | 3 | 3 | 4 | 10 | 36 |  |  | 0.28 | 60480 |  |  |  |  | 4464860 |  | Upgrade for Bike Loop and Event Bypass support
TR | 2 | Rudolph Lake Lane | CTY H | XX | 0.6 | 36.05 |  | 0.6 |  |  |  | 3 | 4 | 3 | 10 | 36 |  | 0.6 |  | 57000 |  |  |  |  | 4521860
TR | 2 | Wool Lake Lane | CTY K West | XX | 0.76 | 36.81 |  | 0.76 |  | 1967, 1972, 1983 |  | 3 | 3 | 4 | 10 | 36 |  | 0.76 |  | 72200 |  |  |  |  | 4594060 |  |  | 0.39885
TR | 1 | North Town Line Rd (Town Road 116) | US 51 North | Le Fave Rd, Island Lake Rd | 1 | 37.81 |  | 1 |  | 1991 |  | 4 | 4 | 2 | 10 | 32 |  | 0 |  | 0 | [7 empty] | #DIV/0!
|  | 20% | [23 empty] | 1260880
TR | 2 | Harmony Point Lane | US 51 North | between M and H | 0.6 | 38.41 |  | 0.6 |  | 1974, 1982 |  | 2 | 3 | 5 | 10 | 30 |  | 0.6 |  | 57000 |  |  |  |  | 4651060 |  | narrow road | 0.42093
TR | 2 | Shore Drive | CTY K West | Newcomb Lane | 1.03 | 39.44 |  | 1.03 |  | 1991 |  | 2 | 3 | 5 | 10 | 30 |  | 1.03 |  | 97850 |  |  |  |  | 4748910
TR | 1 | Bakken Road (West) | CTY H | HWY 51 N | 2.15 | 41.59 |  | 2.15 |  |  |  | 3 | 3 | 3 | 9 | 27 |  | 0 |  | 0
TR | 2 | La Fave Road | US 51 North | Island Lake Road | 1.24 | 42.83 |  | 1.24 |  | 1970 |  | 3 | 3 | 3 | 9 | 27 |  | 0.25 |  | 23750 |  |  |  |  | 4772660 |  | Northwest segment only
TR | 1 | Ben Bendrick Drive (Lake Shore Drive) | CTY M South | XX | 1.7 | 44.53 |  |  | 1.7 |  |  | 4 | 3 | 2 | 9 | 24 |  |  | 0 | 0 |  |  |  |  | 4772660
TR | 2 | Green Street | CTY M | Old K | 0.27 | 44.8 |  | 0.27 |  |  |  | 4 | 2 | 3 | 9 | 24 |  | 0.27 |  | 25650 |  |  |  |  | 4798310
TR | 2 | High Pines Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln | 1.1 | 45.9 |  | 1.1 |  | 1978 |  | 3 | 4 | 2 | 9 | 24 |  | 1.1 |  | 104500 |  |  |  |  | 4902810 |  | needs improved turn around area
TR | 2 | Lucas Lane | CTY K West | XX | 0.15 | 46.05 |  | 0.15 |  | 1971 |  | 2 | 2 | 5 | 9 | 20 |  | 0.15 |  | 14250 |  |  |  |  | 4917060 |  | paved to start of campground
TR | 2 | Arrowhead Drive | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road | 0.6 | 46.65 | 0.15 | 0.45 |  | 82, 88 |  | 2 | 3 | 3 | 8 | 18 |  | 0.6 |  | 51750 |  |  |  |  | 4968810 |  | turn around work
TR | 2 | Evergreen Lane | CTY K West | XX | 1.98 | 48.63 |  | 1.98 |  | 1974 |  | 3 | 2 | 3 | 8 | 18 |  | 1.98 |  | 188100 |  |  |  |  | 5156910 |  | check condition
TR | 2 | Mann Lake Road | CTY M South | XX | 0.75 | 49.38 |  | 0.75 |  | 1973, 1990 |  | 2 | 3 | 3 | 8 | 18 |  | 0.65 |  | 61750 |  |  |  |  | 5218660 |  | first .1m ok, no turn around
TR | 2 | Middle Gresham Lane | US 51 North (near H) | XX | 0.43 | 49.81 |  | 0.43 |  |  |  | 2 | 3 | 3 | 8 | 18 |  | 0.43 |  | 40850 |  |  |  |  | 5259510
TR | 2 | Keego Road | CTY K West | XX | 1.25 | 51.06 |  | 1.25 |  | 1984 |  | 2 | 2 | 4 | 8 | 16 | 0 | 1.25 |  | 118750 |  |  |  |  | 5378260
TR | 2 | Little Rice Lane | CTY M North | XX | 0.28 | 51.34 |  | 0.28 |  |  |  | 2 | 2 | 4 | 8 | 16 |  | 0.28 |  | 26600 |  |  |  |  | 5404860
TR | 2 | Rintlemen | CTY K West | Fallon Road | 0.6 | 51.94 |  | 0.6 |  |  |  | 2 | 2 | 4 | 8 | 16 |  | 0.6 |  | 57000 |  |  |  |  | 5461860
TR | 2 | Boulder Lane | CTY M North | XX | 0.4 | 52.34 |  | 0.4 |  |  |  | 1 | 3 | 4 | 8 | 12 |  | 0.4 |  | 38000 |  |  |  |  | 5499860
TR | 4 | Camp Manitowish Lane (East) | CTY K West | XX | 0.5 | 52.84 | 0.5 |  |  |  |  | 2 | 2 | 3 | 7 | 12 |  | 0.5 |  | 30000 |  |  |  |  | 5529860 |  | pave it since CMW will be carrying big tax bill
TR | 6 | Clear View Drive | CTY K West | Fallon Road | 0.34 | 53.18 | 0.34 |  |  |  |  | 3 | 2 | 2 | 7 | 12 | 0 |  |  | 0 |  |  |  |  | 5529860 |  | good condition, consider paving all or part
TR | 3 | Grahl Lane | CTY H | XX | 0.43 | 53.61 | 0.43 |  |  |  |  | 3 | 2 | 2 | 7 | 12 |  | 0.43 |  | 25800 |  |  |  |  | 5555660
TR | 5 | Nebish lake Road | CTY K West | XX | 1.97 | 55.58 | 1.97 |  |  |  |  | 4 | 1 | 3 | 8 | 12 | 1.97 |  |  | 78800 |  |  |  |  | 5634460 |  |  | 0.60223
|  | 20% | [23 empty] | 1040400
TR | 5 | Old 51 Road (Bakken Rd - Island Lake Rd) | CTY H, Bakken Rd (east) | US 51 N, Island Lake Rd | 1.8 | 57.38 | 1.8 |  |  | 1980 |  | 2 | 2 | 3 | 7 | 12 | 1.8 |  |  | 72000 |  |  |  |  | 5706460 |  | snowmobile % | 0.62174
TR | 5 | Ridge Lane | CTY M North, High-FT Lake Rd | High Lake Rd | 1.2 | 58.58 | 0.3 | 0.9 |  | 1983 |  | 3 | 4 | 1 | 8 | 12 | 0.3 | 0 |  | 12000 |  |  |  |  | 5718460
TR | 1 | Bear Lake Road | CTY K West | XX | 3.26 | 61.84 |  |  | 3.26 | 1971, 1974, 1986 | 2015 | 3 | 3 | 1 | 7 | 9 |  |  | 0 | 0 | [6 empty] | repaved with asphalt in 2015
TR | 5 | Dam Road | CTY M North | High-Fishtrap Lake Road | 0.8 | 62.64 | 0.8 |  |  |  |  | 3 | 1 | 3 | 7 | 9 | 0.8 |  |  | 32000 |  |  |  |  | 5750460
TR | 2 | Glen Lake Road | CTY K West | Shamrock Road | 0.25 | 62.89 |  | 0.25 |  | 1988 |  | 1 | 3 | 3 | 7 | 9 |  | 0.25 |  | 23750 |  |  |  |  | 5774210
TR | 5 | Nixon Lake Road | CTY K East | XX | 2.6 | 65.49 | 2.6 |  |  |  |  | 3 | 1 | 3 | 7 | 9 | 2.6 |  |  | 104000 |  |  |  |  | 5878210 |  | Seek cost share with DNR
TR | 1 | Old 51 Road (Town Line - Island Lake Rd) | US 51 North | Town Line Rd, Island lake Rd | 1.07 | 66.56 |  | 1.07 |  |  |  | 3 | 1 | 3 | 7 | 9 |  | 0 |  | 0 |  |  |  |  | 5878210
TR | 1 | Rustic Colony Lane | CTY M North | Airport Road | 0.27 | 66.83 |  | 0.27 |  |  |  | 1 | 3 | 3 | 7 | 9 | 0 | 0 |  | 0 |  |  |  |  | 5878210
TR | 4 | Airport Road (gravel) |  |  | 1 | 67.83 | 1 |  |  |  |  | 2 | 1 | 4 | 7 | 8 | 0 | 1 | 0 | 60000 |  |  |  |  | 5938210 |  | Pave one mike of gravel to complete bike trail loop
TR | 1 | Camp Manitowish Lane (West) | CTY K West | XX | 0.5 | 68.33 |  | 0.5 |  |  |  | 2 | 2 | 2 | 6 | 8 |  | 0 |  | 0 |  |  |  |  | 5938210
TR | 4 | Platinum Lane | CTY H | Grahl Lane | 0.23 | 68.56 | 0.23 |  |  |  |  | 2 | 2 | 2 | 6 | 8 |  | 0.23 |  | 13800 |  |  |  |  | 5952010
TR | 1 | Rocky Reef Lane | CTY M South | CTY N West | 0.54 | 69.1 |  | 0.54 |  | 1982, 1992 |  | 2 | 2 | 2 | 6 | 8 |  | 0 |  | 0 |  |  |  |  | 5952010 |  | poor turn around area
TR | 2 | Stiloski Lane | CTY M North, High-FT Lake Rd | Fishtrap Road | 0.37 | 69.47 |  | 0.37 |  | 1975 |  | 1 | 2 | 4 | 7 | 8 |  | 0.37 |  | 35150 |  |  |  |  | 5987160
TR | 4 | Sunset Lane | CTY M South, North Creek Rd | Kern lane, Trout lane | 0.3 | 69.77 | 0.3 |  |  |  |  | 1 | 2 | 4 | 7 | 8 | 0 | 0.3 |  | 18000 |  |  |  |  | 6005160 |  | gravel, is this a town road? Pave it??
TR |  | Town Road 119 (Clear View) | CTY K West, Fallon Rd | Clear View Drive | 0.14 | 69.91 | 0.25 |  |  |  |  | 2 | 2 | 2 | 6 | 8 |  |  | 0 | 0 |  |  |  |  | 6005160
TR | 2 | Trout Lane | CTY M South, North Creek Rd | Kern lane | 0.2 | 70.11 |  | 0.2 |  |  |  | 1 | 2 | 4 | 7 | 8 |  | 0.2 |  | 19000 |  |  |  |  | 6024160
TR | 2 | Whitney Lake Road | CTY K West | XX | 1 | 71.11 | 0.1 | 0.9 |  |  |  | 1 | 2 | 4 | 7 | 8 |  | 1 |  | 91500 |  |  |  |  | 6115660
TR | 1 | Nichols Lake Lane | CTY H | CTY K West | 0.63 | 71.74 |  | 0.63 |  |  |  | 2 | 1 | 3 | 6 | 6 |  | 0 |  | 0 |  |  |  |  | 6115660
TR | 2 | Pine Lane | US 51 North | Bakken Road (west) | 0.45 | 72.19 |  | 0.45 |  | 1984 |  | 1 | 2 | 3 | 6 | 6 |  | 0.45 |  | 42750 |  |  |  |  | 6158410 |  | no turn around
TR | 6 | Point Lane | CTY K West | Fallon Rd, Rintleman Rd | 0.25 | 72.44 | 0.25 |  |  |  |  | 1 | 2 | 3 | 6 | 6 | 0 |  |  | 0 |  |  |  |  | 6158410 |  | Good condition, Consider Paving?
TR | 4 | South Shore Bay Lane | US 51 North | Island Lake Road | 0.15 | 72.59 | 0.15 |  |  |  |  | 1 | 2 | 3 | 6 | 6 |  | 0.15 |  | 6000 |  |  |  |  | 6164410
TR | 2 | Cattail Cove Lane | CTY K West | XX | 0.75 | 73.34 |  | 0.75 |  | 1992 |  | 1 | 1 | 5 | 7 | 5 |  | 0.75 |  | 71250 |  |  |  |  | 6235660
TR | 2 | Major Road | CTY M North | Dairymen's Road | 0.5 | 73.84 |  | 0.5 |  | 1973 |  | 1 | 1 | 5 | 7 | 5 |  | 0.5 |  | 47500 |  |  |  |  | 6283160 |  | road to nowhere, pave only if benefit to Dairymen's
0 | 5 | North Oswego Lake Road | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road | 0.24 | 74.08 | 0.24 |  |  | 1991 |  | 1 | 1 | 5 | 7 | 5 | 0.24 |  |  | 9600 |  |  |  |  | 6292760
TR | 2 | Sherry Drive | CTY M North, High-FT Lake Rd | High Lake Road | 0.05 | 74.13 |  | 0.05 |  |  |  | 1 | 1 | 5 | 7 | 5 |  | 0.05 |  | 4750 |  |  |  |  | 6297510
TR | 2 | Spruce Drive | CTY M North, High-FT Lake Rd | High Lake Road | 0.22 | 74.35 |  | 0.22 |  |  |  | 1 | 1 | 5 | 7 | 5 |  | 0.22 |  | 20900 |  |  |  |  | 6318410 |  | create turn-arounds at each end | 0.80561
|  | 20% | [23 empty] | 683950
TR | 2 | Allequash Lake Road | CTY M South | XX | 0.94 | 75.29 |  | 0.94 |  |  |  | 2 | 0.5 | 4 | 6.5 | 4 |  | 0.94 |  | 89300 |  |  |  |  | 6407710 |  |  | 0.8158
TR | 2 | Annes Place | Old K | Green Street | 0.14 | 75.43 |  | 0.14 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0.14 |  | 13300 |  |  |  |  | 6421010
TR | 1 | Birchwood Lane | CTY M North | Airport Road | 0.36 | 75.79 |  | 0.36 |  | 1984 |  | 1 | 2 | 2 | 5 | 4 |  | 0 |  | 0
TR | 4 | Blue Heron Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead | 0.12 | 75.91 | 0.12 |  |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.12 |  | 7200 |  |  |  |  | 6428210
TR | 1 | Blueberry Lane | Main Street, CTY K West | Center Street | 0.25 | 76.16 |  | 0.25 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0 |  | 0 |  |  |  |  | 6428210
TR | 2 | Campo Fiesta Lane | CTY M South | North Creek Road | 0.13 | 76.29 |  | 0.13 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.13 |  | 12350 |  |  |  |  | 6440560
TR | 1 | Center Street | CTY M South, Park Street | Marsh Rd, Ada, Blueberry | 0.31 | 76.6 |  | 0.31 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0 |  | 0 |  |  |  |  | 6440560
TR | 2 | Church Street | Old K | Green Street | 0.14 | 76.74 |  | 0.14 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0.14 |  | 13300 |  |  |  |  | 6453860
TR | 2 | Dolittle Road | CTY M North | Boulder Lane | 0.15 | 76.89 |  | 0.15 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.15 |  | 14250 |  |  |  |  | 6468110 |  | make widening part of agreement with owners, doable
TR | 2 | East Fitzgerald Lane | US 51 N, Island lake Rd | Fitzgerald Lane | 0.11 | 77 |  | 0.11 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.11 |  | 10450 |  |  |  |  | 6478560
TR | 2 | Fitzgerald Lane | US 51 North | Island Lake Road | 0.2 | 77.2 |  | 0.2 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.2 |  | 19000 |  |  |  |  | 6497560
TR | 4 | Little Crooked Lane | CTY K West | Bear Lake Road | 0.38 | 77.58 | 0.38 |  |  |  |  | 1 | 2 | 2 | 5 | 4 |  | 0.38 |  | 22800 |  |  |  |  | 6520360
TR | 1 | Town Hall Road | Around Community Building |  | 0.12 | 77.7 |  |  | 0.12 | 1987 |  | 4 | 1 | 1 | 6 | 4 |  |  |  | 0 |  |  |  |  | 6520360
TR | 4 | White Deer Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead | 0.12 | 77.82 | 0.12 |  |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.12 |  | 4800 |  |  |  |  | 6525160
TR | 4 | Balsam Lane | US 51 North | Bakken Road (west) | 0.35 | 78.17 | 0.35 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.35 |  | 21000 |  |  |  |  | 6546160 |  | no turn around
TR | 5 | Bass Lake Road | CTY K West | Bear Lake Road | 0.41 | 78.58 | 0.41 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.41 |  |  | 16400 |  |  |  |  | 6562560
TR | 5 | Birch Point Lane | CTY K West | Bear Lake Road | 0.19 | 78.77 | 0.19 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.19 |  |  | 7600 |  |  |  |  | 6570160
TR | 2 | Charlotte Place Lane | US 51 North | XX | 0.25 | 79.02 |  | 0.25 |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.25 |  | 23750 |  |  |  |  | 6593910
TR | 4 | En-Dah Win Lane | CTY K East | XX | 0.15 | 79.17 | 0.15 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.1 |  | 6000 |  |  |  |  | 6599910 |  | only pave to T
TR | 5 | Halverson Lane | CTY M South | XX | 0.12 | 79.29 | 0.12 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.12 |  |  | 4800 |  |  |  |  | 6604710
TR | 1 | Kassien Lane | US 51 North | Island Lake Road | 0.54 | 79.83 |  | 0.54 |  |  |  | 1 | 1 | 3 | 5 | 3 |  |  |  | 0 |  |  |  |  | 6604710
TR | 4 | Partridge Lane | CTY M North, High-FT Lake Rd | High Lake Road | 1.1 | 80.93 | 1.1 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 1.1 |  | 66000 |  |  |  |  | 6670710
TR | 4 | Perch Lane | CTY M South (by N) |  | 0.23 | 81.16 | 0.23 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.23 |  | 21850 |  |  |  |  | 6692560 |  | no turn around
TR | 5 | Pine Shores Lane | US 51 North | Bakken Road (west) | 0.06 | 81.22 | 0.06 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.06 |  |  | 2400 |  |  |  |  | 6694960
TR | 4 | Pinewood Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln | 0.12 | 81.34 | 0.12 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.12 |  | 7200 |  |  |  |  | 6702160
TR | 2 | Red Fox Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead | 0.09 | 81.43 |  | 0.09 |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.09 |  | 8550 |  |  |  |  | 6710710
TR | 1 | Senior Drive | CTY M, Park Street | Green Street | 0.2 | 81.63 |  | 0.2 |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0 |  | 0 |  |  |  |  | 6710710
TR | 6 | Street Lake Lane | CTY H | XX | 0.65 | 82.28 | 0.65 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  |  |  | 0 |  |  |  |  | 6710710 |  | do we want to pave??
TR | 5 | White Birch Lane | CTY M North, High-FT Lake Rd | Osewgo-FT Lake Road | 0.45 | 82.73 | 0.45 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.45 |  |  | 18000 |  |  |  |  | 6728710
TR | 6 | Keego Road East | CTY K West, Bear lake Road | Keego Road | 1.31 | 84.04 | 1.31 |  |  |  |  | 1 | 0.5 | 5 | 6.5 | 2.5 |  | 0 |  | 0 |  |  |  |  | 6728710
TR | 6 | Old Flambeau Road | CTY H?? | Bakken Rd ?? | 0.74 | 84.78 | 0.74 |  |  |  |  | 0.5 | 1 | 5 | 6.5 | 2.5 | 0 |  |  | 0 |  |  |  |  | 6728710 |  | No signs, looks like snowmobile trail, barely a road
TR | 1 | Ada Street | CTY M | Main Street | 0.25 | 85.03 |  | 0.25 |  |  | <10 | 1 | 1 | 2 | 4 | 2 |  | 0 |  | 0 |  |  |  |  | 6728710
TR | 6 | Birch Drive | CTY M North, High-FT Lake Rd | High Lake Road | 0.25 | 85.28 | 0.25 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 0 |  |  | 0 |  |  |  |  | 6728710
TR | 1 | Blaisdell Street | Main Street, CTY K West | Ada, Blueberry | 0.17 | 85.45 |  | 0.17 |  |  |  | 1 | 1 | 2 | 4 | 2 |  | 0 |  | 0 |  |  |  |  | 6728710
TR | 1 | Community Street | CTY K West | Blaisdell Street | 0.2 | 85.65 |  | 0.2 |  |  |  | 1 | 1 | 2 | 4 | 2 |  | 0 |  | 0 |  |  |  |  | 6728710
TR | 5 | Maple Lake Road | CTY K West | XX | 0.35 | 86 | 0.35 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 0.35 |  |  | 14000 |  |  |  |  | 6742710
TR | 2 | Reible Court | Old K | XX | 0.12 | 86.12 |  | 0.12 |  |  |  | 1 | 1 | 2 | 4 | 2 |  | 0.12 |  | 11400 |  |  |  |  | 6754110
TR | 6 | River lane | CTY K West | XX | 0.2 | 86.32 | 0.2 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 0 |  |  | 0 |  |  |  |  | 6754110
TR | 6 | South Rudolph Lake Lane | CTY H | Rudolph Lake Lane | 0.26 | 86.58 | 0.26 |  |  | 1987 |  | 1 | 1 | 2 | 4 | 2 |  |  |  | 0 |  |  |  |  | 6754110
TR | 5 | West Big Lake Road (lane) | CTY K West | XX | 1.04 | 87.62 | 1.04 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 1.04 |  |  | 41600 |  |  |  |  | 6795710 |  | one house, why is this a town road?
TR | 5 | Boat Landing Road (Island lake) | US 51 North | Island Lake Road | 0.5 | 88.12 | 0.5 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 0.5 |  |  | 20000 |  |  |  |  | 6815710
TR | 1 | Day Lake Landing Road | Day Lake Road | XXX | 0.22 | 88.34 | 0.22 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 0 |  |  | 0 |  |  |  |  | 6815710
TR | 5 | Day Lake Road | North Creek Road | US 51 North | 2.91 | 91.25 | 2.91 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 2.91 |  |  | 58200 |  |  |  |  | 6873910 |  | Basic work, not full gravel work up
TR | 4 | Marsh Road | CTY M South | CTY K West | 1.04 | 92.29 | 1.04 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 |  | 1.04 |  | 62400 |  |  |  |  | 6936310 |  | Create Bike bypass for through riders, better use of events
TR | 6 | Vandercook Road | CTY M South | XX | 0.08 | 92.37 | 0.08 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 0 |  |  | 0 | [6 empty] | trapped between Arbor Vitae roads, snowmobile trail 100%
TR | 1 | Good Life Lane | CTY M North | Airport Road | 0.44 | 92.81 |  |  | 0.44 |  |  | 1 | 1 | 1 | 3 | 1 |  |  | 0 | 0
TR | 6 | Jag Lake Road | CTY H | XX | 0.08 | 92.89 | 0.08 |  |  |  |  | 1 | 0.5 | 2 | 3.5 | 1 |  | 0 |  | 0 | [6 empty] | boat landing
TR | 1 | Round Lake Road | CTY K West | Bear Lake Road | 0.1 | 92.99 |  | 0.1 |  |  |  | 1 | 0.5 | 2 | 3.5 | 1 |  | 0 |  | 0
TR | 1 | Cemetary Road | CTY K West | XX | 0.18 | 93.17 |  | 0.18 |  |  |  | 1 | 0.5 | 1 | 2.5 | 0.5 |  | 0 |  | 0
TR | 0 | Old 51 East Hoffman Road |  | 0.26 | 0 | 93.17 | [8 empty] | 0
TR | 0 | Old 51 Old H |  | 1.17 | 0 | 93.17 | [8 empty] | 0
TR | 1 | Round Lake Road (Presque Isle) | CTY K West | Bear Lake Road | 1.25 | 94.42 |  | 1.25 | [6 empty] | 0 |  |  | 0 |  | 0
TR |  | Town Road 127 |  |  | 0.1 | 94.52 | [8 empty] | 0
TR |  | Town Road 133 |  |  | 0.15 | 94.67 | [8 empty] | 0
|  | 20% | [23 empty] | 617900
[5 empty] | 93.17 |  | 26.04 | 55.17 | 8.57 | [7 empty] | 13.74 | 34.56 | 15.86 | 6936310 |  |  |  |  | TOTAL ESTIMATED COST
[8 empty] | Town Road Mileage | 89.78 | [7 empty] | Improvement Mileage |  | 64.16 | [6 empty] | 6936310
[17 empty] | Percent of Total Mileage |  | 71.46%
[17 empty] | % of | Accum. |  | Cost by 20%
[6 empty] | COLOR KEY | [10 empty] | Dollars | Miles | % | Increments
[6 empty] | 1 | Recently Updated, Or in Good Condition - No work planned | [9 empty] | 48.05% | 19.05 | 20 | 3333180
[6 empty] | 2 | Paved Road, repaving planned, same surface | [9 empty] | 18.18% | 36.81 | 20 | 1260880
[6 empty] | 3 | Paved Road, repaving planned, new surface | [9 empty] | 15% | 55.58 | 20 | 1040400
[6 empty] | 4 | Existing Gravel Road, planned upgrade to pavement | [9 empty] | 9.86% | 74.35 | 20 | 683950
[6 empty] | 5 | Existing Gravel Road, general grading and gravel | [9 empty] | 8.908% | 92.29 | 20 | 617900
[6 empty] | 6 | Existing Gravel Road/Fire Road - No Plans | [11 empty] | 100 | 6936310
PAVING COST PER MILE
|  |  |  | Existing Surface | Gravel | Chip Seal | Asphalt
|  | Gravel |  | GRAVEL | 40000 | 60000 | 197000
|  | Chip Seal |  | CHIP SEAL | 40000 | 95000 | 216000
|  | Asphalt |  | ASPHALT | 40000 | 95000 | 216000
Note on U3: Greg Van Grinsven: Removed 1.5 multiplier factor to widen the road for bike trail loop
Note on U9: Greg Van Grinsven: Removed 1.5 multiplier factor to widen the road for bike trail loop
Note on U16: Greg Van Grinsven: Removed 1.5 multiplier factor to widen the road for bike trail loop
Note on U17: Greg Van Grinsven: Removed 1.5 multiplier factor to widen the road for bike trail loop
Note on U18: Greg Van Grinsven: Removed 1.5 multiplier factor to widen the road for bike trail loop
Note on H147: Greg Van Grinsven: Add $19,000 per mile to pulverize chip seal or asphalt material.
Note on H148: Greg Van Grinsven: Add $19,000 per mile to pulverize chip seal or asphalt material.

## Roads-Priority Grp No Asphalt
03_02_17 | PLAN |  |  |  | Length |  |  | SURFACE TYPE |  |  |  | RATING |  |  |  |  | RESURFACE PLAN |  |  |  | RESURFACE |  | Work Scope |  | Extra Work | ACCUM.
TYPE | CAT | ROAD NAME | Primary Access Road | Secondary Access Road | Miles | Accum. | Gravel | Chip | Asphalt | Seal Coated or Resurfaced |  | Traffic | Occupancy | Condition | Priority | Weighted | Gravel | Chip | Asphalt | Alt 1 | COST EST | Surface | Engrg | Extra | Description | COST EST |  | COMMENTS
TR | 3 | Allen Road | CTY M North | High Lake Road | 0.68 | 0.68 |  | 0.68 |  | 1975, 1990 |  | 5 | 5 | 5 | 15 | 125 |  | 0.68 |  |  | 96900 |  |  |  |  | 96900 |  | upgrade to asphalt, widen 8' for Bike lanes (White Deer Loop)
TR | 3 | Fishtrap Lake Road | CTY M North, High-FT Lake Rd | XX | 2.04 | 2.72 |  | 2.04 |  | 72,73,75,82,86 |  | 5 | 5 | 5 | 15 | 125 |  | 2.04 |  |  | 193800 |  |  |  |  | 290700 |  | Do we want all or % as Asphalt??? Shown with asphalt to trail corner
TR | 3 | Newcomb Lane | CTY K West | XX | 3.5 | 6.22 |  | 3.5 |  | 78,80,83,88,92 |  | 5 | 5 | 5 | 15 | 125 |  | 3.5 |  |  | 332500 |  |  |  |  | 623200 |  | Why Asphalt? Not a high population area like Fishtrap Lake Rd.
TR | 3 | North Creek Road | CTY M South | CTY H | 4.57 | 10.79 |  | 4.57 |  | 75, 76, 87, 92 |  | 5 | 5 | 5 | 15 | 125 |  | 4.57 |  |  | 434150 |  |  |  |  | 1057350 |  | Possible width increase for Bike Route, Cost share with DNR
TR | 3 | Fallon Road | CTY K West | XX | 2.08 | 12.87 |  | 2.08 |  | 1984, 1986 |  | 5 | 5 | 4 | 14 | 100 |  | 2.08 |  |  | 197600 |  |  |  |  | 1254950 |  |  | 0.13945
TR | 2 | Island Lake Road | US 51 North | XX | 1.28 | 14.15 |  | 1.28 |  | 1987 |  | 4 | 5 | 4 | 13 | 80 |  | 1.28 |  |  | 121600 |  |  |  |  | 1376550
TR | 2 | High-Fishtrap Lake Road | CTY M North | XX | 1.1 | 15.25 |  | 1.1 |  |  |  | 5 | 5 | 3 | 13 | 75 |  | 1.1 |  |  | 156750 |  |  |  |  | 1533300 |  | asphalt for loop, add 8' to width
TR | 4 | Big Muskellunge Road | CTY M South | XX | 2.7 | 17.95 | 1.2 | 1 | 0.5 | 1976 |  | 5 | 3 | 4 | 12 | 60 |  | 2.2 |  |  | 209000 |  |  |  |  | 1742300
TR | 2 | Kern Lane | CTY m South | North Creek Road | 1.1 | 19.05 |  | 1.1 |  |  |  | 3 | 4 | 5 | 12 | 60 |  | 1.1 |  |  | 104500 |  |  |  |  | 1846800 |  |  | 0.20641
TR | 4 | Airport Road (paved) | CTY M North | Dairymen's Road | 2.45 | 21.5 |  | 1.45 |  | 1969, 1984 |  | 5 | 5 | 2 | 12 | 50 |  | 0 |  |  | 0
|  | 20% | [24 empty] | 1846800
TR | 2 | Shamrock Lane | CTY K West | Highland Drive | 0.4 | 21.9 |  | 0.4 |  |  |  | 3 | 4 | 4 | 11 | 48 |  | 0.4 |  |  | 38000 |  |  |  |  | 1884800
TR | 2 | Concora Road | Old K | XX | 0.8 | 22.7 |  | 0.8 |  |  |  | 3 | 3 | 5 | 11 | 45 |  | 0.8 |  |  | 76000 |  |  |  |  | 1960800
TR | 2 | High Lake Road |  |  | 3.8 | 26.5 |  | 1.3 |  |  |  | 3 | 3 | 5 | 11 | 45 |  | 1.8 |  |  | 171000 |  |  |  |  | 2131800 |  | Between Allen and Ridge is okay, Chip ridge to end, asphalt loop leg
TR | 2 | Old K Road | CTY M, Main Street | CTYK East | 2.79 | 29.29 |  | 2.79 |  | 1969, 1991 |  | 3 | 3 | 5 | 11 | 45 |  | 2.79 |  |  | 397575 |  |  |  |  | 2529375 |  | widen 8' for bike loop (Asphalt??)
TR | 3 | Dairymens Road | CTY M North | XX | 1.55 | 30.84 |  | 1.55 |  | 1973, 1988 |  | 4 | 5 | 2 | 11 | 40 |  | 1.55 |  |  | 502200 |  |  |  |  | 3031575 |  | Asphalt to benefit Dairymens and Bike loop, widen 8'
TR | 1 | Oswego-Fishtrap Lake Road | CTY M North, High-FT Lake Rd | Fishtrap Road | 1.9 | 32.74 |  | 1.9 |  |  |  | 4 | 5 | 2 | 11 | 40 |  | 0 |  |  | 0 |  |  |  |  | 3031575
TR | 1 | South Town Line | US 51 North | XX | 1.36 | 34.1 |  | 1.36 |  | 1976, 1988 |  | 4 | 5 | 2 | 11 | 40 |  | 0 |  |  | 0 |  |  |  |  | 3031575
TR | 2 | Bakken Road (East) | CTY H | HWY 51 N | 1.07 | 35.17 |  | 1.07 |  | 67,68 |  | 3 | 3 | 4 | 10 | 36 |  | 1.07 |  |  | 101650 |  |  |  |  | 3133225 |  | Asphalt upgrade??
TR | 3 | Highland Drive | CTY K West | CTY M North | 0.28 | 35.45 |  | 0.28 |  | 1976, 1990 |  | 3 | 3 | 4 | 10 | 36 |  | 0.28 |  |  | 0 |  |  |  |  | 3133225 |  | Upgrade for Bike Loop and Event Bypass support
TR | 2 | Rudolph Lake Lane | CTY H | XX | 0.6 | 36.05 |  | 0.6 |  |  |  | 3 | 4 | 3 | 10 | 36 |  | 0.6 |  |  | 57000 |  |  |  |  | 3190225
TR | 2 | Wool Lake Lane | CTY K West | XX | 0.76 | 36.81 |  | 0.76 |  | 1967, 1972, 1983 |  | 3 | 3 | 4 | 10 | 36 |  | 0.76 |  |  | 72200 |  |  |  |  | 3262425 |  |  | 0.39885
TR | 1 | North Town Line Rd (Town Road 116) | US 51 North | Le Fave Rd, Island Lake Rd | 1 | 37.81 |  | 1 |  | 1991 |  | 4 | 4 | 2 | 10 | 32 |  | 0 |  |  | 0 | [7 empty] | #DIV/0!
|  | 20% | [24 empty] | 1415625
TR | 2 | Harmony Point Lane | US 51 North | between M and H | 0.6 | 38.41 |  | 0.6 |  | 1974, 1982 |  | 2 | 3 | 5 | 10 | 30 |  | 0.6 |  |  | 57000 |  |  |  |  | 3319425 |  | narrow road | 0.42093
TR | 2 | Shore Drive | CTY K West | Newcomb Lane | 1.03 | 39.44 |  | 1.03 |  | 1991 |  | 2 | 3 | 5 | 10 | 30 |  | 1.03 |  |  | 97850 |  |  |  |  | 3417275
TR | 1 | Bakken Road (West) | CTY H | HWY 51 N | 2.15 | 41.59 |  | 2.15 |  |  |  | 3 | 3 | 3 | 9 | 27 |  | 0 |  |  | 0
TR | 2 | La Fave Road | US 51 North | Island Lake Road | 1.24 | 42.83 |  | 1.24 |  | 1970 |  | 3 | 3 | 3 | 9 | 27 |  | 0.25 |  |  | 23750 |  |  |  |  | 3441025 |  | Northwest segment only
TR | 1 | Ben Bendrick Drive (Lake Shore Drive) | CTY M South | XX | 1.7 | 44.53 |  |  | 1.7 |  |  | 4 | 3 | 2 | 9 | 24 |  |  | 0 |  | 0 |  |  |  |  | 3441025
TR | 2 | Green Street | CTY M | Old K | 0.27 | 44.8 |  | 0.27 |  |  |  | 4 | 2 | 3 | 9 | 24 |  | 0.27 |  |  | 25650 |  |  |  |  | 3466675
TR | 2 | High Pines Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln | 1.1 | 45.9 |  | 1.1 |  | 1978 |  | 3 | 4 | 2 | 9 | 24 |  | 1.1 |  |  | 104500 |  |  |  |  | 3571175 |  | needs improved turn around area
TR | 2 | Lucas Lane | CTY K West | XX | 0.15 | 46.05 |  | 0.15 |  | 1971 |  | 2 | 2 | 5 | 9 | 20 |  | 0.15 |  |  | 14250 |  |  |  |  | 3585425 |  | paved to start of campground
TR | 2 | Arrowhead Drive | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road | 0.6 | 46.65 | 0.15 | 0.45 |  | 82, 88 |  | 2 | 3 | 3 | 8 | 18 |  | 0.6 |  |  | 51750 |  |  |  |  | 3637175 |  | turn around work
TR | 2 | Evergreen Lane | CTY K West | XX | 1.98 | 48.63 |  | 1.98 |  | 1974 |  | 3 | 2 | 3 | 8 | 18 |  | 1.98 |  |  | 188100 |  |  |  |  | 3825275 |  | check condition
TR | 2 | Mann Lake Road | CTY M South | XX | 0.75 | 49.38 |  | 0.75 |  | 1973, 1990 |  | 2 | 3 | 3 | 8 | 18 |  | 0.65 |  |  | 61750 |  |  |  |  | 3887025 |  | first .1m ok, no turn around
TR | 2 | Middle Gresham Lane | US 51 North (near H) | XX | 0.43 | 49.81 |  | 0.43 |  |  |  | 2 | 3 | 3 | 8 | 18 |  | 0.43 |  |  | 40850 |  |  |  |  | 3927875
TR | 2 | Keego Road | CTY K West | XX | 1.25 | 51.06 |  | 1.25 |  | 1984 |  | 2 | 2 | 4 | 8 | 16 | 0 | 1.25 |  |  | 118750 |  |  |  |  | 4046625
TR | 2 | Little Rice Lane | CTY M North | XX | 0.28 | 51.34 |  | 0.28 |  |  |  | 2 | 2 | 4 | 8 | 16 |  | 0.28 |  |  | 26600 |  |  |  |  | 4073225
TR | 2 | Rintlemen | CTY K West | Fallon Road | 0.6 | 51.94 |  | 0.6 |  |  |  | 2 | 2 | 4 | 8 | 16 |  | 0.6 |  |  | 57000 |  |  |  |  | 4130225
TR | 2 | Boulder Lane | CTY M North | XX | 0.4 | 52.34 |  | 0.4 |  |  |  | 1 | 3 | 4 | 8 | 12 |  | 0.4 |  |  | 38000 |  |  |  |  | 4168225
TR | 4 | Camp Manitowish Lane (East) | CTY K West | XX | 0.5 | 52.84 | 0.5 |  |  |  |  | 2 | 2 | 3 | 7 | 12 |  | 0.5 |  |  | 30000 |  |  |  |  | 4198225 |  | pave it since CMW will be carrying big tax bill
TR | 6 | Clear View Drive | CTY K West | Fallon Road | 0.34 | 53.18 | 0.34 |  |  |  |  | 3 | 2 | 2 | 7 | 12 | 0 |  |  |  | 0 |  |  |  |  | 4198225 |  | good condition, consider paving all or part
TR | 3 | Grahl Lane | CTY H | XX | 0.43 | 53.61 | 0.43 |  |  |  |  | 3 | 2 | 2 | 7 | 12 |  | 0.43 |  |  | 25800 |  |  |  |  | 4224025
TR | 5 | Nebish lake Road | CTY K West | XX | 1.97 | 55.58 | 1.97 |  |  |  |  | 4 | 1 | 3 | 8 | 12 | 1.97 |  |  |  | 78800 |  |  |  |  | 4302825 |  |  | 0.60223
|  | 20% | [24 empty] | 1040400
TR | 5 | Old 51 Road (Bakken Rd - Island Lake Rd) | CTY H, Bakken Rd (east) | US 51 N, Island Lake Rd | 1.8 | 57.38 | 1.8 |  |  | 1980 |  | 2 | 2 | 3 | 7 | 12 | 1.8 |  |  |  | 72000 |  |  |  |  | 4374825 |  | snowmobile % | 0.62174
TR | 5 | Ridge Lane | CTY M North, High-FT Lake Rd | High Lake Rd | 1.2 | 58.58 | 0.3 | 0.9 |  | 1983 |  | 3 | 4 | 1 | 8 | 12 | 0.3 | 0 |  |  | 12000 |  |  |  |  | 4386825
TR | 1 | Bear Lake Road | CTY K West | XX | 3.26 | 61.84 |  |  | 3.26 | 1971, 1974, 1986 | 2015 | 3 | 3 | 1 | 7 | 9 |  |  | 0 |  | 0 | [6 empty] | repaved with asphalt in 2015
TR | 5 | Dam Road | CTY M North | High-Fishtrap Lake Road | 0.8 | 62.64 | 0.8 |  |  |  |  | 3 | 1 | 3 | 7 | 9 | 0.8 |  |  |  | 32000 |  |  |  |  | 4418825
TR | 2 | Glen Lake Road | CTY K West | Shamrock Road | 0.25 | 62.89 |  | 0.25 |  | 1988 |  | 1 | 3 | 3 | 7 | 9 |  | 0.25 |  |  | 23750 |  |  |  |  | 4442575
TR | 5 | Nixon Lake Road | CTY K East | XX | 2.6 | 65.49 | 2.6 |  |  |  |  | 3 | 1 | 3 | 7 | 9 | 2.6 |  |  |  | 104000 |  |  |  |  | 4546575 |  | Seek cost share with DNR
TR | 1 | Old 51 Road (Town Line - Island Lake Rd) | US 51 North | Town Line Rd, Island lake Rd | 1.07 | 66.56 |  | 1.07 |  |  |  | 3 | 1 | 3 | 7 | 9 |  | 0 |  |  | 0 |  |  |  |  | 4546575
TR | 1 | Rustic Colony Lane | CTY M North | Airport Road | 0.27 | 66.83 |  | 0.27 |  |  |  | 1 | 3 | 3 | 7 | 9 | 0 | 0 |  |  | 0 |  |  |  |  | 4546575
TR | 4 | Airport Road (gravel) |  |  | 1 | 67.83 | 1 |  |  |  |  | 2 | 1 | 4 | 7 | 8 | 0 | 1 | 0 |  | 60000 |  |  |  |  | 4606575 |  | Pave one mike of gravel to complete bike trail loop
TR | 1 | Camp Manitowish Lane (West) | CTY K West | XX | 0.5 | 68.33 |  | 0.5 |  |  |  | 2 | 2 | 2 | 6 | 8 |  | 0 |  |  | 0 |  |  |  |  | 4606575
TR | 4 | Platinum Lane | CTY H | Grahl Lane | 0.23 | 68.56 | 0.23 |  |  |  |  | 2 | 2 | 2 | 6 | 8 |  | 0.23 |  |  | 13800 |  |  |  |  | 4620375
TR | 1 | Rocky Reef Lane | CTY M South | CTY N West | 0.54 | 69.1 |  | 0.54 |  | 1982, 1992 |  | 2 | 2 | 2 | 6 | 8 |  | 0 |  |  | 0 |  |  |  |  | 4620375 |  | poor turn around area
TR | 2 | Stiloski Lane | CTY M North, High-FT Lake Rd | Fishtrap Road | 0.37 | 69.47 |  | 0.37 |  | 1975 |  | 1 | 2 | 4 | 7 | 8 |  | 0.37 |  |  | 35150 |  |  |  |  | 4655525
TR | 4 | Sunset Lane | CTY M South, North Creek Rd | Kern lane, Trout lane | 0.3 | 69.77 | 0.3 |  |  |  |  | 1 | 2 | 4 | 7 | 8 | 0 | 0.3 |  |  | 18000 |  |  |  |  | 4673525 |  | gravel, is this a town road? Pave it??
TR |  | Town Road 119 (Clear View) | CTY K West, Fallon Rd | Clear View Drive | 0.14 | 69.91 | 0.25 |  |  |  |  | 2 | 2 | 2 | 6 | 8 |  |  | 0 |  | 0 |  |  |  |  | 4673525
TR | 2 | Trout Lane | CTY M South, North Creek Rd | Kern lane | 0.2 | 70.11 |  | 0.2 |  |  |  | 1 | 2 | 4 | 7 | 8 |  | 0.2 |  |  | 19000 |  |  |  |  | 4692525
TR | 2 | Whitney Lake Road | CTY K West | XX | 1 | 71.11 | 0.1 | 0.9 |  |  |  | 1 | 2 | 4 | 7 | 8 |  | 1 |  |  | 91500 |  |  |  |  | 4784025
TR | 1 | Nichols Lake Lane | CTY H | CTY K West | 0.63 | 71.74 |  | 0.63 |  |  |  | 2 | 1 | 3 | 6 | 6 |  | 0 |  |  | 0 |  |  |  |  | 4784025
TR | 2 | Pine Lane | US 51 North | Bakken Road (west) | 0.45 | 72.19 |  | 0.45 |  | 1984 |  | 1 | 2 | 3 | 6 | 6 |  | 0.45 |  |  | 42750 |  |  |  |  | 4826775 |  | no turn around
TR | 6 | Point Lane | CTY K West | Fallon Rd, Rintleman Rd | 0.25 | 72.44 | 0.25 |  |  |  |  | 1 | 2 | 3 | 6 | 6 | 0 |  |  |  | 0 |  |  |  |  | 4826775 |  | Good condition, Consider Paving?
TR | 4 | South Shore Bay Lane | US 51 North | Island Lake Road | 0.15 | 72.59 | 0.15 |  |  |  |  | 1 | 2 | 3 | 6 | 6 |  | 0.15 |  |  | 6000 |  |  |  |  | 4832775
TR | 2 | Cattail Cove Lane | CTY K West | XX | 0.75 | 73.34 |  | 0.75 |  | 1992 |  | 1 | 1 | 5 | 7 | 5 |  | 0.75 |  |  | 71250 |  |  |  |  | 4904025
TR | 2 | Major Road | CTY M North | Dairymen's Road | 0.5 | 73.84 |  | 0.5 |  | 1973 |  | 1 | 1 | 5 | 7 | 5 |  | 0.5 |  |  | 47500 |  |  |  |  | 4951525 |  | road to nowhere, pave only if benefit to Dairymen's
0 | 5 | North Oswego Lake Road | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road | 0.24 | 74.08 | 0.24 |  |  | 1991 |  | 1 | 1 | 5 | 7 | 5 | 0.24 |  |  |  | 9600 |  |  |  |  | 4961125
TR | 2 | Sherry Drive | CTY M North, High-FT Lake Rd | High Lake Road | 0.05 | 74.13 |  | 0.05 |  |  |  | 1 | 1 | 5 | 7 | 5 |  | 0.05 |  |  | 4750 |  |  |  |  | 4965875
TR | 2 | Spruce Drive | CTY M North, High-FT Lake Rd | High Lake Road | 0.22 | 74.35 |  | 0.22 |  |  |  | 1 | 1 | 5 | 7 | 5 |  | 0.22 |  |  | 20900 |  |  |  |  | 4986775 |  | create turn-arounds at each end | 0.80561
|  | 20% | [24 empty] | 683950
TR | 2 | Allequash Lake Road | CTY M South | XX | 0.94 | 75.29 |  | 0.94 |  |  |  | 2 | 0.5 | 4 | 6.5 | 4 |  | 0.94 |  |  | 89300 |  |  |  |  | 5076075 |  |  | 0.8158
TR | 2 | Annes Place | Old K | Green Street | 0.14 | 75.43 |  | 0.14 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0.14 |  |  | 13300 |  |  |  |  | 5089375
TR | 1 | Birchwood Lane | CTY M North | Airport Road | 0.36 | 75.79 |  | 0.36 |  | 1984 |  | 1 | 2 | 2 | 5 | 4 |  | 0 |  |  | 0
TR | 4 | Blue Heron Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead | 0.12 | 75.91 | 0.12 |  |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.12 |  |  | 7200 |  |  |  |  | 5096575
TR | 1 | Blueberry Lane | Main Street, CTY K West | Center Street | 0.25 | 76.16 |  | 0.25 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0 |  |  | 0 |  |  |  |  | 5096575
TR | 2 | Campo Fiesta Lane | CTY M South | North Creek Road | 0.13 | 76.29 |  | 0.13 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.13 |  |  | 12350 |  |  |  |  | 5108925
TR | 1 | Center Street | CTY M South, Park Street | Marsh Rd, Ada, Blueberry | 0.31 | 76.6 |  | 0.31 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0 |  |  | 0 |  |  |  |  | 5108925
TR | 2 | Church Street | Old K | Green Street | 0.14 | 76.74 |  | 0.14 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0.14 |  |  | 13300 |  |  |  |  | 5122225
TR | 2 | Dolittle Road | CTY M North | Boulder Lane | 0.15 | 76.89 |  | 0.15 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.15 |  |  | 14250 |  |  |  |  | 5136475 |  | make widening part of agreement with owners, doable
TR | 2 | East Fitzgerald Lane | US 51 N, Island lake Rd | Fitzgerald Lane | 0.11 | 77 |  | 0.11 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.11 |  |  | 10450 |  |  |  |  | 5146925
TR | 2 | Fitzgerald Lane | US 51 North | Island Lake Road | 0.2 | 77.2 |  | 0.2 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.2 |  |  | 19000 |  |  |  |  | 5165925
TR | 4 | Little Crooked Lane | CTY K West | Bear Lake Road | 0.38 | 77.58 | 0.38 |  |  |  |  | 1 | 2 | 2 | 5 | 4 |  | 0.38 |  |  | 22800 |  |  |  |  | 5188725
TR | 1 | Town Hall Road | Around Community Building |  | 0.12 | 77.7 |  |  | 0.12 | 1987 |  | 4 | 1 | 1 | 6 | 4 |  |  |  |  | 0 |  |  |  |  | 5188725
TR | 4 | White Deer Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead | 0.12 | 77.82 | 0.12 |  |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.12 |  |  | 4800 |  |  |  |  | 5193525
TR | 4 | Balsam Lane | US 51 North | Bakken Road (west) | 0.35 | 78.17 | 0.35 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.35 |  |  | 21000 |  |  |  |  | 5214525 |  | no turn around
TR | 5 | Bass Lake Road | CTY K West | Bear Lake Road | 0.41 | 78.58 | 0.41 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.41 |  |  |  | 16400 |  |  |  |  | 5230925
TR | 5 | Birch Point Lane | CTY K West | Bear Lake Road | 0.19 | 78.77 | 0.19 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.19 |  |  |  | 7600 |  |  |  |  | 5238525
TR | 2 | Charlotte Place Lane | US 51 North | XX | 0.25 | 79.02 |  | 0.25 |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.25 |  |  | 23750 |  |  |  |  | 5262275
TR | 4 | En-Dah Win Lane | CTY K East | XX | 0.15 | 79.17 | 0.15 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.1 |  |  | 6000 |  |  |  |  | 5268275 |  | only pave to T
TR | 5 | Halverson Lane | CTY M South | XX | 0.12 | 79.29 | 0.12 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.12 |  |  |  | 4800 |  |  |  |  | 5273075
TR | 1 | Kassien Lane | US 51 North | Island Lake Road | 0.54 | 79.83 |  | 0.54 |  |  |  | 1 | 1 | 3 | 5 | 3 |  |  |  |  | 0 |  |  |  |  | 5273075
TR | 4 | Partridge Lane | CTY M North, High-FT Lake Rd | High Lake Road | 1.1 | 80.93 | 1.1 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 1.1 |  |  | 66000 |  |  |  |  | 5339075
TR | 4 | Perch Lane | CTY M South (by N) |  | 0.23 | 81.16 | 0.23 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.23 |  |  | 21850 |  |  |  |  | 5360925 |  | no turn around
TR | 5 | Pine Shores Lane | US 51 North | Bakken Road (west) | 0.06 | 81.22 | 0.06 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.06 |  |  |  | 2400 |  |  |  |  | 5363325
TR | 4 | Pinewood Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln | 0.12 | 81.34 | 0.12 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.12 |  |  | 7200 |  |  |  |  | 5370525
TR | 2 | Red Fox Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead | 0.09 | 81.43 |  | 0.09 |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.09 |  |  | 8550 |  |  |  |  | 5379075
TR | 1 | Senior Drive | CTY M, Park Street | Green Street | 0.2 | 81.63 |  | 0.2 |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0 |  |  | 0 |  |  |  |  | 5379075
TR | 6 | Street Lake Lane | CTY H | XX | 0.65 | 82.28 | 0.65 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  |  |  |  | 0 |  |  |  |  | 5379075 |  | do we want to pave??
TR | 5 | White Birch Lane | CTY M North, High-FT Lake Rd | Osewgo-FT Lake Road | 0.45 | 82.73 | 0.45 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.45 |  |  |  | 18000 |  |  |  |  | 5397075
TR | 6 | Keego Road East | CTY K West, Bear lake Road | Keego Road | 1.31 | 84.04 | 1.31 |  |  |  |  | 1 | 0.5 | 5 | 6.5 | 2.5 |  | 0 |  |  | 0 |  |  |  |  | 5397075
TR | 6 | Old Flambeau Road | CTY H?? | Bakken Rd ?? | 0.74 | 84.78 | 0.74 |  |  |  |  | 0.5 | 1 | 5 | 6.5 | 2.5 | 0 |  |  |  | 0 |  |  |  |  | 5397075 |  | No signs, looks like snowmobile trail, barely a road
TR | 1 | Ada Street | CTY M | Main Street | 0.25 | 85.03 |  | 0.25 |  |  | <10 | 1 | 1 | 2 | 4 | 2 |  | 0 |  |  | 0 |  |  |  |  | 5397075
TR | 6 | Birch Drive | CTY M North, High-FT Lake Rd | High Lake Road | 0.25 | 85.28 | 0.25 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 0 |  |  |  | 0 |  |  |  |  | 5397075
TR | 1 | Blaisdell Street | Main Street, CTY K West | Ada, Blueberry | 0.17 | 85.45 |  | 0.17 |  |  |  | 1 | 1 | 2 | 4 | 2 |  | 0 |  |  | 0 |  |  |  |  | 5397075
TR | 1 | Community Street | CTY K West | Blaisdell Street | 0.2 | 85.65 |  | 0.2 |  |  |  | 1 | 1 | 2 | 4 | 2 |  | 0 |  |  | 0 |  |  |  |  | 5397075
TR | 5 | Maple Lake Road | CTY K West | XX | 0.35 | 86 | 0.35 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 0.35 |  |  |  | 14000 |  |  |  |  | 5411075
TR | 2 | Reible Court | Old K | XX | 0.12 | 86.12 |  | 0.12 |  |  |  | 1 | 1 | 2 | 4 | 2 |  | 0.12 |  |  | 11400 |  |  |  |  | 5422475
TR | 6 | River lane | CTY K West | XX | 0.2 | 86.32 | 0.2 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 0 |  |  |  | 0 |  |  |  |  | 5422475
TR | 6 | South Rudolph Lake Lane | CTY H | Rudolph Lake Lane | 0.26 | 86.58 | 0.26 |  |  | 1987 |  | 1 | 1 | 2 | 4 | 2 |  |  |  |  | 0 |  |  |  |  | 5422475
TR | 5 | West Big Lake Road (lane) | CTY K West | XX | 1.04 | 87.62 | 1.04 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 1.04 |  |  |  | 41600 |  |  |  |  | 5464075 |  | one house, why is this a town road?
TR | 5 | Boat Landing Road (Island lake) | US 51 North | Island Lake Road | 0.5 | 88.12 | 0.5 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 0.5 |  |  |  | 20000 |  |  |  |  | 5484075
TR | 1 | Day Lake Landing Road | Day Lake Road | XXX | 0.22 | 88.34 | 0.22 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 0 |  |  |  | 0 |  |  |  |  | 5484075
TR | 5 | Day Lake Road | North Creek Road | US 51 North | 2.91 | 91.25 | 2.91 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 2.91 |  |  |  | 58200 |  |  |  |  | 5542275 |  | Basic work, not full gravel work up
TR | 4 | Marsh Road | CTY M South | CTY K West | 1.04 | 92.29 | 1.04 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 |  | 1.04 |  |  | 62400 |  |  |  |  | 5604675 |  | Create Bike bypass for through riders, better use of events
TR | 6 | Vandercook Road | CTY M South | XX | 0.08 | 92.37 | 0.08 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 0 |  |  |  | 0 | [6 empty] | trapped between Arbor Vitae roads, snowmobile trail 100%
TR | 1 | Good Life Lane | CTY M North | Airport Road | 0.44 | 92.81 |  |  | 0.44 |  |  | 1 | 1 | 1 | 3 | 1 |  |  | 0 |  | 0
TR | 6 | Jag Lake Road | CTY H | XX | 0.08 | 92.89 | 0.08 |  |  |  |  | 1 | 0.5 | 2 | 3.5 | 1 |  | 0 |  |  | 0 | [6 empty] | boat landing
TR | 1 | Round Lake Road | CTY K West | Bear Lake Road | 0.1 | 92.99 |  | 0.1 |  |  |  | 1 | 0.5 | 2 | 3.5 | 1 |  | 0 |  |  | 0
TR | 1 | Cemetary Road | CTY K West | XX | 0.18 | 93.17 |  | 0.18 |  |  |  | 1 | 0.5 | 1 | 2.5 | 0.5 |  | 0 |  |  | 0
TR | 0 | Old 51 East Hoffman Road |  | 0.26 | 0 | 93.17 | [8 empty] | 0
TR | 0 | Old 51 Old H |  | 1.17 | 0 | 93.17 | [8 empty] | 0
TR | 1 | Round Lake Road (Presque Isle) | CTY K West | Bear Lake Road | 1.25 | 94.42 |  | 1.25 | [6 empty] | 0 |  |  | 0 |  |  | 0
TR |  | Town Road 127 |  |  | 0.1 | 94.52 | [8 empty] | 0
TR |  | Town Road 133 |  |  | 0.15 | 94.67 | [8 empty] | 0
|  | 20% | [24 empty] | 617900
[5 empty] | 93.17 |  | 26.04 | 57.72 | 6.02 | [7 empty] | 13.74 | 50.42 | 0 |  | 5604675 |  |  |  |  | TOTAL ESTIMATED COST
[8 empty] | Town Road Mileage | 89.78 | [7 empty] | Improvement Mileage |  | 64.16 | [7 empty] | 5604675
[17 empty] | Percent of Total Mileage |  | 71.46%
[17 empty] | % of | Accum. |  |  | Cost by 20%
[6 empty] | COLOR KEY | [10 empty] | Dollars | Miles | % |  | Increments
[6 empty] | 1 | Recently Updated, Or in Good Condition - No work planned | [9 empty] | 32.95% | 19.05 | 20 |  | 1846800
[6 empty] | 2 | Paved Road, repaving planned, same surface | [9 empty] | 25.26% | 36.81 | 20 |  | 1415625
[6 empty] | 3 | Paved Road, repaving planned, new surface | [9 empty] | 18.56% | 55.58 | 20 |  | 1040400
[6 empty] | 4 | Existing Gravel Road, planned upgrade to pavement | [9 empty] | 12.2% | 74.35 | 20 |  | 683950
[6 empty] | 5 | Existing Gravel Road, general grading and gravel | [9 empty] | 11.02% | 92.29 | 20 |  | 617900
[6 empty] | 6 | Existing Gravel Road/Fire Road - No Plans | [11 empty] | 100 |  | 5604675
PAVING COST PER MILE
|  |  |  | Existing Surface | Gravel | Chip Seal | Asphalt
|  | Gravel |  | GRAVEL | 40000 | 60000 | 197000
|  | Chip Seal |  | CHIP SEAL | 40000 | 95000 | 216000
|  | Asphalt |  | ASPHALT | 40000 | 95000 | 216000
Note on H147: Greg Van Grinsven: Add $19,000 per mile to pulverize chip seal or asphalt material.
Note on H148: Greg Van Grinsven: Add $19,000 per mile to pulverize chip seal or asphalt material.

## Questions & Comments
Questions:
What about cost of markings, lines, signs?
What about easements costs for bike lanes, turn arounds, widening?
What about engineering costs for widening, turn arounds, general improvements
What bridge or culvert work should we include?
What roads, mileage have potential cost sharing with the DNR?
What grant money is available?
What potential do we have for the "new road" material?
How many miles of road can a contractor complete in a year?
Comments:
Road Prioritization Factors:
Traffic Levels, Occupancy, and Condition
All costs are estimates based upon average cost per mile for each road type, gravel, chip and seal, and asphalt.
Final costs will be determine once the engineeering work is completed. i.e. culverts, regrading, widening, turn around improvements etc.
Priority list may be modified to save on construction costs. i.e. roads may be grouped to minimize equipment setup and relocation costs
Additional discussion will be required to review needs / desires to add bike trail loops.
White Tail Dear Loop - High / Fishtrap Lake Road to Allen Road
Airport Loop - Dairymens Road to Airport Road
Lumberjack Trail Loop - Old K to Hwy K

## Roads-Option 1
1_7_17 | PLAN |  |  |  | Length |  |  | SURFACE TYPE |  |  |  | RATING |  |  |  |  | RESURFACE PLAN |  |  | RESURFACE |  | Work Scope |  | Extra Work | ACCUM.
TYPE | CAT | ROAD NAME | Primary Access Road | Secondary Access Road | Miles | Accum. | Gravel | Chip | Asphalt | Seal Coated or Resurfaced |  | Traffic | Occupancy | Condition | Priority | Weighted | Gravel | Chip | Asphalt | COST EST | Surface | Engrg | Extra | Description | COST EST |  | COMMENTS
TR | 3 | Allen Road | CTY M North | High Lake Road | 0.68 | 0.68 |  | 0.68 |  | 1975, 1990 |  | 5 | 5 | 5 | 15 | 125 |  | 0 | 0.68 | 105400 |  |  |  |  | 105400 |  | upgrade to asphalt, widen 8' for Bike lanes (White Deer Loop)
TR | 3 | Fishtrap Lake Road | CTY M North, High-FT Lake Rd | XX | 2.04 | 2.72 |  | 2.04 |  | 72,73,75,82,86 |  | 5 | 5 | 5 | 15 | 125 |  | 0.64 | 1.4 | 255400 |  |  |  |  | 360800 |  | Do we want all or % as Asphalt??? Shown with asphalt to trail corner
TR | 3 | Newcomb Lane | CTY K West | XX | 3.5 | 6.22 |  | 3.5 |  | 78,80,83,88,92 |  | 5 | 5 | 5 | 15 | 125 |  |  | 3.5 | 542500 |  |  |  |  | 903300 |  | Why Asphalt? Not a high population area like Fishtrap Lake Rd.
TR | 3 | North Creek Road | CTY M South | CTY H | 4.57 | 10.79 |  | 4.57 |  | 75, 76, 87, 92 |  | 5 | 5 | 5 | 15 | 125 |  |  | 4.57 | 708350 |  |  |  |  | 1611650 |  | Possible width increase for Bike Route, Cost share with DNR
TR | 3 | Fallon Road | CTY K West | XX | 2.08 | 12.87 |  | 2.08 |  | 1984, 1986 |  | 5 | 5 | 4 | 14 | 100 |  |  | 2.08 | 322400 |  |  |  |  | 1934050 |  |  | 0.13945
TR | 2 | Island Lake Road | US 51 North | XX | 1.28 | 14.15 |  | 1.28 |  | 1987 |  | 4 | 5 | 4 | 13 | 80 |  | 1.28 |  | 121600 |  |  |  |  | 2055650
TR | 2 | High-Fishtrap Lake Road | CTY M North | XX | 1.1 | 15.25 |  |  | 1.1 |  |  | 5 | 5 | 3 | 13 | 75 |  |  | 1.1 | 170500 |  |  |  |  | 2226150 |  | asphalt for loop, add 8' to width
TR | 4 | Big Muskellunge Road | CTY M South | XX | 2.7 | 17.95 | 1.2 | 1 | 0.5 | 1976 |  | 5 | 3 | 4 | 12 | 60 |  | 2.2 |  | 167000 |  |  |  |  | 2393150
TR | 2 | Kern Lane | CTY m South | North Creek Road | 1.1 | 19.05 |  | 1.1 |  |  |  | 3 | 4 | 5 | 12 | 60 |  | 1.1 |  | 104500 |  |  |  |  | 2497650 |  |  | 0.20641
TR | 4 | Airport Road (paved) | CTY M North | Dairymen's Road | 2.45 | 21.5 |  |  | 1.45 | 1969, 1984 |  | 5 | 5 | 2 | 12 | 50 |  |  | 0 | 0
|  | 20% | [23 empty] | 2497650
TR | 2 | Shamrock Lane | CTY K West | Highland Drive | 0.4 | 21.9 |  | 0.4 |  |  |  | 3 | 4 | 4 | 11 | 48 |  | 0.4 |  | 38000 |  |  |  |  | 2535650
TR | 2 | Concora Road | Old K | XX | 0.8 | 22.7 |  | 0.8 |  |  |  | 3 | 3 | 5 | 11 | 45 |  | 0.8 |  | 76000 |  |  |  |  | 2611650
TR | 2 | High Lake Road |  |  | 3.8 | 26.5 |  | 1.3 |  |  |  | 3 | 3 | 5 | 11 | 45 |  | 1.1 | 0.7 | 267250 |  |  |  |  | 2878900 |  | Between Allen and Ridge is okay, Chip ridge to end, asphalt loop leg
TR | 2 | Old K Road | CTY M, Main Street | CTYK East | 2.79 | 29.29 |  | 2.79 |  | 1969, 1991 |  | 3 | 3 | 5 | 11 | 45 |  | 2.79 |  | 265050 |  |  |  |  | 3143950 |  | widen 8' for bike loop (Asphalt??)
TR | 3 | Dairymens Road | CTY M North | XX | 1.55 | 30.84 |  | 1.55 |  | 1973, 1988 |  | 4 | 5 | 2 | 11 | 40 |  |  | 1.55 | 240250 |  |  |  |  | 3384200 |  | Asphalt to benefit Dairymens and Bike loop, widen 8'
TR | 1 | Oswego-Fishtrap Lake Road | CTY M North, High-FT Lake Rd | Fishtrap Road | 1.9 | 32.74 |  | 1.9 |  |  |  | 4 | 5 | 2 | 11 | 40 |  | 0 |  | 0 |  |  |  |  | 3384200
TR | 1 | South Town Line | US 51 North | XX | 1.36 | 34.1 |  | 1.36 |  | 1976, 1988 |  | 4 | 5 | 2 | 11 | 40 |  | 0 |  | 0 |  |  |  |  | 3384200
TR | 2 | Bakken Road (East) | CTY H | HWY 51 N | 1.07 | 35.17 |  | 1.07 |  | 67,68 |  | 3 | 3 | 4 | 10 | 36 |  | 1.07 |  | 101650 |  |  |  |  | 3485850 |  | Asphalt upgrade??
TR | 3 | Highland Drive | CTY K West | CTY M North | 0.28 | 35.45 |  | 0.28 |  | 1976, 1990 |  | 3 | 3 | 4 | 10 | 36 |  |  | 0.28 | 43400 |  |  |  |  | 3529250 |  | Upgrade for Bike Loop and Event Bypass support
TR | 2 | Rudolph Lake Lane | CTY H | XX | 0.6 | 36.05 |  | 0.6 |  |  |  | 3 | 4 | 3 | 10 | 36 |  | 0.6 |  | 57000 |  |  |  |  | 3586250
TR | 2 | Wool Lake Lane | CTY K West | XX | 0.76 | 36.81 |  | 0.76 |  | 1967, 1972, 1983 |  | 3 | 3 | 4 | 10 | 36 |  | 0.76 |  | 72200 |  |  |  |  | 3658450 |  |  | 0.39885
TR | 1 | North Town Line Rd (Town Road 116) | US 51 North | Le Fave Rd, Island Lake Rd | 1 | 37.81 |  | 1 |  | 1991 |  | 4 | 4 | 2 | 10 | 32 |  | 0 |  | 0 | [7 empty] | #DIV/0!
|  | 20% | [23 empty] | 1160800
TR | 2 | Harmony Point Lane | US 51 North | between M and H | 0.6 | 38.41 |  | 0.6 |  | 1974, 1982 |  | 2 | 3 | 5 | 10 | 30 |  | 0.6 |  | 57000 |  |  |  |  | 3715450 |  | narrow road | 0.42093
TR | 2 | Shore Drive | CTY K West | Newcomb Lane | 1.03 | 39.44 |  | 1.03 |  | 1991 |  | 2 | 3 | 5 | 10 | 30 |  | 1.03 |  | 97850 |  |  |  |  | 3813300
TR | 1 | Bakken Road (West) | CTY H | HWY 51 N | 2.15 | 41.59 |  | 2.15 |  |  |  | 3 | 3 | 3 | 9 | 27 |  | 0 |  | 0
TR | 2 | La Fave Road | US 51 North | Island Lake Road | 1.24 | 42.83 |  | 1.24 |  | 1970 |  | 3 | 3 | 3 | 9 | 27 |  | 0.25 |  | 23750 |  |  |  |  | 3837050 |  | Northwest segment only
TR | 1 | Ben Bendrick Drive (Lake Shore Drive) | CTY M South | XX | 1.7 | 44.53 |  |  | 1.7 |  |  | 4 | 3 | 2 | 9 | 24 |  |  | 0 | 0 |  |  |  |  | 3837050
TR | 2 | Green Street | CTY M | Old K | 0.27 | 44.8 |  | 0.27 |  |  |  | 4 | 2 | 3 | 9 | 24 |  | 0.27 |  | 25650 |  |  |  |  | 3862700
TR | 2 | High Pines Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln | 1.1 | 45.9 |  | 1.1 |  | 1978 |  | 3 | 4 | 2 | 9 | 24 |  | 1.1 |  | 104500 |  |  |  |  | 3967200 |  | needs improved turn around area
TR | 2 | Lucas Lane | CTY K West | XX | 0.15 | 46.05 |  | 0.15 |  | 1971 |  | 2 | 2 | 5 | 9 | 20 |  | 0.15 |  | 14250 |  |  |  |  | 3981450 |  | paved to start of campground
TR | 2 | Arrowhead Drive | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road | 0.6 | 46.65 | 0.15 | 0.45 |  | 82, 88 |  | 2 | 3 | 3 | 8 | 18 |  | 0.6 |  | 51750 |  |  |  |  | 4033200 |  | turn around work
TR | 2 | Evergreen Lane | CTY K West | XX | 1.98 | 48.63 |  | 1.98 |  | 1974 |  | 3 | 2 | 3 | 8 | 18 |  | 1.98 |  | 188100 |  |  |  |  | 4221300 |  | check condition
TR | 2 | Mann Lake Road | CTY M South | XX | 0.75 | 49.38 |  | 0.75 |  | 1973, 1990 |  | 2 | 3 | 3 | 8 | 18 |  | 0.65 |  | 61750 |  |  |  |  | 4283050 |  | first .1m ok, no turn around
TR | 2 | Middle Gresham Lane | US 51 North (near H) | XX | 0.43 | 49.81 |  | 0.43 |  |  |  | 2 | 3 | 3 | 8 | 18 |  | 0.43 |  | 40850 |  |  |  |  | 4323900
TR | 2 | Keego Road | CTY K West | XX | 1.25 | 51.06 |  | 1.25 |  | 1984 |  | 2 | 2 | 4 | 8 | 16 | 0 | 1.25 |  | 118750 |  |  |  |  | 4442650
TR | 2 | Little Rice Lane | CTY M North | XX | 0.28 | 51.34 |  | 0.28 |  |  |  | 2 | 2 | 4 | 8 | 16 |  | 0.28 |  | 26600 |  |  |  |  | 4469250
TR | 2 | Rintlemen | CTY K West | Fallon Road | 0.6 | 51.94 |  | 0.6 |  |  |  | 2 | 2 | 4 | 8 | 16 |  | 0.6 |  | 57000 |  |  |  |  | 4526250
TR | 2 | Boulder Lane | CTY M North | XX | 0.4 | 52.34 |  | 0.4 |  |  |  | 1 | 3 | 4 | 8 | 12 |  | 0.4 |  | 38000 |  |  |  |  | 4564250
TR | 4 | Camp Manitowish Lane (East) | CTY K West | XX | 0.5 | 52.84 | 0.5 |  |  |  |  | 2 | 2 | 3 | 7 | 12 |  | 0.5 |  | 30000 |  |  |  |  | 4594250 |  | pave it since CMW will be carrying big tax bill
TR | 6 | Clear View Drive | CTY K West | Fallon Road | 0.34 | 53.18 | 0.34 |  |  |  |  | 3 | 2 | 2 | 7 | 12 | 0 |  |  | 0 |  |  |  |  | 4594250 |  | good condition, consider paving all or part
TR | 3 | Grahl Lane | CTY H | XX | 0.43 | 53.61 | 0.43 |  |  |  |  | 3 | 2 | 2 | 7 | 12 |  | 0.43 |  | 25800 |  |  |  |  | 4620050
TR | 5 | Nebish lake Road | CTY K West | XX | 1.97 | 55.58 | 1.97 |  |  |  |  | 4 | 1 | 3 | 8 | 12 | 1.97 |  |  | 78800 |  |  |  |  | 4698850 |  |  | 0.60223
|  | 20% | [23 empty] | 1040400
TR | 5 | Old 51 Road (Bakken Rd - Island Lake Rd) | CTY H, Bakken Rd (east) | US 51 N, Island Lake Rd | 1.8 | 57.38 | 1.8 |  |  | 1980 |  | 2 | 2 | 3 | 7 | 12 | 1.8 |  |  | 72000 |  |  |  |  | 4770850 |  | snowmobile % | 0.62174
TR | 5 | Ridge Lane | CTY M North, High-FT Lake Rd | High Lake Rd | 1.2 | 58.58 | 0.3 | 0.9 |  | 1983 |  | 3 | 4 | 1 | 8 | 12 | 0.3 | 0 |  | 12000 |  |  |  |  | 4782850
TR | 1 | Bear Lake Road | CTY K West | XX | 3.26 | 61.84 |  |  | 3.26 | 1971, 1974, 1986 | 2015 | 3 | 3 | 1 | 7 | 9 |  |  | 0 | 0 | [6 empty] | repaved with asphalt in 2015
TR | 5 | Dam Road | CTY M North | High-Fishtrap Lake Road | 0.8 | 62.64 | 0.8 |  |  |  |  | 3 | 1 | 3 | 7 | 9 | 0.8 |  |  | 32000 |  |  |  |  | 4814850
TR | 2 | Glen Lake Road | CTY K West | Shamrock Road | 0.25 | 62.89 |  | 0.25 |  | 1988 |  | 1 | 3 | 3 | 7 | 9 |  | 0.25 |  | 23750 |  |  |  |  | 4838600
TR | 5 | Nixon Lake Road | CTY K East | XX | 2.6 | 65.49 | 2.6 |  |  |  |  | 3 | 1 | 3 | 7 | 9 | 2.6 |  |  | 104000 |  |  |  |  | 4942600 |  | Seek cost share with DNR
TR | 1 | Old 51 Road (Town Line - Island Lake Rd) | US 51 North | Town Line Rd, Island lake Rd | 1.07 | 66.56 |  | 1.07 |  |  |  | 3 | 1 | 3 | 7 | 9 |  | 0 |  | 0 |  |  |  |  | 4942600
TR | 1 | Rustic Colony Lane | CTY M North | Airport Road | 0.27 | 66.83 |  | 0.27 |  |  |  | 1 | 3 | 3 | 7 | 9 | 0 | 0 |  | 0 |  |  |  |  | 4942600
TR | 4 | Airport Road (gravel) |  |  | 1 | 67.83 | 1 |  |  |  |  | 2 | 1 | 4 | 7 | 8 | 0 | 1 | 0 | 60000 |  |  |  |  | 5002600 |  | Pave one mike of gravel to complete bike trail loop
TR | 1 | Camp Manitowish Lane (West) | CTY K West | XX | 0.5 | 68.33 |  | 0.5 |  |  |  | 2 | 2 | 2 | 6 | 8 |  | 0 |  | 0 |  |  |  |  | 5002600
TR | 4 | Platinum Lane | CTY H | Grahl Lane | 0.23 | 68.56 | 0.23 |  |  |  |  | 2 | 2 | 2 | 6 | 8 |  | 0.23 |  | 13800 |  |  |  |  | 5016400
TR | 1 | Rocky Reef Lane | CTY M South | CTY N West | 0.54 | 69.1 |  | 0.54 |  | 1982, 1992 |  | 2 | 2 | 2 | 6 | 8 |  | 0 |  | 0 |  |  |  |  | 5016400 |  | poor turn around area
TR | 2 | Stiloski Lane | CTY M North, High-FT Lake Rd | Fishtrap Road | 0.37 | 69.47 |  | 0.37 |  | 1975 |  | 1 | 2 | 4 | 7 | 8 |  | 0.37 |  | 35150 |  |  |  |  | 5051550
TR | 4 | Sunset Lane | CTY M South, North Creek Rd | Kern lane, Trout lane | 0.3 | 69.77 | 0.3 |  |  |  |  | 1 | 2 | 4 | 7 | 8 | 0 | 0.3 |  | 18000 |  |  |  |  | 5069550 |  | gravel, is this a town road? Pave it??
TR |  | Town Road 119 (Clear View) | CTY K West, Fallon Rd | Clear View Drive | 0.14 | 69.91 | 0.25 |  |  |  |  | 2 | 2 | 2 | 6 | 8 |  |  | 0 | 0 |  |  |  |  | 5069550
TR | 2 | Trout Lane | CTY M South, North Creek Rd | Kern lane | 0.2 | 70.11 |  | 0.2 |  |  |  | 1 | 2 | 4 | 7 | 8 |  | 0.2 |  | 19000 |  |  |  |  | 5088550
TR | 2 | Whitney Lake Road | CTY K West | XX | 1 | 71.11 | 0.1 | 0.9 |  |  |  | 1 | 2 | 4 | 7 | 8 |  | 1 |  | 91500 |  |  |  |  | 5180050
TR | 1 | Nichols Lake Lane | CTY H | CTY K West | 0.63 | 71.74 |  | 0.63 |  |  |  | 2 | 1 | 3 | 6 | 6 |  | 0 |  | 0 |  |  |  |  | 5180050
TR | 2 | Pine Lane | US 51 North | Bakken Road (west) | 0.45 | 72.19 |  | 0.45 |  | 1984 |  | 1 | 2 | 3 | 6 | 6 |  | 0.45 |  | 42750 |  |  |  |  | 5222800 |  | no turn around
TR | 6 | Point Lane | CTY K West | Fallon Rd, Rintleman Rd | 0.25 | 72.44 | 0.25 |  |  |  |  | 1 | 2 | 3 | 6 | 6 | 0 |  |  | 0 |  |  |  |  | 5222800 |  | Good condition, Consider Paving?
TR | 4 | South Shore Bay Lane | US 51 North | Island Lake Road | 0.15 | 72.59 | 0.15 |  |  |  |  | 1 | 2 | 3 | 6 | 6 |  | 0.15 |  | 6000 |  |  |  |  | 5228800
TR | 2 | Cattail Cove Lane | CTY K West | XX | 0.75 | 73.34 |  | 0.75 |  | 1992 |  | 1 | 1 | 5 | 7 | 5 |  | 0.75 |  | 71250 |  |  |  |  | 5300050
TR | 2 | Major Road | CTY M North | Dairymen's Road | 0.5 | 73.84 |  | 0.5 |  | 1973 |  | 1 | 1 | 5 | 7 | 5 |  | 0.5 |  | 47500 |  |  |  |  | 5347550 |  | road to nowhere, pave only if benefit to Dairymen's
0 | 5 | North Oswego Lake Road | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road | 0.24 | 74.08 | 0.24 |  |  | 1991 |  | 1 | 1 | 5 | 7 | 5 | 0.24 |  |  | 9600 |  |  |  |  | 5357150
TR | 2 | Sherry Drive | CTY M North, High-FT Lake Rd | High Lake Road | 0.05 | 74.13 |  | 0.05 |  |  |  | 1 | 1 | 5 | 7 | 5 |  | 0.05 |  | 4750 |  |  |  |  | 5361900
TR | 2 | Spruce Drive | CTY M North, High-FT Lake Rd | High Lake Road | 0.22 | 74.35 |  | 0.22 |  |  |  | 1 | 1 | 5 | 7 | 5 |  | 0.22 |  | 20900 |  |  |  |  | 5382800 |  | create turn-arounds at each end | 0.80561
|  | 20% | [23 empty] | 683950
TR | 2 | Allequash Lake Road | CTY M South | XX | 0.94 | 75.29 |  | 0.94 |  |  |  | 2 | 0.5 | 4 | 6.5 | 4 |  | 0.94 |  | 89300 |  |  |  |  | 5472100 |  |  | 0.8158
TR | 2 | Annes Place | Old K | Green Street | 0.14 | 75.43 |  | 0.14 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0.14 |  | 13300 |  |  |  |  | 5485400
TR | 1 | Birchwood Lane | CTY M North | Airport Road | 0.36 | 75.79 |  | 0.36 |  | 1984 |  | 1 | 2 | 2 | 5 | 4 |  | 0 |  | 0
TR | 4 | Blue Heron Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead | 0.12 | 75.91 | 0.12 |  |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.12 |  | 7200 |  |  |  |  | 5492600
TR | 1 | Blueberry Lane | Main Street, CTY K West | Center Street | 0.25 | 76.16 |  | 0.25 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0 |  | 0 |  |  |  |  | 5492600
TR | 2 | Campo Fiesta Lane | CTY M South | North Creek Road | 0.13 | 76.29 |  | 0.13 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.13 |  | 12350 |  |  |  |  | 5504950
TR | 1 | Center Street | CTY M South, Park Street | Marsh Rd, Ada, Blueberry | 0.31 | 76.6 |  | 0.31 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0 |  | 0 |  |  |  |  | 5504950
TR | 2 | Church Street | Old K | Green Street | 0.14 | 76.74 |  | 0.14 |  |  |  | 2 | 1 | 2 | 5 | 4 |  | 0.14 |  | 13300 |  |  |  |  | 5518250
TR | 2 | Dolittle Road | CTY M North | Boulder Lane | 0.15 | 76.89 |  | 0.15 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.15 |  | 14250 |  |  |  |  | 5532500 |  | make widening part of agreement with owners, doable
TR | 2 | East Fitzgerald Lane | US 51 N, Island lake Rd | Fitzgerald Lane | 0.11 | 77 |  | 0.11 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.11 |  | 10450 |  |  |  |  | 5542950
TR | 2 | Fitzgerald Lane | US 51 North | Island Lake Road | 0.2 | 77.2 |  | 0.2 |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.2 |  | 19000 |  |  |  |  | 5561950
TR | 4 | Little Crooked Lane | CTY K West | Bear Lake Road | 0.38 | 77.58 | 0.38 |  |  |  |  | 1 | 2 | 2 | 5 | 4 |  | 0.38 |  | 22800 |  |  |  |  | 5584750
TR | 1 | Town Hall Road | Around Community Building |  | 0.12 | 77.7 |  |  | 0.12 | 1987 |  | 4 | 1 | 1 | 6 | 4 |  |  |  | 0 |  |  |  |  | 5584750
TR | 4 | White Deer Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead | 0.12 | 77.82 | 0.12 |  |  |  |  | 1 | 1 | 4 | 6 | 4 |  | 0.12 |  | 4800 |  |  |  |  | 5589550
TR | 4 | Balsam Lane | US 51 North | Bakken Road (west) | 0.35 | 78.17 | 0.35 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.35 |  | 21000 |  |  |  |  | 5610550 |  | no turn around
TR | 5 | Bass Lake Road | CTY K West | Bear Lake Road | 0.41 | 78.58 | 0.41 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.41 |  |  | 16400 |  |  |  |  | 5626950
TR | 5 | Birch Point Lane | CTY K West | Bear Lake Road | 0.19 | 78.77 | 0.19 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.19 |  |  | 7600 |  |  |  |  | 5634550
TR | 2 | Charlotte Place Lane | US 51 North | XX | 0.25 | 79.02 |  | 0.25 |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.25 |  | 23750 |  |  |  |  | 5658300
TR | 4 | En-Dah Win Lane | CTY K East | XX | 0.15 | 79.17 | 0.15 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.1 |  | 6000 |  |  |  |  | 5664300 |  | only pave to T
TR | 5 | Halverson Lane | CTY M South | XX | 0.12 | 79.29 | 0.12 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.12 |  |  | 4800 |  |  |  |  | 5669100
TR | 1 | Kassien Lane | US 51 North | Island Lake Road | 0.54 | 79.83 |  | 0.54 |  |  |  | 1 | 1 | 3 | 5 | 3 |  |  |  | 0 |  |  |  |  | 5669100
TR | 4 | Partridge Lane | CTY M North, High-FT Lake Rd | High Lake Road | 1.1 | 80.93 | 1.1 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 1.1 |  | 66000 |  |  |  |  | 5735100
TR | 4 | Perch Lane | CTY M South (by N) |  | 0.23 | 81.16 | 0.23 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.23 |  | 21850 |  |  |  |  | 5756950 |  | no turn around
TR | 5 | Pine Shores Lane | US 51 North | Bakken Road (west) | 0.06 | 81.22 | 0.06 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.06 |  |  | 2400 |  |  |  |  | 5759350
TR | 4 | Pinewood Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln | 0.12 | 81.34 | 0.12 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.12 |  | 7200 |  |  |  |  | 5766550
TR | 2 | Red Fox Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead | 0.09 | 81.43 |  | 0.09 |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0.09 |  | 8550 |  |  |  |  | 5775100
TR | 1 | Senior Drive | CTY M, Park Street | Green Street | 0.2 | 81.63 |  | 0.2 |  |  |  | 1 | 1 | 3 | 5 | 3 |  | 0 |  | 0 |  |  |  |  | 5775100
TR | 6 | Street Lake Lane | CTY H | XX | 0.65 | 82.28 | 0.65 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  |  |  | 0 |  |  |  |  | 5775100 |  | do we want to pave??
TR | 5 | White Birch Lane | CTY M North, High-FT Lake Rd | Osewgo-FT Lake Road | 0.45 | 82.73 | 0.45 |  |  |  |  | 1 | 1 | 3 | 5 | 3 | 0.45 |  |  | 18000 |  |  |  |  | 5793100
TR | 6 | Keego Road East | CTY K West, Bear lake Road | Keego Road | 1.31 | 84.04 | 1.31 |  |  |  |  | 1 | 0.5 | 5 | 6.5 | 2.5 |  | 0 |  | 0 |  |  |  |  | 5793100
TR | 6 | Old Flambeau Road | CTY H?? | Bakken Rd ?? | 0.74 | 84.78 | 0.74 |  |  |  |  | 0.5 | 1 | 5 | 6.5 | 2.5 | 0 |  |  | 0 |  |  |  |  | 5793100 |  | No signs, looks like snowmobile trail, barely a road
TR | 1 | Ada Street | CTY M | Main Street | 0.25 | 85.03 |  | 0.25 |  |  | <10 | 1 | 1 | 2 | 4 | 2 |  | 0 |  | 0 |  |  |  |  | 5793100
TR | 6 | Birch Drive | CTY M North, High-FT Lake Rd | High Lake Road | 0.25 | 85.28 | 0.25 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 0 |  |  | 0 |  |  |  |  | 5793100
TR | 1 | Blaisdell Street | Main Street, CTY K West | Ada, Blueberry | 0.17 | 85.45 |  | 0.17 |  |  |  | 1 | 1 | 2 | 4 | 2 |  | 0 |  | 0 |  |  |  |  | 5793100
TR | 1 | Community Street | CTY K West | Blaisdell Street | 0.2 | 85.65 |  | 0.2 |  |  |  | 1 | 1 | 2 | 4 | 2 |  | 0 |  | 0 |  |  |  |  | 5793100
TR | 5 | Maple Lake Road | CTY K West | XX | 0.35 | 86 | 0.35 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 0.35 |  |  | 14000 |  |  |  |  | 5807100
TR | 2 | Reible Court | Old K | XX | 0.12 | 86.12 |  | 0.12 |  |  |  | 1 | 1 | 2 | 4 | 2 |  | 0.12 |  | 11400 |  |  |  |  | 5818500
TR | 6 | River lane | CTY K West | XX | 0.2 | 86.32 | 0.2 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 0 |  |  | 0 |  |  |  |  | 5818500
TR | 6 | South Rudolph Lake Lane | CTY H | Rudolph Lake Lane | 0.26 | 86.58 | 0.26 |  |  | 1987 |  | 1 | 1 | 2 | 4 | 2 |  |  |  | 0 |  |  |  |  | 5818500
TR | 5 | West Big Lake Road (lane) | CTY K West | XX | 1.04 | 87.62 | 1.04 |  |  |  |  | 1 | 1 | 2 | 4 | 2 | 1.04 |  |  | 41600 |  |  |  |  | 5860100 |  | one house, why is this a town road?
TR | 5 | Boat Landing Road (Island lake) | US 51 North | Island Lake Road | 0.5 | 88.12 | 0.5 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 0.5 |  |  | 20000 |  |  |  |  | 5880100
TR | 1 | Day Lake Landing Road | Day Lake Road | XXX | 0.22 | 88.34 | 0.22 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 0 |  |  | 0 |  |  |  |  | 5880100
TR | 5 | Day Lake Road | North Creek Road | US 51 North | 2.91 | 91.25 | 2.91 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 2.91 |  |  | 58200 |  |  |  |  | 5938300 |  | Basic work, not full gravel work up
TR | 4 | Marsh Road | CTY M South | CTY K West | 1.04 | 92.29 | 1.04 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 |  | 1.04 |  | 62400 |  |  |  |  | 6000700 |  | Create Bike bypass for through riders, better use of events
TR | 6 | Vandercook Road | CTY M South | XX | 0.08 | 92.37 | 0.08 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 | 0 |  |  | 0 | [6 empty] | trapped between Arbor Vitae roads, snowmobile trail 100%
TR | 1 | Good Life Lane | CTY M North | Airport Road | 0.44 | 92.81 |  |  | 0.44 |  |  | 1 | 1 | 1 | 3 | 1 |  |  | 0 | 0
TR | 6 | Jag Lake Road | CTY H | XX | 0.08 | 92.89 | 0.08 |  |  |  |  | 1 | 0.5 | 2 | 3.5 | 1 |  | 0 |  | 0 | [6 empty] | boat landing
TR | 1 | Round Lake Road | CTY K West | Bear Lake Road | 0.1 | 92.99 |  | 0.1 |  |  |  | 1 | 0.5 | 2 | 3.5 | 1 |  | 0 |  | 0
TR | 1 | Cemetary Road | CTY K West | XX | 0.18 | 93.17 |  | 0.18 |  |  |  | 1 | 0.5 | 1 | 2.5 | 0.5 |  | 0 |  | 0
TR | 0 | Old 51 East Hoffman Road |  | 0.26 | 0 | 93.17 | [8 empty] | 0
TR | 0 | Old 51 Old H |  | 1.17 | 0 | 93.17 | [8 empty] | 0
TR | 1 | Round Lake Road (Presque Isle) | CTY K West | Bear Lake Road | 1.25 | 94.42 |  | 1.25 | [6 empty] | 0 |  |  | 0 |  | 0
TR |  | Town Road 127 |  |  | 0.1 | 94.52 | [8 empty] | 0
TR |  | Town Road 133 |  |  | 0.15 | 94.67 | [8 empty] | 0
|  | 20% | [23 empty] | 617900
[5 empty] | 93.17 |  | 26.04 | 55.17 | 8.57 | [7 empty] | 13.74 | 34.56 | 15.86 | 6000700 |  |  |  |  | TOTAL ESTIMATED COST
[8 empty] | Town Road Mileage | 89.78 | [7 empty] | Improvement Mileage |  | 64.16
[17 empty] | Percent of Total Mileage |  | 71.46%
[17 empty] | % of | Accum. |  | Cost by 20%
[6 empty] | COLOR KEY | [10 empty] | Dollars | Miles | % | Increments
[6 empty] | 1 | Recently Updated, Or in Good Condition - No work planned | [9 empty] | 41.62% | 19.05 | 20 | 2497650
[6 empty] | 2 | Paved Road, repaving planned, same surface | [9 empty] | 19.34% | 36.81 | 20 | 1160800
[6 empty] | 3 | Paved Road, repaving planned, new surface | [9 empty] | 17.34% | 55.58 | 20 | 1040400
[6 empty] | 4 | Existing Gravel Road, planned upgrade to pavement | [9 empty] | 11.4% | 74.35 | 20 | 683950
[6 empty] | 5 | Existing Gravel Road, general grading and gravel | [9 empty] | 10.3% | 92.29 | 20 | 617900
[6 empty] | 6 | Existing Gravel Road/Fire Road - No Plans | [11 empty] | 100 | 6000700
PAVING COST PER MILE
|  |  |  | Existing Surface | Gravel | Chip Seal | Asphalt
|  | Gravel |  | GRAVEL | 40000 | 60000 | 155000
|  | Chip Seal |  | CHIP SEAL | 40000 | 95000 | 155000
|  | Asphalt |  | ASPHALT | 40000 | 95000 | 155000

## Roads-CatAlphaSort
TOWN OF BOULDER JUNCTION
TOWN ROAD REDEVELOPMENT PLAN
| PLAN |  |  |  | Length |  | SURFACE TYPE |  |  |  |  | RESURFACE PLAN |  |  | Estimated
TYPE | CAT | ROAD NAME | Primary Access Road | Secondary Access Road | ER | TR | Gravel | Chip | Asphalt | Seal Coated or Resurfaced |  | Gravel | Chip | Asphalt | RESURFACE COST | COMMENTS
TR | 1 | Ada Street | CTY M | Main Street |  | 0.25 |  | 0.25 |  |  | <10 |  | 0 |  | 0
TR | 4 | Airport Road - gravel | CTY M North | Dairymen's Road |  | 2.45 | 1 |  |  | 1969, 1984 |  | 0 | 1 | 0 | 60000 | Pave 1 mi of gravel, denote "bike share", (Airport Loop)
| 4 | Airport Road - paved | [6 empty] | 1.45 |  |  |  |  | 1.45
TR | 3 | Allen Road | CTY M North | High Lake Road |  | 0.68 |  | 0.68 |  | 1975, 1990 |  |  | 0 | 0.68 | 158100 | upgrade to asphalt, widen 8' for Bike lanes (White Deer Loop)
TR | 2 | Allequash Lake Road | CTY M South | XX |  | 0.94 |  | 0.94 |  |  |  |  | 0.94 |  | 89300
TR | 2 | Annes Place | Old K | Green Street |  | 0.14 |  | 0.14 |  |  |  |  | 0.14 |  | 13300
TR | 2 | Arrowhead Drive | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road |  | 0.55 | 0.15 | 0.45 |  | 82, 88 |  |  | 0.6 |  | 51750
TR | 2 | Bakken Road (East) | CTY H | HWY 51 N |  | 1.07 |  | 1.07 |  | 67,68 |  |  | 1.07 |  | 101650 | Asphalt upgrade??
TR | 1 | Bakken Road (West) | CTY H | HWY 51 N |  | 2.15 |  | 2.15 |  |  |  |  | 0 |  | 0
TR | 4 | Balsam Lane | US 51 North | Bakken Road (west) |  | 0.35 | 0.35 | [5 empty] | 0.35 |  | 21000 | no turn around
TR | 5 | Bass Lake Road | CTY K West | Bear Lake Road |  | 0.41 | 0.41 |  |  |  |  | 0.41 |  |  | 16400
TR | 1 | Bear Lake Road | CTY K West | XX |  | 3.26 |  |  | 3.26 | 1971, 1974, 1986 | 2015 |  |  | 0 | 0
TR | 1 | Ben Bendrick Drive (Lake Shore Drive) | CTY M South | XX |  | 1.7 |  |  | 1.7 |  |  |  |  | 0 | 0
TR | 4 | Big Muskellunge Road | CTY M South | XX |  | 2.7 | 1.2 | 1 | 0.5 | 1976 |  |  | 2.2 |  | 167000
TR | 6 | Birch Drive | CTY M North, High-FT Lake Rd | High Lake Road |  | 0.25 | 0.25 |  |  |  |  | 0 |  |  | 0
TR | 5 | Birch Point Lane | CTY K West | Bear Lake Road |  | 0.19 | 0.19 |  |  |  |  | 0.19 |  |  | 7600
TR | 1 | Birchwood Lane | CTY M North | Airport Road |  | 0.36 |  | 0.36 |  | 1984 |  |  | 0 |  | 0
TR | 1 | Blaisdell Street | Main Street, CTY K West | Ada, Blueberry |  | 0.17 |  | 0.17 |  |  |  |  | 0 |  | 0
TR | 4 | Blue Heron Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead |  | 0.12 | 0.12 | [5 empty] | 0.12 |  | 7200
TR | 1 | Blueberry Lane | Main Street, CTY K West | Center Street |  | 0.25 |  | 0.25 |  |  |  |  | 0 |  | 0
TR | 5 | Boat Landing Road (Island lake) | US 51 North | Island Lake Road |  | 0.5 | 0.5 |  |  |  |  | 0.5 |  |  | 20000
TR | 2 | Boulder Lane | CTY M North | XX |  | 0.4 |  | 0.4 |  |  |  |  | 0.4 |  | 38000
TR | 4 | Camp Manitowish Lane (East) | CTY K West | XX |  | 0.5 | 0.5 | [5 empty] | 0.5 |  | 30000 | pave it since CMW will be carrying big tax bill
TR | 1 | Camp Manitowish Lane (West) | CTY K West | XX |  | 0.5 |  | 0.5 |  |  |  |  | 0 |  | 0
TR | 2 | Campo Fiesta Lane | CTY M South | North Creek Road |  | 0.13 |  | 0.13 |  |  |  |  | 0.13 |  | 12350
TR | 2 | Cattail Cove Lane | CTY K West | XX |  | 0.75 |  | 0.75 |  | 1992 |  |  | 0.75 |  | 71250
TR | 1 | Cemetary Road | CTY K West | XX |  | 0.18 |  | 0.18 |  |  |  |  | 0 |  | 0
TR | 1 | Center Street | CTY M South, Park Street | Marsh Rd, Ada, Blueberry |  | 0.31 |  | 0.31 |  |  |  |  | 0 |  | 0
TR | 2 | Charlotte Place Lane | US 51 North | XX |  | 0.25 |  | 0.25 |  |  |  |  | 0.25 |  | 23750
TR | 2 | Church Street | Old K | Green Street |  | 0.14 |  | 0.14 |  |  |  |  | 0.14 |  | 13300
TR | 6 | Clear View Drive | CTY K West | Fallon Road |  | 0.34 | 0.34 |  |  |  |  | 0 |  |  | 0 | good condition, consider paving all or part
TR | 1 | Community Street | CTY K West | Blaisdell Street |  | 0.2 |  | 0.2 |  |  |  |  | 0 |  | 0
TR | 2 | Concora Road | Old K | XX |  | 0.8 |  | 0.8 |  |  |  |  | 0.8 |  | 76000
TR | 3 | Dairymens Road | CTY M North | XX |  | 1.55 |  | 1.55 |  | 1973, 1988 |  |  |  | 1.55 | 360375 | Asphalt to benefit Dairymens and Bike loop, widen 8'
TR | 5 | Dam Road | CTY M North | High-Fishtrap Lake Road |  | 0.8 | 0.8 |  |  |  |  | 0.8 |  |  | 32000
TR | 1 | Day Lake Landing Road | Day Lake Road | XXX |  | 0.22 | 0.22 |  |  |  |  | 0 |  |  | 0
TR | 5 | Day Lake Road | North Creek Road | US 51 North |  | 2.91 | 2.91 |  |  |  |  | 2.91 |  |  | 58200 | Basic work, not full gravel work up
TR | 2 | Dolittle Road | CTY M North | Boulder Lane |  | 0.15 |  | 0.15 |  |  |  |  | 0.15 |  | 14250 | make widening part of agreement with owners, doable
TR | 2 | East Fitzgerald Lane | US 51 N, Island lake Rd | Fitzgerald Lane |  | 0.11 |  | 0.11 |  |  |  |  | 0.11 |  | 10450
TR | 4 | En-Dah Win Lane | CTY K East | XX |  | 0.15 | 0.15 | [5 empty] | 0.1 |  | 6000 | only pave to T
TR | 2 | Evergreen Lane | CTY K West | XX |  | 1.98 |  | 1.98 |  | 1974 |  |  | 1.98 |  | 188100 | check condition
TR | 3 | Fallon Road | CTY K West | XX |  | 2.08 |  | 2.08 |  | 1984, 1986 |  |  |  | 2.08 | 322400
TR | 3 | Fishtrap Lake Road | CTY M North, High-FT Lake Rd | XX |  | 2.04 |  | 2.04 |  | 72,73,75,82,86 |  |  | 0.64 | 1.4 | 255400 | Do we want all or % as Asphalt??? Shown with asphalt to trail corner
TR | 2 | Fitzgerald Lane | US 51 North | Island Lake Road |  | 0.2 |  | 0.2 |  |  |  |  | 0.2 |  | 19000
TR | 2 | Glen Lake Road | CTY K West | Shamrock Road |  | 0.25 |  | 0.25 |  | 1988 |  |  | 0.25 |  | 23750
TR | 1 | Good Life Lane | CTY M North | Airport Road |  | 0.44 |  |  | 0.44 |  |  |  |  | 0 | 0
TR | 3 | Grahl Lane | CTY H | XX |  | 0.43 | 0.43 | [5 empty] | 0.43 |  | 25800
TR | 2 | Green Street | CTY M | Old K |  | 0.27 |  | 0.27 |  |  |  |  | 0.27 |  | 25650
TR | 5 | Halverson Lane | CTY M South | XX |  | 0.12 | 0.12 |  |  |  |  | 0.12 |  |  | 4800
TR | 2 | Harmony Point Lane | US 51 North | between M and H |  | 0.6 |  | 0.6 |  | 1974, 1982 |  |  | 0.6 |  | 57000 | narrow road
TR | 2 | High Lake Road | CTY M North, High-FT Lake Rd | Allen Road |  | 3.8 |  |  | 3.8 | 1972, 1983 |  |  | 1.1 | 0.7 | 267250 | Between Allen and Ridge is okay, Chip ridge to end, asphalt loop leg
TR | 2 | High Pines Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln |  | 1.1 |  | 1.1 |  | 1978 |  |  | 1.1 |  | 104500 | needs improved turn around area
TR | 2 | High-Fishtrap Lake Road | CTY M North | XX |  | 1.1 |  |  | 1.1 |  |  |  |  | 1.1 | 255750 | asphalt for loop, add 8' to width
TR | 3 | Highland Drive | CTY K West | CTY M North |  | 0.28 |  | 0.28 |  | 1976, 1990 |  |  |  | 0.28 | 43400 | Upgrade for Bike Loop and Event Bypass support
TR | 2 | Island Lake Road | US 51 North | XX |  | 1.28 |  | 1.28 |  | 1987 |  |  | 1.28 |  | 121600
TR | 6 | Jag Lake Road | CTY H | XX |  | 0.08 | 0.08 |  |  |  |  | 0 |  |  | 0
TR | 1 | Kassien Lane | US 51 North | Island Lake Road |  | 0.54 |  | 0.54 |  |  |  |  | 0 |  | 0
TR | 2 | Keego Road | CTY K West | XX |  | 1.25 |  | 1.25 |  | 1984 |  |  | 1.25 |  | 118750
TR | 6 | Keego Road East | CTY K West, Bear lake Road | Keego Road |  | 1.31 | 1.31 |  |  |  |  | 0 |  |  | 0
TR | 2 | Kern Lane | CTY m South | North Creek Road |  | 1.1 |  | 1.1 |  |  |  |  | 1.1 |  | 104500
TR | 2 | La Fave Road | US 51 North | Island Lake Road |  | 1.24 |  | 1.24 |  | 1970 |  |  | 0.25 |  | 23750 | Northwest segment only
TR | 4 | Little Crooked Lane | CTY K West | Bear Lake Road |  | 0.38 | 0.38 | [5 empty] | 0.38 |  | 22800 | Upgrade to chip seal
TR | 2 | Little Rice Lane | CTY M North | XX |  | 0.28 |  | 0.28 |  |  |  |  | 0.28 |  | 26600
TR | 2 | Lucas Lane | CTY K West | XX |  | 0.15 |  | 0.15 |  | 1971 |  |  | 0.15 |  | 14250 | paved to start of campground
TR | 2 | Major Road | CTY M North | Dairymen's Road |  | 0.5 |  | 0.5 |  | 1973 |  |  | 0.5 |  | 47500 | road to nowhere, pave only if benefit to Dairymen's
TR | 2 | Mann Lake Road | CTY M South | XX |  | 0.75 |  | 0.75 |  | 1973, 1990 |  |  | 0.65 |  | 61750 | first .1m ok, no turn around
TR | 5 | Maple Lake Road | CTY K West | XX |  | 0.35 | 0.35 |  |  |  |  | 0.35 |  |  | 14000
TR | 4 | Marsh Road | CTY M South | CTY K West |  | 1.04 | 1.04 | [5 empty] | 1.04 |  | 62400 | Create Bike bypass for through riders, better use of events
TR | 2 | Middle Gresham Lane | US 51 North (near H) | XX |  | 0.43 |  | 0.43 |  |  |  |  | 0.43 |  | 40850
TR | 5 | Nebish lake Road | CTY K West | XX |  | 1.97 | 1.97 |  |  |  |  | 1.97 |  |  | 78800
TR | 3 | Newcomb Lane | CTY K West | XX |  | 3.5 |  | 3.5 |  | 78,80,83,88,92 |  |  |  | 3.5 | 542500
TR | 1 | Nichols Lake Lane | CTY H | CTY K West |  | 0.63 |  | 0.63 |  |  |  |  | 0 |  | 0
TR | 5 | Nixon Lake Road | CTY K East | XX |  | 2.6 | 2.6 |  |  |  |  | 2.6 |  |  | 104000 | Seek cost share with DNR
TR | 3 | North Creek Road | CTY M South | CTY H |  | 4.57 |  | 4.57 |  | 75, 76, 87, 92 |  |  |  | 4.57 | 708350 | Possible width increase for Bike Route, Cost share with DNR
TR | 5 | North Oswego Lake Road | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road |  | 0.24 | 0.24 |  |  | 1991 |  | 0.24 |  |  | 9600
TR | 1 | North Town Line Rd (Town Road 116) | US 51 North | Le Fave Rd, Island Lake Rd |  | 1 |  | 1 |  | 1991 |  |  | 0 |  | 0
TR | 0 | Old 51 East Hoffman Road |  | 0.26
TR | 0 | Old 51 Old H |  | 1.17
TR | 5 | Old 51 Road (Bakken Rd - Island Lake Rd) | CTY H, Bakken Rd (east) | US 51 N, Island Lake Rd |  | 1.8 | 1.8 |  |  | 1980 |  | 1.8 |  |  | 72000 | snowmobile %
TR | 1 | Old 51 Road (Town Line - Island Lake Rd) | US 51 North | Town Line Rd, Island lake Rd |  | 1.07 |  | 1.07 |  |  |  |  | 0 |  | 0
TR | 6 | Old Flambeau Road | CTY H?? | Bakken Rd ?? |  | 0.74 | 0.74 |  |  |  |  | 0 |  |  | 0 | No signs, looks like snowmobile trail, barely a road
TR | 2 | Old K Road | CTY M, Main Street | CTYK East |  | 2.79 |  | 2.79 |  | 1969, 1991 |  |  | 2.79 |  | 397575 | widen 8' for bike loop (Asphalt??)
TR | 1 | Oswego-Fishtrap Lake Road | CTY M North, High-FT Lake Rd | Fishtrap Road |  | 1.9 |  | 1.9 |  |  |  |  | 0 |  | 0
TR | 4 | Partridge Lane | CTY M North, High-FT Lake Rd | High Lake Road |  | 1.1 | 1.1 | [5 empty] | 1.1 |  | 66000
TR | 4 | Perch Lane | CTY M South (by N) |  |  | 0.23 | 0.23 | [5 empty] | 0.23 |  | 13800 | no turn around
TR | 2 | Pine Lane | US 51 North | Bakken Road (west) |  | 0.45 |  | 0.45 |  | 1984 |  |  | 0.45 |  | 42750 | no turn around
TR | 5 | Pine Shores Lane | US 51 North | Bakken Road (west) |  | 0.06 | 0.06 |  |  |  |  | 0.06 |  |  | 2400
TR | 4 | Pinewood Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln |  | 0.12 | 0.12 | [5 empty] | 0.12 |  | 7200
TR | 4 | Platinum Lane | CTY H | Grahl Lane |  | 0.23 | 0.23 | [5 empty] | 0.23 |  | 13800
TR | 6 | Point Lane | CTY K West | Fallon Rd, Rintleman Rd |  | 0.25 | 0.25 |  |  |  |  | 0 |  |  | 0 | Good condition, Consider Paving?
TR | 2 | Red Fox Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead |  | 0.09 |  | 0.09 |  |  |  |  | 0.09 |  | 8550
TR | 2 | Reible Court | Old K | XX |  | 0.12 |  | 0.12 |  |  |  |  | 0.12 |  | 11400
TR | 5 | Ridge Lane | CTY M North, High-FT Lake Rd | High Lake Rd |  | 1.2 | 0.3 | 0.9 |  | 1983 |  | 0.3 | 0.9 |  | 12000
TR | 2 | Rintlemen | CTY K West | Fallon Road |  | 0.6 |  | 0.6 |  |  |  |  | 0.6 |  | 57000
TR | 6 | River lane | CTY K West | XX |  | 0.2 | 0.2 |  |  |  |  | 0 |  |  | 0
TR | 1 | Rocky Reef Lane | CTY M South | CTY N West |  | 0.54 |  | 0.54 |  | 1982, 1992 |  |  | 0 |  | 0 | poor turn around area
TR | 1 | Round Lake Road | CTY K West | Bear Lake Road |  | 0.1 |  | 0.1 |  |  |  |  | 0 |  | 0
TR | 1 | Round Lake Road (Presque Isle) | CTY K West | Bear Lake Road |  | 1.25 |  | 1.25 |  |  |  |  | 0 |  | 0
TR | 2 | Rudolph Lake Lane | CTY H | XX |  | 0.6 |  | 0.6 |  |  |  |  | 0.6 |  | 57000
TR | 6 | Rudolph Lake Lane (South) | CTY H | Rudolph Lake Lane |  | 0.26 | 0.26 |  |  | 1987 |  | 0 |  |  | 0
TR | 1 | Rustic Colony Lane | CTY M North | Airport Road |  | 0.27 |  | 0.27 |  |  |  |  | 0 |  | 0
TR | 1 | Senior Drive | CTY M, Park Street | Green Street |  | 0.2 |  | 0.2 |  |  |  |  | 0 |  | 0
TR | 2 | Shamrock Lane | CTY K West | Highland Drive |  | 0.4 |  | 0.4 |  |  |  |  | 0.4 |  | 38000
TR | 2 | Sherry Drive | CTY M North, High-FT Lake Rd | High Lake Road |  | 0.05 |  | 0.05 |  |  |  |  | 0.05 |  | 4750
TR | 2 | Shore Drive | CTY K West | Newcomb Lane |  | 1.03 |  | 1.03 |  | 1991 |  |  | 1.03 |  | 97850
TR |  | South Rudolph Lake Lane | CTY H | Rudolph Lake Lane
TR | 4 | South Shore Bay Lane | US 51 North | Island Lake Road |  | 0.15 | 0.15 | [5 empty] | 0.15 |  | 9000
TR | 1 | South Town Line | US 51 North | XX |  | 1.36 |  | 1.36 |  | 1976, 1988 |  |  | 0 |  | 0
TR | 2 | Spruce Drive | CTY M North, High-FT Lake Rd | High Lake Road |  | 0.22 |  | 0.22 |  |  |  |  | 0.22 |  | 20900 | create turn-arounds at each end
TR | 2 | Stiloski Lane | CTY M North, High-FT Lake Rd | Fishtrap Road |  | 0.37 |  | 0.37 |  | 1975 |  |  | 0.37 |  | 35150
TR | 6 | Street Lake Lane | CTY H | XX |  | 0.65 | 0.65 |  |  |  |  | 0 |  |  | 0 | do we want to pave??
TR | 4 | Sunset Lane | CTY M South, North Creek Rd | Kern lane, Trout lane |  | 0.3 | 0.3 | [5 empty] | 0.3 |  | 18000 | gravel, is this a town road? Pave it??
TR | 1 | Town Hall Road | Around Community Building |  |  | 0.12 |  |  | 0.12 | 1987 |  |  |  | 0 | 0
TR |  | Town Road 119 | CTY K West, Fallon Rd | Clear View Drive |  | 0.14
TR |  | Town Road 127 |  |  |  | 0.1
TR |  | Town Road 133 |  |  |  | 0.15 | X
TR | 2 | Trout Lane | CTY M South, North Creek Rd | Kern lane |  | 0.2 |  | 0.2 |  |  |  |  | 0.2 |  | 19000
TR | 6 | Vandercook Road | CTY M South | XX |  | 0.08 | 0.08 |  |  |  |  | 0 |  |  | 0 | trapped between Arbor Vitae roads, snowmobile trail 100%
TR | 5 | West Big Lake Road | CTY K West | XX |  | 1.04 | 1.04 |  |  |  |  | 1.04 |  |  | 41600
TR | 5 | White Birch Lane | CTY M North, High-FT Lake Rd | Osewgo-FT Lake Road |  | 0.45 | 0.45 |  |  |  |  | 0.45 |  |  | 18000
TR | 4 | White Deer Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead |  | 0.12 | 0.12 | [5 empty] | 0.12 |  | 7200
TR | 2 | Whitney Lake Road | CTY K West | XX |  | 1 | 0.1 | 0.9 |  |  |  |  | 1 |  | 91500
TR | 2 | Wool Lake Lane | CTY K West | XX |  | 0.76 |  | 0.76 |  | 1967, 1972, 1983 |  |  | 0.76 |  | 72200
ER | 0 | Abe Le Fave Trail | US 51 N, Island lake Rd | Le Fave Rd | 0.15
ER | 0 | Arbutus Court | CTY M North | XX
ER | 0 | Arneders Lane | CTY M North | High Lake Road | 0.15
ER | 0 | Back Country lane | US 51 N, Airport Rd | Rustic Colony Lane
ER | 0 | Bays End | CTY K West, Highland Drive | Shamrock, Island Point | 0.1
ER | 0 | Bayshore Trail
ER | 0 | Beach View Trail | Old K | Concora Road | 0.05
ER | 0 | Bearwalk Lane | CTY M North | Airport Road
ER | 0 | Belden lane | CTY M North | Boulder Lane | 0.2
ER | 0 | Best Fishes Lane | CTY M South | North Creek Road | 0.43
ER | 0 | Bog Trail | US 51 North | XX
ER | 0 | Boulder Ridge trail | CTY M North | XX | 0.2
ER | 0 | Brenner Trail | CTY K West | XX | 0.34
ER | 0 | Brouwer Trail | CTY M North, Airport Rd | Rustic Colony Lane | 0.15
ER | 0 | Camp Osoha Lane | CTY M South | Big Muskellunge Rd | 0.16
ER | 0 | Campo Fiesta Lane (Extension) | CTY M South | North Creek Road |  |  | X
ER | 0 | Canon Hill Circle | CTY N West | XX
ER | 0 | Carmies Trail | CTY M South | North Creek Road | 0.3
ER | 0 | Cliffs Trail | CTY M North | Fishtrap Road | 0.2
ER | 0 | Coach Lane | US 51 North | Island Lake Road | 0.1
ER | 0 | Concora Road (extension) |  |  | 0.28
ER |  | Copp Lane
ER | 0 | Coreen lane | CTY M North
ER | 0 | Crooked Trail | CTY K West | Evergreen Lane | 0.5
ER | 0 | Darren Road | CTY H | XX
ER | 0 | Dr Kate Trail | CTY K West | Newcomb Lane | 0.2
ER | 0 | Drake Lane (Dairyman's) | CTY M North | Dairymen's Road
ER | 0 | Drewsen Lane | CTY K West, Wool Lake Ln | Ray Berch Lane | 0.2
ER | 0 | Eagle Resort Trail | US 51 North | Middle Gresham Lane
ER | 0 | Eagles Post Trail | CTY M North, High-FT Lake Rd | Fishtrap Road
ER | 0 | Elizabeth Lake Lane | CTY M North | XX
ER | 0 | Evergreen Lodge Lane | CTY K West | Evergreen Lane | 0.05
ER |  | Field Lane
ER | 0 | Filbey Trail | CTY K West | Evergreen Lane
ER | 0 | Fishtrap Resort Lane | CTY M North, High-FT Lake Rd | Fishtrap Road
ER | 0 | Fox Trail | CTY K West | Newcomb Lane | [11 empty] | is this a TOWN ROAD
ER | 0 | Goodwille Trail | US 51 N, Island lake Rd | Le Fave Road
ER | 0 | Grassy Lake Lane | CTY M North | XX | 0.1
ER | 0 | Grassy Lake Lane | CTY M North | XX | 0.3
ER |  | Gresham Creek Trail
ER | 0 | Harrington Lane | CTY K West | Whitney Lake Road | 0.25
ER | 0 | Headwaters Trail | Cty M North | XX | 0.14
ER | 0 | Hidden Bay Lane | CTY K West, Highland Drive | Shamrock Lane | 0.09
ER | 0 | Hideaway Bay Trail |  |  | 0.16
ER | 0 | High Pines Lane (extension) | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln | 0.33
ER | 0 | Hoag Circle | CTY K West, Highland Drive | Shamrock Lane | 0.1
ER | 0 | Home Lake Lane (Dairyman's) | CTY M North | Dairymen's Road
ER | 0 | Island Point Lane | CTY K West, Highland Drive | Shamrock Lane
ER | 0 | John Lane
ER | 0 | Junction Lane
ER | 0 | June Bug Circle | CTY M North | High Lake Road | 0.1
ER | 0 | Keego Lake Road (Keego extension) | CTY K West | Keego Road | 0.1
ER | 0 | Labrador trail | CTY M South | North Creek Road | 0.3
ER | 0 | Little John Lake Trail | CTY M South | CTY N East | 0.05
ER | 0 | Lone Tree Trail | CTY M North | High Lake Road | 0.1
ER | 0 | Lost Canoe Trail | CTY K East | XX
ER | 0 | Milo Trail | CTY K East | XX | 0.1
ER | 0 | Modrusani Trail | CTY M South | North Creek Road | 0.3
ER | 0 | Muskie Mack Trail | CTY N East | XX | 0.11
ER |  | Musky Lodge Lane
ER | 0 | Natures Way Road | CTY H, baaken Rd, Island lake Rd | Old 51 (Bakken-Island Lake) | 0.3
ER | 0 | Nelson Lake Lane | US 51 North | Bakken Road (west)
ER | 0 | North Shore Pines Lane | Cty H | XX | 0.44
ER | 0 | Owls Lane | CTY K West | Camp Manitowish ln - East | 0.2
ER | 0 | Pat Lin Lane | US 51 North | Bakken Road (west)
ER | 0 | Patterson Place |  |  | 0.2
ER | 0 | Patterson Place |  |  | 0.12
ER | 0 | Pine Shores Lane (extension) |  |  | 0.09
ER | 0 | Pinewood Lane (extension) | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln | 0.15 |  | X
ER | 0 | Piney Road (Dairyman's) | CTY M North | Dairymen's Road
ER | 0 | Porter Trail | CTY M North, High-FT Lake Rd | Fishtrap Road
ER | 0 | Princess Pine Lane | CTY M South | North Creek Road | 0.5
ER | 0 | R.E.S.Lane | CTY H | Rudolph Lake Lane | 0.75
ER |  | Raven Retreat Trail
ER | 0 | Ray Berch lane | CTY K West | Wool Lake Lane | 0.2
ER | 0 | Rice Bay Lane | CTY K West | Fallon Road | 0.38
ER | 0 | Ritzke Trail | CTY H | XX | 0.1
ER | 0 | River Run Lane | CTY K West | XX | 0.75
ER |  | Riverstone Drive
ER |  | Ryan Road
ER | 0 | Sandy Bank Lane | CTY K West, Newcomb Ln | Shore Drive | 0.1
ER | 0 | Sarah Jane Lane | US 51 N, Island lake Rd | Le Fave Rd, Abe Le Fave Tr | 0.15
ER | 0 | Schuenemann Trail | CTY H | XX | 0.48
ER | 0 | Sea Wolf Trail | CTY K West | Bear Lake Road | 0.6
ER | 0 | Shalimar Lane | CTY H, North Creek Road | Wilson Lane | 0.1
ER | 0 | Shamrock lane (extension) | CTY K West | Highland Drive | 0.22
ER | 0 | Shelter Bay Trail | CTY M North | Fishtrap Road | 0.1
ER | 0 | Shoemaker Trail | CTY H, Rudolph Lake Ln | R.E.S Lane | 0.6
ER | 0 | Six Point Lane | CTY M North | Airport Road
ER | 0 | Stiloski Lane (Extension) | CTY M North, High-FT Lake Rd | Fishtrap Road | 0.23 |  | X
ER | 0 | Stone Gate Lane | US 51 North | XX
ER | 0 | Stonehaven | CTY K West | Bear Lake Road
ER | 0 | Summer Bay Trail | CTY M North, High-FT Lake Rd | High Lake, Ridge Ln, High Pines | 0.75
ER | 0 | Swanson Trail
ER | 0 | Taylor Timber Trail | CTY M North, High-FT Lake Rd | High Lake, Ridge Ln, High Pines | 0.6
ER | 0 | The Narrows Trail | CTY M North, High-FT Lake Rd | Fishtrap Road, Stiloski Ln | 0.42
ER | 0 | Timber Oak Trail
ER | 0 | Totem Trail | CTY M South, North Creek Rd | Princess Pine Lane | 0.08
ER | 0 | Vanny Trail | US 51 North | Jolin Lane
ER | 0 | Wee Pines Trail | US 51 North | XX
ER | 0 | White Sand Trail | Old K | Concora Road | 0.05 |  |  | 0.05 |  |  |  |  | 0.05 |  | 4750
ER | 0 | Wildcat Road | CTY M North | XX | [11 empty] | assume Presque Ilse handles this road
ER | 0 | Wildwood Lane | CTY K West, CTY M North | Highland Drive | 0.4
ER | 0 | Williams Lane | US 51 North | XX
ER | 0 | Wilson Lane | CTY H | North Creek Road | 0.3
ER | 0 | Windy Shores Drive | CTY M South, North Creek Rd | Princess Pine Lane | 0.1
ER | 0 | Wittigs Point Lane | CTY M North, High-FT Lake Rd | Fishtrap Road
ER | 0 | Wolf Lake lane (Dairyman's) | CTY M North | Dairymen's Road
|  |  |  | TOTAL MILES | 15.85 | 93.62 | 25.79 | 55.12 | 12.37 |  |  | 13.74 | 35.46 | 17.31 | 6388650 | TOTAL ESTIMATED COST
[8 empty] | Town Road Mileage | 93.28 |  |  |  |  | 66.51
[9 empty] | 99.64% |  |  |  |  | 71.04% | Percent of Town Roads receiving roadwork
COLOR KEY
|  | 1 | Recently Updated, Or in Good Condition - No work planned |  | Recently Updated, Or in Good Condition - No work planned
|  | 2 | Paved Road, repaving planned, same surface |  | Paved Road, repaving planned, same surface
|  | 3 | Paved Road, repaving planned, new surface |  | Paved Road, repaving planned, new surface
|  | 4 | Existing Gravel Road, planned upgrade to pavement |  | Existing Gravel Road, planned upgrade to pavement
|  | 5 | Existing Gravel Road, general grading and gravel |  | Existing Gravel Road, general grading and gravel
|  | 6 | Existing Gravel Road/Fire Road - No Plans |  | Existing Gravel Road/Fire Road - No Plans
PAVING COST PER MILE
|  |  |  | Existing Surface | Gravel | Chip Seal | Asphalt
|  |  |  | GRAVEL | 40000 | 60000 | 155000
|  |  |  | CHIP SEAL | 40000 | 95000 | 155000
|  |  |  | ASPHALT | 40000 | 95000 | 155000
NOTES:
| 1 | what about cost of markings, lines, signs?
| 2 | what about easements costs for bike lanes, turn arounds, widening?
| 3 | what about engineering costs for widening, turn arounds, general improvements
| 4 | any bridge or culvert work to include?
| 5 | need to identify roads, mileage for potential cost share
6
7
8
9
Note on Q8: Greg Van Grinsven: I didn't think Dairymens wanted us to do this?

## Roads-CatConSort
TOWN OF BOULDER JUNCTION
TOWN ROAD REDEVELOPMENT PLAN
| PLAN |  |  |  | Length |  | SURFACE TYPE |  |  |  |  | RESURFACE PLAN |  |  | Estimated
TYPE | CAT | ROAD NAME | Primary Access Road | Secondary Access Road | ER | TR | Gravel | Chip | Asphalt | Seal Coated or Resurfaced |  | Gravel | Chip | Asphalt | RESURFACE COST | COMMENTS
TR | 0 | Old 51 East Hoffman Road |  | 0.26
TR | 0 | Old 51 Old H |  | 1.17
TR | 1 | Ada Street | CTY M | Main Street |  | 0.25 |  | 0.25 |  |  | <10 |  | 0 |  | 0
TR | 1 | Bakken Road (West) | CTY H | HWY 51 N |  | 2.15 |  | 2.15 |  |  |  |  | 0 |  | 0
TR | 1 | Bear Lake Road | CTY K West | XX |  | 3.26 |  |  | 3.26 | 1971, 1974, 1986 | 2015 |  |  | 0 | 0
TR | 1 | Ben Bendrick Drive (Lake Shore Drive) | CTY M South | XX |  | 1.7 |  |  | 1.7 |  |  |  |  | 0 | 0
TR | 1 | Birchwood Lane | CTY M North | Airport Road |  | 0.36 |  | 0.36 |  | 1984 |  |  | 0 |  | 0
TR | 1 | Blaisdell Street | Main Street, CTY K West | Ada, Blueberry |  | 0.17 |  | 0.17 |  |  |  |  | 0 |  | 0
TR | 1 | Blueberry Lane | Main Street, CTY K West | Center Street |  | 0.25 |  | 0.25 |  |  |  |  | 0 |  | 0
TR | 1 | Camp Manitowish Lane (West) | CTY K West | XX |  | 0.5 |  | 0.5 |  |  |  |  | 0 |  | 0
TR | 1 | Cemetary Road | CTY K West | XX |  | 0.18 |  | 0.18 |  |  |  |  | 0 |  | 0
TR | 1 | Center Street | CTY M South, Park Street | Marsh Rd, Ada, Blueberry |  | 0.31 |  | 0.31 |  |  |  |  | 0 |  | 0
TR | 1 | Community Street | CTY K West | Blaisdell Street |  | 0.2 |  | 0.2 |  |  |  |  | 0 |  | 0
TR | 1 | Day Lake Landing Road | Day Lake Road | XXX |  | 0.22 | 0.22 |  |  |  |  | 0 |  |  | 0
TR | 1 | Good Life Lane | CTY M North | Airport Road |  | 0.44 |  |  | 0.44 |  |  |  |  | 0 | 0
TR | 1 | Kassien Lane | US 51 North | Island Lake Road |  | 0.54 |  | 0.54 |  |  |  |  | 0 |  | 0
TR | 1 | Nichols Lake Lane | CTY H | CTY K West |  | 0.63 |  | 0.63 |  |  |  |  | 0 |  | 0
TR | 1 | North Town Line Rd (Town Road 116) | US 51 North | Le Fave Rd, Island Lake Rd |  | 1 |  | 1 |  | 1991 |  |  | 0 |  | 0
TR | 1 | Old 51 Road (Town Line - Island Lake Rd) | US 51 North | Town Line Rd, Island lake Rd |  | 1.07 |  | 1.07 |  |  |  |  | 0 |  | 0
TR | 1 | Oswego-Fishtrap Lake Road | CTY M North, High-FT Lake Rd | Fishtrap Road |  | 1.9 |  | 1.9 |  |  |  |  | 0 |  | 0
TR | 1 | Rocky Reef Lane | CTY M South | CTY N West |  | 0.54 |  | 0.54 |  | 1982, 1992 |  |  | 0 |  | 0 | poor turn around area
TR | 1 | Round Lake Road | CTY K West | Bear Lake Road |  | 0.1 |  | 0.1 |  |  |  |  | 0 |  | 0
TR | 1 | Round Lake Road (Presque Isle) | CTY K West | Bear Lake Road |  | 1.25 |  | 1.25 |  |  |  |  | 0 |  | 0
TR | 1 | Rustic Colony Lane | CTY M North | Airport Road |  | 0.27 |  | 0.27 |  |  |  |  | 0 |  | 0
TR | 1 | Senior Drive | CTY M, Park Street | Green Street |  | 0.2 |  | 0.2 |  |  |  |  | 0 |  | 0
TR | 1 | South Town Line | US 51 North | XX |  | 1.36 |  | 1.36 |  | 1976, 1988 |  |  | 0 |  | 0
TR | 1 | Town Hall Road | Around Community Building |  |  | 0.12 |  |  | 0.12 | 1987 |  |  |  | 0 | 0
TR | 2 | Allequash Lake Road | CTY M South | XX |  | 0.94 |  | 0.94 |  |  |  |  | 0.94 |  | 89300
TR | 2 | Annes Place | Old K | Green Street |  | 0.14 |  | 0.14 |  |  |  |  | 0.14 |  | 13300
TR | 2 | Arrowhead Drive | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road |  | 0.55 | 0.15 | 0.45 |  | 82, 88 |  |  | 0.6 |  | 51750
TR | 2 | Bakken Road (East) | CTY H | HWY 51 N |  | 1.07 |  | 1.07 |  | 67,68 |  |  | 1.07 |  | 101650 | Asphalt upgrade??
TR | 2 | Boulder Lane | CTY M North | XX |  | 0.4 |  | 0.4 |  |  |  |  | 0.4 |  | 38000
TR | 2 | Campo Fiesta Lane | CTY M South | North Creek Road |  | 0.13 |  | 0.13 |  |  |  |  | 0.13 |  | 12350
TR | 2 | Cattail Cove Lane | CTY K West | XX |  | 0.75 |  | 0.75 |  | 1992 |  |  | 0.75 |  | 71250
TR | 2 | Charlotte Place Lane | US 51 North | XX |  | 0.25 |  | 0.25 |  |  |  |  | 0.25 |  | 23750
TR | 2 | Church Street | Old K | Green Street |  | 0.14 |  | 0.14 |  |  |  |  | 0.14 |  | 13300
TR | 2 | Concora Road | Old K | XX |  | 0.8 |  | 0.8 |  |  |  |  | 0.8 |  | 76000
TR | 2 | Dolittle Road | CTY M North | Boulder Lane |  | 0.15 |  | 0.15 |  |  |  |  | 0.15 |  | 14250 | make widening part of agreement with owners, doable
TR | 2 | East Fitzgerald Lane | US 51 N, Island lake Rd | Fitzgerald Lane |  | 0.11 |  | 0.11 |  |  |  |  | 0.11 |  | 10450
TR | 2 | Evergreen Lane | CTY K West | XX |  | 1.98 |  | 1.98 |  | 1974 |  |  | 1.98 |  | 188100 | check condition
TR | 2 | Fitzgerald Lane | US 51 North | Island Lake Road |  | 0.2 |  | 0.2 |  |  |  |  | 0.2 |  | 19000
TR | 2 | Glen Lake Road | CTY K West | Shamrock Road |  | 0.25 |  | 0.25 |  | 1988 |  |  | 0.25 |  | 23750
TR | 2 | Green Street | CTY M | Old K |  | 0.27 |  | 0.27 |  |  |  |  | 0.27 |  | 25650
TR | 2 | Harmony Point Lane | US 51 North | between M and H |  | 0.6 |  | 0.6 |  | 1974, 1982 |  |  | 0.6 |  | 57000 | narrow road
TR | 2 | High Lake Road | CTY M North, High-FT Lake Rd | Allen Road |  | 3.8 |  |  | 3.8 | 1972, 1983 |  |  | 1.1 | 0.7 | 267250 | Between Allen and Ridge is okay, Chip ridge to end, asphalt loop leg
TR | 2 | High Pines Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln |  | 1.1 |  | 1.1 |  | 1978 |  |  | 1.1 |  | 104500 | needs improved turn around area
TR | 2 | High-Fishtrap Lake Road | CTY M North | XX |  | 1.1 |  |  | 1.1 |  |  |  |  | 1.1 | 255750 | asphalt for loop, add 8' to width
TR | 2 | Island Lake Road | US 51 North | XX |  | 1.28 |  | 1.28 |  | 1987 |  |  | 1.28 |  | 121600
TR | 2 | Keego Road | CTY K West | XX |  | 1.25 |  | 1.25 |  | 1984 |  |  | 1.25 |  | 118750
TR | 2 | Kern Lane | CTY m South | North Creek Road |  | 1.1 |  | 1.1 |  |  |  |  | 1.1 |  | 104500
TR | 2 | La Fave Road | US 51 North | Island Lake Road |  | 1.24 |  | 1.24 |  | 1970 |  |  | 0.25 |  | 23750 | Northwest segment only
TR | 2 | Little Rice Lane | CTY M North | XX |  | 0.28 |  | 0.28 |  |  |  |  | 0.28 |  | 26600
TR | 2 | Lucas Lane | CTY K West | XX |  | 0.15 |  | 0.15 |  | 1971 |  |  | 0.15 |  | 14250 | paved to start of campground
TR | 2 | Major Road | CTY M North | Dairymen's Road |  | 0.5 |  | 0.5 |  | 1973 |  |  | 0.5 |  | 47500 | road to nowhere, pave only if benefit to Dairymen's
TR | 2 | Mann Lake Road | CTY M South | XX |  | 0.75 |  | 0.75 |  | 1973, 1990 |  |  | 0.65 |  | 61750 | first .1m ok, no turn around
TR | 2 | Middle Gresham Lane | US 51 North (near H) | XX |  | 0.43 |  | 0.43 |  |  |  |  | 0.43 |  | 40850
TR | 2 | Old K Road | CTY M, Main Street | CTYK East |  | 2.79 |  | 2.79 |  | 1969, 1991 |  |  | 2.79 |  | 397575 | widen 8' for bike loop (Asphalt??)
TR | 2 | Pine Lane | US 51 North | Bakken Road (west) |  | 0.45 |  | 0.45 |  | 1984 |  |  | 0.45 |  | 42750 | no turn around
TR | 2 | Red Fox Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead |  | 0.09 |  | 0.09 |  |  |  |  | 0.09 |  | 8550
TR | 2 | Reible Court | Old K | XX |  | 0.12 |  | 0.12 |  |  |  |  | 0.12 |  | 11400
TR | 2 | Rintlemen | CTY K West | Fallon Road |  | 0.6 |  | 0.6 |  |  |  |  | 0.6 |  | 57000
TR | 2 | Rudolph Lake Lane | CTY H | XX |  | 0.6 |  | 0.6 |  |  |  |  | 0.6 |  | 57000
TR | 2 | Shamrock Lane | CTY K West | Highland Drive |  | 0.4 |  | 0.4 |  |  |  |  | 0.4 |  | 38000
TR | 2 | Sherry Drive | CTY M North, High-FT Lake Rd | High Lake Road |  | 0.05 |  | 0.05 |  |  |  |  | 0.05 |  | 4750
TR | 2 | Shore Drive | CTY K West | Newcomb Lane |  | 1.03 |  | 1.03 |  | 1991 |  |  | 1.03 |  | 97850
TR | 2 | Spruce Drive | CTY M North, High-FT Lake Rd | High Lake Road |  | 0.22 |  | 0.22 |  |  |  |  | 0.22 |  | 20900 | create turn-arounds at each end
TR | 2 | Stiloski Lane | CTY M North, High-FT Lake Rd | Fishtrap Road |  | 0.37 |  | 0.37 |  | 1975 |  |  | 0.37 |  | 35150
TR | 2 | Trout Lane | CTY M South, North Creek Rd | Kern lane |  | 0.2 |  | 0.2 |  |  |  |  | 0.2 |  | 19000
TR | 2 | Whitney Lake Road | CTY K West | XX |  | 1 | 0.1 | 0.9 |  |  |  |  | 1 |  | 91500
TR | 2 | Wool Lake Lane | CTY K West | XX |  | 0.76 |  | 0.76 |  | 1967, 1972, 1983 |  |  | 0.76 |  | 72200
TR | 3 | Allen Road | CTY M North | High Lake Road |  | 0.68 |  | 0.68 |  | 1975, 1990 |  |  | 0 | 0.68 | 158100 | upgrade to asphalt, widen 8' for Bike lanes (White Deer Loop)
TR | 3 | Dairymens Road | CTY M North | XX |  | 1.55 |  | 1.55 |  | 1973, 1988 |  |  |  | 1.55 | 360375 | Asphalt to benefit Dairymens and Bike loop, widen 8'
TR | 3 | Fallon Road | CTY K West | XX |  | 2.08 |  | 2.08 |  | 1984, 1986 |  |  |  | 2.08 | 322400
TR | 3 | Fishtrap Lake Road | CTY M North, High-FT Lake Rd | XX |  | 2.04 |  | 2.04 |  | 72,73,75,82,86 |  |  | 0.64 | 1.4 | 255400 | Do we want all or % as Asphalt??? Shown with asphalt to trail corner
TR | 3 | Grahl Lane | CTY H | XX |  | 0.43 | 0.43 | [5 empty] | 0.43 |  | 25800
TR | 3 | Highland Drive | CTY K West | CTY M North |  | 0.28 |  | 0.28 |  | 1976, 1990 |  |  |  | 0.28 | 43400 | Upgrade for Bike Loop and Event Bypass support
TR | 3 | Newcomb Lane | CTY K West | XX |  | 3.5 |  | 3.5 |  | 78,80,83,88,92 |  |  |  | 3.5 | 542500
TR | 3 | North Creek Road | CTY M South | CTY H |  | 4.57 |  | 4.57 |  | 75, 76, 87, 92 |  |  |  | 4.57 | 708350 | Possible width increase for Bike Route, Cost share with DNR
TR | 4 | Airport Road | CTY M North | Dairymen's Road |  | 2.45 | 1 |  | 1.45 | 1969, 1984 |  | 0 | 1 | 0 | 60000 | Pave 1 mi of gravel, denote "bike share", (Airport Loop)
TR | 4 | Balsam Lane | US 51 North | Bakken Road (west) |  | 0.35 | 0.35 | [5 empty] | 0.35 |  | 21000 | no turn around
TR | 4 | Big Muskellunge Road | CTY M South | XX |  | 2.7 | 1.2 | 1 | 0.5 | 1976 |  |  | 2.2 |  | 167000
TR | 4 | Blue Heron Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead |  | 0.12 | 0.12 | [5 empty] | 0.12 |  | 7200
TR | 4 | Camp Manitowish Lane (East) | CTY K West | XX |  | 0.5 | 0.5 | [5 empty] | 0.5 |  | 30000 | pave it since CMW will be carrying big tax bill
TR | 4 | En-Dah Win Lane | CTY K East | XX |  | 0.15 | 0.15 | [5 empty] | 0.1 |  | 6000 | only pave to T
TR | 4 | Little Crooked Lane | CTY K West | Bear Lake Road |  | 0.38 | 0.38 | [5 empty] | 0.38 |  | 22800
TR | 4 | Marsh Road | CTY M South | CTY K West |  | 1.04 | 1.04 | [5 empty] | 1.04 |  | 62400 | Create Bike bypass for through riders, better use of events
TR | 4 | Partridge Lane | CTY M North, High-FT Lake Rd | High Lake Road |  | 1.1 | 1.1 | [5 empty] | 1.1 |  | 66000
TR | 4 | Perch Lane | CTY M South (by N) |  |  | 0.23 | 0.23 | [5 empty] | 0.23 |  | 13800 | no turn around
TR | 4 | Pinewood Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln |  | 0.12 | 0.12 | [5 empty] | 0.12 |  | 7200
TR | 4 | Platinum Lane | CTY H | Grahl Lane |  | 0.23 | 0.23 | [5 empty] | 0.23 |  | 13800
TR | 4 | South Shore Bay Lane | US 51 North | Island Lake Road |  | 0.15 | 0.15 | [5 empty] | 0.15 |  | 9000
TR | 4 | Sunset Lane | CTY M South, North Creek Rd | Kern lane, Trout lane |  | 0.3 | 0.3 | [5 empty] | 0.3 |  | 18000 | gravel, is this a town road? Pave it??
TR | 4 | White Deer Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead |  | 0.12 | 0.12 | [5 empty] | 0.12 |  | 7200
TR | 5 | Bass Lake Road | CTY K West | Bear Lake Road |  | 0.41 | 0.41 |  |  |  |  | 0.41 |  |  | 16400
TR | 5 | Birch Point Lane | CTY K West | Bear Lake Road |  | 0.19 | 0.19 |  |  |  |  | 0.19 |  |  | 7600
TR | 5 | Boat Landing Road (Island lake) | US 51 North | Island Lake Road |  | 0.5 | 0.5 |  |  |  |  | 0.5 |  |  | 20000
TR | 5 | Dam Road | CTY M North | High-Fishtrap Lake Road |  | 0.8 | 0.8 |  |  |  |  | 0.8 |  |  | 32000
TR | 5 | Day Lake Road | North Creek Road | US 51 North |  | 2.91 | 2.91 |  |  |  |  | 2.91 |  |  | 58200 | Basic work, not full gravel work up
TR | 5 | Halverson Lane | CTY M South | XX |  | 0.12 | 0.12 |  |  |  |  | 0.12 |  |  | 4800
TR | 5 | Maple Lake Road | CTY K West | XX |  | 0.35 | 0.35 |  |  |  |  | 0.35 |  |  | 14000
TR | 5 | Nebish lake Road | CTY K West | XX |  | 1.97 | 1.97 |  |  |  |  | 1.97 |  |  | 78800
TR | 5 | Nixon Lake Road | CTY K East | XX |  | 2.6 | 2.6 |  |  |  |  | 2.6 |  |  | 104000 | Seek cost share with DNR
TR | 5 | North Oswego Lake Road | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road |  | 0.24 | 0.24 |  |  | 1991 |  | 0.24 |  |  | 9600
TR | 5 | Old 51 Road (Bakken Rd - Island Lake Rd) | CTY H, Bakken Rd (east) | US 51 N, Island Lake Rd |  | 1.8 | 1.8 |  |  | 1980 |  | 1.8 |  |  | 72000 | snowmobile %
TR | 5 | Pine Shores Lane | US 51 North | Bakken Road (west) |  | 0.06 | 0.06 |  |  |  |  | 0.06 |  |  | 2400
TR | 5 | Ridge Lane | CTY M North, High-FT Lake Rd | High Lake Rd |  | 1.2 | 0.3 | 0.9 |  | 1983 |  | 0.3 | 0 |  | 12000
TR | 5 | West Big Lake Road | CTY K West | XX |  | 1.04 | 1.04 |  |  |  |  | 1.04 |  |  | 41600
TR | 5 | White Birch Lane | CTY M North, High-FT Lake Rd | Osewgo-FT Lake Road |  | 0.45 | 0.45 |  |  |  |  | 0.45 |  |  | 18000
TR | 6 | Birch Drive | CTY M North, High-FT Lake Rd | High Lake Road |  | 0.25 | 0.25 |  |  |  |  | 0 |  |  | 0
TR | 6 | Clear View Drive | CTY K West | Fallon Road |  | 0.34 | 0.34 |  |  |  |  | 0 |  |  | 0 | good condition, consider paving all or part
TR | 6 | Jag Lake Road | CTY H | XX |  | 0.08 | 0.08 |  |  |  |  | 0 |  |  | 0
TR | 6 | Keego Road East | CTY K West, Bear lake Road | Keego Road |  | 1.31 | 1.31 |  |  |  |  | 0 |  |  | 0
TR | 6 | Old Flambeau Road | CTY H?? | Bakken Rd ?? |  | 0.74 | 0.74 |  |  |  |  | 0 |  |  | 0 | No signs, looks like snowmobile trail, barely a road
TR | 6 | Point Lane | CTY K West | Fallon Rd, Rintleman Rd |  | 0.25 | 0.25 |  |  |  |  | 0 |  |  | 0 | Good condition, Consider Paving?
TR | 6 | River lane | CTY K West | XX |  | 0.2 | 0.2 |  |  |  |  | 0 |  |  | 0
TR | 6 | Rudolph Lake Lane (South) | CTY H | Rudolph Lake Lane |  | 0.26 | 0.26 |  |  | 1987 |  | 0 |  |  | 0
TR | 6 | Street Lake Lane | CTY H | XX |  | 0.65 | 0.65 |  |  |  |  | 0 |  |  | 0 | do we want to pave??
TR | 6 | Vandercook Road | CTY M South | XX |  | 0.08 | 0.08 |  |  |  |  | 0 |  |  | 0 | trapped between Arbor Vitae roads, snowmobile trail 100%
TR |  | South Rudolph Lake Lane | CTY H | Rudolph Lake Lane
TR |  | Town Road 119 | CTY K West, Fallon Rd | Clear View Drive |  | 0.14
TR |  | Town Road 127 |  |  |  | 0.1
TR |  | Town Road 133 |  |  |  | 0.15 | X
ER | 0 | Abe Le Fave Trail | US 51 N, Island lake Rd | Le Fave Rd | 0.15
ER | 0 | Arbutus Court | CTY M North | XX
ER | 0 | Arneders Lane | CTY M North | High Lake Road | 0.15
ER | 0 | Back Country lane | US 51 N, Airport Rd | Rustic Colony Lane
ER | 0 | Bays End | CTY K West, Highland Drive | Shamrock, Island Point | 0.1
ER | 0 | Bayshore Trail
ER | 0 | Beach View Trail | Old K | Concora Road | 0.05
ER | 0 | Bearwalk Lane | CTY M North | Airport Road
ER | 0 | Belden lane | CTY M North | Boulder Lane | 0.2
ER | 0 | Best Fishes Lane | CTY M South | North Creek Road | 0.43
ER | 0 | Bog Trail | US 51 North | XX
ER | 0 | Boulder Ridge trail | CTY M North | XX | 0.2
ER | 0 | Brenner Trail | CTY K West | XX | 0.34
ER | 0 | Brouwer Trail | CTY M North, Airport Rd | Rustic Colony Lane | 0.15
ER | 0 | Camp Osoha Lane | CTY M South | Big Muskellunge Rd | 0.16
ER | 0 | Campo Fiesta Lane (Extension) | CTY M South | North Creek Road |  |  | X
ER | 0 | Canon Hill Circle | CTY N West | XX
ER | 0 | Carmies Trail | CTY M South | North Creek Road | 0.3
ER | 0 | Cliffs Trail | CTY M North | Fishtrap Road | 0.2
ER | 0 | Coach Lane | US 51 North | Island Lake Road | 0.1
ER | 0 | Concora Road (extension) |  |  | 0.28
ER | 0 | Coreen lane | CTY M North
ER | 0 | Crooked Trail | CTY K West | Evergreen Lane | 0.5
ER | 0 | Darren Road | CTY H | XX
ER | 0 | Dr Kate Trail | CTY K West | Newcomb Lane | 0.2
ER | 0 | Drake Lane (Dairyman's) | CTY M North | Dairymen's Road
ER | 0 | Drewsen Lane | CTY K West, Wool Lake Ln | Ray Berch Lane | 0.2
ER | 0 | Eagle Resort Trail | US 51 North | Middle Gresham Lane
ER | 0 | Eagles Post Trail | CTY M North, High-FT Lake Rd | Fishtrap Road
ER | 0 | Elizabeth Lake Lane | CTY M North | XX
ER | 0 | Evergreen Lodge Lane | CTY K West | Evergreen Lane | 0.05
ER | 0 | Filbey Trail | CTY K West | Evergreen Lane
ER | 0 | Fishtrap Resort Lane | CTY M North, High-FT Lake Rd | Fishtrap Road
ER | 0 | Fox Trail | CTY K West | Newcomb Lane | [11 empty] | is this a TOWN ROAD
ER | 0 | Goodwille Trail | US 51 N, Island lake Rd | Le Fave Road
ER | 0 | Grassy Lake Lane | CTY M North | XX | 0.1
ER | 0 | Grassy Lake Lane | CTY M North | XX | 0.3
ER | 0 | Harrington Lane | CTY K West | Whitney Lake Road | 0.25
ER | 0 | Headwaters Trail | Cty M North | XX | 0.14
ER | 0 | Hidden Bay Lane | CTY K West, Highland Drive | Shamrock Lane | 0.09
ER | 0 | Hideaway Bay Trail |  |  | 0.16
ER | 0 | High Pines Lane (extension) | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln | 0.33
ER | 0 | Hoag Circle | CTY K West, Highland Drive | Shamrock Lane | 0.1
ER | 0 | Home Lake Lane (Dairyman's) | CTY M North | Dairymen's Road
ER | 0 | Island Point Lane | CTY K West, Highland Drive | Shamrock Lane
ER | 0 | John Lane
ER | 0 | Junction Lane
ER | 0 | June Bug Circle | CTY M North | High Lake Road | 0.1
ER | 0 | Keego Lake Road (Keego extension) | CTY K West | Keego Road | 0.1
ER | 0 | Labrador trail | CTY M South | North Creek Road | 0.3
ER | 0 | Little John Lake Trail | CTY M South | CTY N East | 0.05
ER | 0 | Lone Tree Trail | CTY M North | High Lake Road | 0.1
ER | 0 | Lost Canoe Trail | CTY K East | XX
ER | 0 | Milo Trail | CTY K East | XX | 0.1
ER | 0 | Modrusani Trail | CTY M South | North Creek Road | 0.3
ER | 0 | Muskie Mack Trail | CTY N East | XX | 0.11
ER | 0 | Natures Way Road | CTY H, baaken Rd, Island lake Rd | Old 51 (Bakken-Island Lake) | 0.3
ER | 0 | Nelson Lake Lane | US 51 North | Bakken Road (west)
ER | 0 | North Shore Pines Lane | Cty H | XX | 0.44
ER | 0 | Owls Lane | CTY K West | Camp Manitowish ln - East | 0.2
ER | 0 | Pat Lin Lane | US 51 North | Bakken Road (west)
ER | 0 | Patterson Place |  |  | 0.2
ER | 0 | Patterson Place |  |  | 0.12
ER | 0 | Pine Shores Lane (extension) |  |  | 0.09
ER | 0 | Pinewood Lane (extension) | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln | 0.15 |  | X
ER | 0 | Piney Road (Dairyman's) | CTY M North | Dairymen's Road
ER | 0 | Porter Trail | CTY M North, High-FT Lake Rd | Fishtrap Road
ER | 0 | Princess Pine Lane | CTY M South | North Creek Road | 0.5
ER | 0 | R.E.S.Lane | CTY H | Rudolph Lake Lane | 0.75
ER | 0 | Ray Berch lane | CTY K West | Wool Lake Lane | 0.2
ER | 0 | Rice Bay Lane | CTY K West | Fallon Road | 0.38
ER | 0 | Ritzke Trail | CTY H | XX | 0.1
ER | 0 | River Run Lane | CTY K West | XX | 0.75
ER | 0 | Sandy Bank Lane | CTY K West, Newcomb Ln | Shore Drive | 0.1
ER | 0 | Sarah Jane Lane | US 51 N, Island lake Rd | Le Fave Rd, Abe Le Fave Tr | 0.15
ER | 0 | Schuenemann Trail | CTY H | XX | 0.48
ER | 0 | Sea Wolf Trail | CTY K West | Bear Lake Road | 0.6
ER | 0 | Shalimar Lane | CTY H, North Creek Road | Wilson Lane | 0.1
ER | 0 | Shamrock lane (extension) | CTY K West | Highland Drive | 0.22
ER | 0 | Shelter Bay Trail | CTY M North | Fishtrap Road | 0.1
ER | 0 | Shoemaker Trail | CTY H, Rudolph Lake Ln | R.E.S Lane | 0.6
ER | 0 | Six Point Lane | CTY M North | Airport Road
ER | 0 | Stiloski Lane (Extension) | CTY M North, High-FT Lake Rd | Fishtrap Road | 0.23 |  | X
ER | 0 | Stone Gate Lane | US 51 North | XX
ER | 0 | Stonehaven | CTY K West | Bear Lake Road
ER | 0 | Summer Bay Trail | CTY M North, High-FT Lake Rd | High Lake, Ridge Ln, High Pines | 0.75
ER | 0 | Swanson Trail
ER | 0 | Taylor Timber Trail | CTY M North, High-FT Lake Rd | High Lake, Ridge Ln, High Pines | 0.6
ER | 0 | The Narrows Trail | CTY M North, High-FT Lake Rd | Fishtrap Road, Stiloski Ln | 0.42
ER | 0 | Timber Oak Trail
ER | 0 | Totem Trail | CTY M South, North Creek Rd | Princess Pine Lane | 0.08
ER | 0 | Vanny Trail | US 51 North | Jolin Lane
ER | 0 | Wee Pines Trail | US 51 North | XX
ER | 0 | White Sand Trail | Old K | Concora Road | 0.05 |  |  | 0.05 |  |  |  |  | 0.05 |  | 4750
ER | 0 | Wildcat Road | CTY M North | XX | [11 empty] | assume Presque Ilse handles this road
ER | 0 | Wildwood Lane | CTY K West, CTY M North | Highland Drive | 0.4
ER | 0 | Williams Lane | US 51 North | XX
ER | 0 | Wilson Lane | CTY H | North Creek Road | 0.3
ER | 0 | Windy Shores Drive | CTY M South, North Creek Rd | Princess Pine Lane | 0.1
ER | 0 | Wittigs Point Lane | CTY M North, High-FT Lake Rd | Fishtrap Road
ER | 0 | Wolf Lake lane (Dairyman's) | CTY M North | Dairymen's Road
ER |  | Copp Lane
ER |  | Field Lane
ER |  | Gresham Creek Trail
ER |  | Musky Lodge Lane
ER |  | Raven Retreat Trail
ER |  | Riverstone Drive
ER |  | Ryan Road
|  |  |  | TOTAL MILES | 15.85 | 93.62 | 25.79 | 55.17 | 12.37 |  |  | 13.74 | 34.61 | 15.86 | 6393400 | TOTAL ESTIMATED COST
[8 empty] | Town Road Mileage | 93.33 |  |  | Gravel | Chip | Asphalt
[9 empty] | 99.69% |  |  |  |  | 68.59% | Percent of Town Roads receiving roadwork
COLOR KEY
|  | 1 | Recently Updated, Or in Good Condition - No work planned
|  | 2 | Paved Road, repaving planned, same surface
|  | 3 | Paved Road, repaving planned, new surface
|  | 4 | Existing Gravel Road, planned upgrade to pavement
|  | 5 | Existing Gravel Road, general grading and gravel
|  | 6 | Existing Gravel Road/Fire Road - No Plans
PAVING COST PER MILE
|  |  |  | Existing Surface | Gravel | Chip Seal | Asphalt
|  |  |  | GRAVEL | 40000 | 60000 | 155000
|  |  |  | CHIP SEAL | 40000 | 95000 | 155000
|  |  |  | ASPHALT | 40000 | 95000 | 155000
NOTES:
| 1 | what about cost of markings, lines, signs?
| 2 | what about easements costs for bike lanes, turn arounds, widening?
| 3 | what about engineering costs for widening, turn arounds, general improvements
| 4 | any bridge or culvert work to include?
| 5 | need to identify roads, mileage for potential cost share
6
7
8
9

## Roads-Ranking
TOWN OF BOULDER JUNCTION
TOWN ROAD REDEVELOPMENT PLAN
| PLAN |  |  |  | Length |  | SURFACE TYPE |  |  |  |  | RATING |  |  |  |  | Work Scope |  | Extra Work
TYPE | CAT | ROAD NAME | Primary Access Road | Secondary Access Road | ER | TR | Gravel | Chip | Asphalt | Seal Coated or Resurfaced |  | Traffic | Occupancy | Condition | Score | Surface | Engrg | Extra | Description | COMMENTS
TR | 3 | Allen Road | CTY M North | High Lake Road |  | 0.68 |  | 0.68 |  | 1975, 1990 |  | 5 | 5 | 5 | 15 |  |  |  |  | upgrade to asphalt, widen 8' for Bike lanes (White Deer Loop)
TR | 3 | Fishtrap Lake Road | CTY M North, High-FT Lake Rd | XX |  | 2.04 |  | 2.04 |  | 72,73,75,82,86 |  | 5 | 5 | 5 | 15 |  |  |  |  | Do we want all or % as Asphalt??? Shown with asphalt to trail corner
TR | 3 | Newcomb Lane | CTY K West | XX |  | 3.5 |  | 3.5 |  | 78,80,83,88,92 |  | 5 | 5 | 5 | 15
TR | 3 | North Creek Road | CTY M South | CTY H |  | 4.57 |  | 4.57 |  | 75, 76, 87, 92 |  | 5 | 5 | 5 | 15 |  |  |  |  | Possible width increase for Bike Route, Cost share with DNR
TR | 2 | Kern Lane | CTY m South | North Creek Road |  | 1.1 |  | 1.1 |  |  |  | 3 | 4 | 5 | 12
TR | 2 | Concora Road | Old K | XX |  | 0.8 |  | 0.8 |  |  |  | 3 | 3 | 5 | 11
TR | 2 | High Lake Road (after Ridge) | [5 empty] | 1.3 |  |  |  | 3 | 3 | 5 | 11
TR | 2 | Old K Road | CTY M, Main Street | CTYK East |  | 2.79 |  | 2.79 |  | 1969, 1991 |  | 3 | 3 | 5 | 11 |  |  |  |  | widen 8' for bike loop (Asphalt??)
TR | 2 | Harmony Point Lane | US 51 North | between M and H |  | 0.6 |  | 0.6 |  | 1974, 1982 |  | 2 | 3 | 5 | 10 |  |  |  |  | narrow road
TR | 2 | Shore Drive | CTY K West | Newcomb Lane |  | 1.03 |  | 1.03 |  | 1991 |  | 2 | 3 | 5 | 10
TR | 2 | Lucas Lane | CTY K West | XX |  | 0.15 |  | 0.15 |  | 1971 |  | 2 | 2 | 5 | 9 |  |  |  |  | paved to start of campground
TR | 2 | Cattail Cove Lane | CTY K West | XX |  | 0.75 |  | 0.75 |  | 1992 |  | 1 | 1 | 5 | 7
TR | 2 | Major Road | CTY M North | Dairymen's Road |  | 0.5 |  | 0.5 |  | 1973 |  | 1 | 1 | 5 | 7 |  |  |  |  | road to nowhere, pave only if benefit to Dairymen's
TR | 5 | North Oswego Lake Road | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road |  | 0.24 | 0.24 |  |  | 1991 |  | 1 | 1 | 5 | 7
TR | 2 | Sherry Drive | CTY M North, High-FT Lake Rd | High Lake Road |  | 0.05 |  | 0.05 |  |  |  | 1 | 1 | 5 | 7
TR | 2 | Spruce Drive | CTY M North, High-FT Lake Rd | High Lake Road |  | 0.22 |  | 0.22 |  |  |  | 1 | 1 | 5 | 7 |  |  |  |  | create turn-arounds at each end
TR | 6 | Keego Road East | CTY K West, Bear lake Road | Keego Road |  | 1.31 | 1.31 |  |  |  |  | 1 | 0.5 | 5 | 6.5
TR | 6 | Old Flambeau Road | CTY H?? | Bakken Rd ?? |  | 0.74 | 0.74 |  |  |  |  | 0.5 | 1 | 5 | 6.5 |  |  |  |  | No signs, looks like snowmobile trail, barely a road
TR | 3 | Fallon Road | CTY K West | XX |  | 2.08 |  | 2.08 |  | 1984, 1986 |  | 5 | 5 | 4 | 14
TR | 2 | Island Lake Road | US 51 North | XX |  | 1.28 |  | 1.28 |  | 1987 |  | 4 | 5 | 4 | 13
TR | 4 | Big Muskellunge Road | CTY M South | XX |  | 2.7 | 1.2 | 1 | 0.5 | 1976 |  | 5 | 3 | 4 | 12
TR | 2 | Shamrock Lane | CTY K West | Highland Drive |  | 0.4 |  | 0.4 |  |  |  | 3 | 4 | 4 | 11
TR | 2 | Bakken Road (East) | CTY H | HWY 51 N |  | 1.07 |  | 1.07 |  | 67,68 |  | 3 | 3 | 4 | 10 |  |  |  |  | Asphalt upgrade??
TR | 3 | Highland Drive | CTY K West | CTY M North |  | 0.28 |  | 0.28 |  | 1976, 1990 |  | 3 | 3 | 4 | 10 |  |  |  |  | Upgrade for Bike Loop and Event Bypass support
TR | 2 | Wool Lake Lane | CTY K West | XX |  | 0.76 |  | 0.76 |  | 1967, 1972, 1983 |  | 3 | 3 | 4 | 10
TR | 2 | Keego Road | CTY K West | XX |  | 1.25 |  | 1.25 |  | 1984 |  | 2 | 2 | 4 | 8
TR | 2 | Little Rice Lane | CTY M North | XX |  | 0.28 |  | 0.28 |  |  |  | 2 | 2 | 4 | 8
TR | 2 | Boulder Lane | CTY M North | XX |  | 0.4 |  | 0.4 |  |  |  | 1 | 3 | 4 | 8
TR | 2 | Rintlemen | CTY K West | Fallon Road |  | 0.6 |  | 0.6 |  |  |  | 2 | 2 | 4 | 8
TR | 2 | Stiloski Lane | CTY M North, High-FT Lake Rd | Fishtrap Road |  | 0.37 |  | 0.37 |  | 1975 |  | 1 | 2 | 4 | 7
TR | 2 | Whitney Lake Road | CTY K West | XX |  | 1 | 0.1 | 0.9 |  |  |  | 1 | 2 | 4 | 7
TR | 4 | Airport Road (gravel) |  |  |  |  | 1 |  |  |  |  | 2 | 1 | 4 | 7
TR | 2 | Trout Lane | CTY M South, North Creek Rd | Kern lane |  | 0.2 |  | 0.2 |  |  |  | 1 | 2 | 4 | 7
TR | 4 | Sunset Lane | CTY M South, North Creek Rd | Kern lane, Trout lane |  | 0.3 | 0.3 |  |  |  |  | 1 | 2 | 4 | 7 |  |  |  |  | gravel, is this a town road? Pave it??
TR | 2 | Allequash Lake Road | CTY M South | XX |  | 0.94 |  | 0.94 |  |  |  | 2 | 0.5 | 4 | 6.5
TR | 2 | Campo Fiesta Lane | CTY M South | North Creek Road |  | 0.13 |  | 0.13 |  |  |  | 1 | 1 | 4 | 6
TR | 2 | Dolittle Road | CTY M North | Boulder Lane |  | 0.15 |  | 0.15 |  |  |  | 1 | 1 | 4 | 6 |  |  |  |  | make widening part of agreement with owners, doable
TR | 4 | Blue Heron Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead |  | 0.12 | 0.12 |  |  |  |  | 1 | 1 | 4 | 6
TR | 4 | White Deer Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead |  | 0.12 | 0.12 |  |  |  |  | 1 | 1 | 4 | 6
TR | 2 | East Fitzgerald Lane | US 51 N, Island lake Rd | Fitzgerald Lane |  | 0.11 |  | 0.11 |  |  |  | 1 | 1 | 4 | 6
TR | 2 | Fitzgerald Lane | US 51 North | Island Lake Road |  | 0.2 |  | 0.2 |  |  |  | 1 | 1 | 4 | 6
TR | 2 | High-Fishtrap Lake Road | CTY M North | XX |  | 1.1 |  |  | 1.1 |  |  | 5 | 5 | 3 | 13 |  |  |  |  | asphalt for loop, add 8' to width
TR | 2 | Rudolph Lake Lane | CTY H | XX |  | 0.6 |  | 0.6 |  |  |  | 3 | 4 | 3 | 10
TR | 2 | Green Street | CTY M | Old K |  | 0.27 |  | 0.27 |  |  |  | 4 | 2 | 3 | 9
TR | 1 | Bakken Road (West) | CTY H | HWY 51 N |  | 2.15 |  | 2.15 |  |  |  | 3 | 3 | 3 | 9
TR | 2 | La Fave Road | US 51 North | Island Lake Road |  | 1.24 |  | 1.24 |  | 1970 |  | 3 | 3 | 3 | 9 |  |  |  |  | Northwest segment only
TR | 2 | Arrowhead Drive | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road |  | 0.55 | 0.15 | 0.45 |  | 82, 88 |  | 2 | 3 | 3 | 8 |  |  |  |  | turn around work
TR | 2 | Evergreen Lane | CTY K West | XX |  | 1.98 |  | 1.98 |  | 1974 |  | 3 | 2 | 3 | 8 |  |  |  |  | check condition
TR | 5 | Nebish lake Road | CTY K West | XX |  | 1.97 | 1.97 |  |  |  |  | 4 | 1 | 3 | 8
TR | 2 | Mann Lake Road | CTY M South | XX |  | 0.75 |  | 0.75 |  | 1973, 1990 |  | 2 | 3 | 3 | 8 |  |  |  |  | first .1m ok, no turn around
TR | 2 | Middle Gresham Lane | US 51 North (near H) | XX |  | 0.43 |  | 0.43 |  |  |  | 2 | 3 | 3 | 8
TR | 5 | Old 51 Road (Bakken Rd - Island Lake Rd) | CTY H, Bakken Rd (east) | US 51 N, Island Lake Rd |  | 1.8 | 1.8 |  |  | 1980 |  | 2 | 2 | 3 | 7 |  |  |  |  | snowmobile %
TR | 2 | Glen Lake Road | CTY K West | Shamrock Road |  | 0.25 |  | 0.25 |  | 1988 |  | 1 | 3 | 3 | 7
TR | 5 | Dam Road | CTY M North | High-Fishtrap Lake Road |  | 0.8 | 0.8 |  |  |  |  | 3 | 1 | 3 | 7
TR | 5 | Nixon Lake Road | CTY K East | XX |  | 2.6 | 2.6 |  |  |  |  | 3 | 1 | 3 | 7 |  |  |  |  | Seek cost share with DNR
TR | 1 | Old 51 Road (Town Line - Island Lake Rd) | US 51 North | Town Line Rd, Island lake Rd |  | 1.07 |  | 1.07 |  |  |  | 3 | 1 | 3 | 7
TR | 4 | Camp Manitowish Lane (East) | CTY K West | XX |  | 0.5 | 0.5 |  |  |  |  | 2 | 2 | 3 | 7 |  |  |  |  | pave it since CMW will be carrying big tax bill
TR | 1 | Rustic Colony Lane | CTY M North | Airport Road |  | 0.27 |  | 0.27 |  |  |  | 1 | 3 | 3 | 7
TR | 1 | Nichols Lake Lane | CTY H | CTY K West |  | 0.63 |  | 0.63 |  |  |  | 2 | 1 | 3 | 6
TR | 2 | Pine Lane | US 51 North | Bakken Road (west) |  | 0.45 |  | 0.45 |  | 1984 |  | 1 | 2 | 3 | 6 |  |  |  |  | no turn around
TR | 6 | Point Lane | CTY K West | Fallon Rd, Rintleman Rd |  | 0.25 | 0.25 |  |  |  |  | 1 | 2 | 3 | 6 |  |  |  |  | Good condition, Consider Paving?
TR | 4 | South Shore Bay Lane | US 51 North | Island Lake Road |  | 0.15 | 0.15 |  |  |  |  | 1 | 2 | 3 | 6
TR | 1 | Senior Drive | CTY M, Park Street | Green Street |  | 0.2 |  | 0.2 |  |  |  | 1 | 1 | 3 | 5
TR | 2 | Charlotte Place Lane | US 51 North | XX |  | 0.25 |  | 0.25 |  |  |  | 1 | 1 | 3 | 5
TR | 2 | Red Fox Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead |  | 0.09 |  | 0.09 |  |  |  | 1 | 1 | 3 | 5
TR | 4 | En-Dah Win Lane | CTY K East | XX |  | 0.15 | 0.15 |  |  |  |  | 1 | 1 | 3 | 5 |  |  |  |  | only pave to T
TR | 4 | Partridge Lane | CTY M North, High-FT Lake Rd | High Lake Road |  | 1.1 | 1.1 |  |  |  |  | 1 | 1 | 3 | 5
TR | 4 | Perch Lane | CTY M South (by N) |  |  | 0.23 | 0.23 |  |  |  |  | 1 | 1 | 3 | 5 |  |  |  |  | no turn around
TR | 4 | Pinewood Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln |  | 0.12 | 0.12 |  |  |  |  | 1 | 1 | 3 | 5
TR | 5 | Birch Point Lane | CTY K West | Bear Lake Road |  | 0.19 | 0.19 |  |  |  |  | 1 | 1 | 3 | 5
TR | 5 | Halverson Lane | CTY M South | XX |  | 0.12 | 0.12 |  |  |  |  | 1 | 1 | 3 | 5
TR | 5 | White Birch Lane | CTY M North, High-FT Lake Rd | Osewgo-FT Lake Road |  | 0.45 | 0.45 |  |  |  |  | 1 | 1 | 3 | 5
TR | 6 | Street Lake Lane | CTY H | XX |  | 0.65 | 0.65 |  |  |  |  | 1 | 1 | 3 | 5 |  |  |  |  | do we want to pave??
TR | 4 | Balsam Lane | US 51 North | Bakken Road (west) |  | 0.35 | 0.35 |  |  |  |  | 1 | 1 | 3 | 5 |  |  |  |  | no turn around
TR | 5 | Bass Lake Road | CTY K West | Bear Lake Road |  | 0.41 | 0.41 |  |  |  |  | 1 | 1 | 3 | 5
TR | 1 | Kassien Lane | US 51 North | Island Lake Road |  | 0.54 |  | 0.54 |  |  |  | 1 | 1 | 3 | 5
TR | 5 | Pine Shores Lane | US 51 North | Bakken Road (west) |  | 0.06 | 0.06 |  |  |  |  | 1 | 1 | 3 | 5
TR | 5 | Day Lake Road | North Creek Road | US 51 North |  | 2.91 | 2.91 |  |  |  |  | 1 | 0.5 | 3 | 4.5 |  |  |  |  | Basic work, not full gravel work up
TR | 1 | Day Lake Landing Road | Day Lake Road | XXX |  | 0.22 | 0.22 |  |  |  |  | 1 | 0.5 | 3 | 4.5
TR | 5 | Boat Landing Road (Island lake) | US 51 North | Island Lake Road |  | 0.5 | 0.5 |  |  |  |  | 1 | 0.5 | 3 | 4.5
TR | 4 | Marsh Road | CTY M South | CTY K West |  | 1.04 | 1.04 |  |  |  |  | 1 | 0.5 | 3 | 4.5 |  |  |  |  | Create Bike bypass for through riders, better use of events
TR | 6 | Vandercook Road | CTY M South | XX |  | 0.08 | 0.08 |  |  |  |  | 1 | 0.5 | 3 | 4.5 |  |  |  |  | trapped between Arbor Vitae roads, snowmobile trail 100%
TR | 2 | High Lake Road (FT to Ridge) | CTY M North, High-FT Lake Rd | Allen Road |  | 3.8 |  |  | 2.5 | 1972, 1983 |  | 5 | 5 | 2 | 12 |  |  |  |  | Between Allen and Ridge is okay, Chip ridge to end, asphalt loop leg
TR | 4 | Airport Road (paved) | CTY M North | Dairymen's Road |  | 2.45 |  |  | 1.45 | 1969, 1984 |  | 5 | 5 | 2 | 12 |  |  |  |  | Pave 1 mi of gravel, denote "bike share", (Airport Loop)
TR | 1 | Oswego-Fishtrap Lake Road | CTY M North, High-FT Lake Rd | Fishtrap Road |  | 1.9 |  | 1.9 |  |  |  | 4 | 5 | 2 | 11
TR | 3 | Dairymens Road | CTY M North | XX |  | 1.55 |  | 1.55 |  | 1973, 1988 |  | 4 | 5 | 2 | 11 |  |  |  |  | Asphalt to benefit Dairymens and Bike loop, widen 8'
TR | 1 | South Town Line | US 51 North | XX |  | 1.36 |  | 1.36 |  | 1976, 1988 |  | 4 | 5 | 2 | 11
TR | 1 | North Town Line Rd (Town Road 116) | US 51 North | Le Fave Rd, Island Lake Rd |  | 1 |  | 1 |  | 1991 |  | 4 | 4 | 2 | 10
TR | 1 | Ben Bendrick Drive (Lake Shore Drive) | CTY M South | XX |  | 1.7 |  |  | 1.7 |  |  | 4 | 3 | 2 | 9
TR | 2 | High Pines Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln |  | 1.1 |  | 1.1 |  | 1978 |  | 3 | 4 | 2 | 9 |  |  |  |  | needs improved turn around area
TR | 3 | Grahl Lane | CTY H | XX |  | 0.43 | 0.43 |  |  |  |  | 3 | 2 | 2 | 7
TR | 6 | Clear View Drive | CTY K West | Fallon Road |  | 0.34 | 0.34 |  |  |  |  | 3 | 2 | 2 | 7 |  |  |  |  | good condition, consider paving all or part
TR | 4 | Platinum Lane | CTY H | Grahl Lane |  | 0.23 | 0.23 |  |  |  |  | 2 | 2 | 2 | 6
TR | 1 | Rocky Reef Lane | CTY M South | CTY N West |  | 0.54 |  | 0.54 |  | 1982, 1992 |  | 2 | 2 | 2 | 6 |  |  |  |  | poor turn around area
TR | 1 | Camp Manitowish Lane (West) | CTY K West | XX |  | 0.5 |  | 0.5 |  |  |  | 2 | 2 | 2 | 6
TR |  | Town Road 119 (Clear View) | CTY K West, Fallon Rd | Clear View Drive |  | 0.14 | 0.25 |  |  |  |  | 2 | 2 | 2 | 6
TR | 2 | Annes Place | Old K | Green Street |  | 0.14 |  | 0.14 |  |  |  | 2 | 1 | 2 | 5
TR | 1 | Center Street | CTY M South, Park Street | Marsh Rd, Ada, Blueberry |  | 0.31 |  | 0.31 |  |  |  | 2 | 1 | 2 | 5
TR | 2 | Church Street | Old K | Green Street |  | 0.14 |  | 0.14 |  |  |  | 2 | 1 | 2 | 5
TR | 1 | Blueberry Lane | Main Street, CTY K West | Center Street |  | 0.25 |  | 0.25 |  |  |  | 2 | 1 | 2 | 5
TR | 4 | Little Crooked Lane | CTY K West | Bear Lake Road |  | 0.38 | 0.38 |  |  |  |  | 1 | 2 | 2 | 5
TR | 1 | Birchwood Lane | CTY M North | Airport Road |  | 0.36 |  | 0.36 |  | 1984 |  | 1 | 2 | 2 | 5
TR | 1 | Ada Street | CTY M | Main Street |  | 0.25 |  | 0.25 |  |  | <10 | 1 | 1 | 2 | 4
TR | 1 | Blaisdell Street | Main Street, CTY K West | Ada, Blueberry |  | 0.17 |  | 0.17 |  |  |  | 1 | 1 | 2 | 4
TR | 1 | Community Street | CTY K West | Blaisdell Street |  | 0.2 |  | 0.2 |  |  |  | 1 | 1 | 2 | 4
TR | 2 | Reible Court | Old K | XX |  | 0.12 |  | 0.12 |  |  |  | 1 | 1 | 2 | 4
TR | 5 | Maple Lake Road | CTY K West | XX |  | 0.35 | 0.35 |  |  |  |  | 1 | 1 | 2 | 4
TR | 5 | West Big Lake Road (lane) | CTY K West | XX |  | 1.04 | 1.04 |  |  |  |  | 1 | 1 | 2 | 4 |  |  |  |  | one house, why is this a town road?
TR | 6 | Birch Drive | CTY M North, High-FT Lake Rd | High Lake Road |  | 0.25 | 0.25 |  |  |  |  | 1 | 1 | 2 | 4
TR | 6 | River lane | CTY K West | XX |  | 0.2 | 0.2 |  |  |  |  | 1 | 1 | 2 | 4
TR | 6 | South Rudolph Lake Lane | CTY H | Rudolph Lake Lane |  | 0.26 | 0.26 |  |  | 1987 |  | 1 | 1 | 2 | 4
TR | 1 | Round Lake Road | CTY K West | Bear Lake Road |  | 0.1 |  | 0.1 |  |  |  | 1 | 0.5 | 2 | 3.5
TR | 6 | Jag Lake Road | CTY H | XX |  | 0.08 | 0.08 |  |  |  |  | 1 | 0.5 | 2 | 3.5 |  |  |  |  | boat landing
TR | 5 | Ridge Lane | CTY M North, High-FT Lake Rd | High Lake Rd |  | 1.2 | 0.3 | 0.9 |  | 1983 |  | 3 | 4 | 1 | 8
TR | 1 | Bear Lake Road | CTY K West | XX |  | 3.26 |  |  | 3.26 | 1971, 1974, 1986 | 2015 | 3 | 3 | 1 | 7 |  |  |  |  | repaved with asphalt in 2015
TR | 1 | Town Hall Road | Around Community Building |  |  | 0.12 |  |  | 0.12 | 1987 |  | 4 | 1 | 1 | 6
TR | 1 | Good Life Lane | CTY M North | Airport Road |  | 0.44 |  |  | 0.44 |  |  | 1 | 1 | 1 | 3
TR | 1 | Cemetary Road | CTY K West | XX |  | 0.18 |  | 0.18 |  |  |  | 1 | 0.5 | 1 | 2.5
TR | 0 | Old 51 East Hoffman Road |  | 0.26 | [10 empty] | 0
TR | 0 | Old 51 Old H |  | 1.17 | [10 empty] | 0
TR | 1 | Round Lake Road (Presque Isle) | CTY K West | Bear Lake Road |  | 1.25 |  | 1.25 | [6 empty] | 0
TR |  | Town Road 127 |  |  |  | 0.1 | [8 empty] | 0
TR |  | Town Road 133 |  |  |  | 0.15 | X | [7 empty] | 0
0
0
|  |  |  | TOTAL MILES | 0 | 93.62 | 26.04 | 56.42 | 11.07 | [9 empty] | 0 | TOTAL ESTIMATED COST
[8 empty] | Town Road Mileage | 93.53
[9 empty] | 99.9% |  |  |  |  | 0% |  |  |  |  | Percent of Town Roads receiving roadwork
COLOR KEY
|  | 1 | Recently Updated, Or in Good Condition - No work planned
|  | 2 | Paved Road, repaving planned, same surface
|  | 3 | Paved Road, repaving planned, new surface
|  | 4 | Existing Gravel Road, planned upgrade to pavement
|  | 5 | Existing Gravel Road, general grading and gravel
|  | 6 | Existing Gravel Road/Fire Road - No Plans
PAVING COST PER MILE
|  |  |  | Existing Surface | Gravel | Chip Seal | Asphalt
|  |  |  | GRAVEL | 40000 | 60000 | 155000
|  |  |  | CHIP SEAL | 40000 | 95000 | 155000
|  |  |  | ASPHALT | 40000 | 95000 | 155000
NOTES:
| 1 | what about cost of markings, lines, signs?
| 2 | what about easements costs for bike lanes, turn arounds, widening?
| 3 | what about engineering costs for widening, turn arounds, general improvements
| 4 | any bridge or culvert work to include?
| 5 | need to identify roads, mileage for potential cost share
6
7
8
9

## Roads-Ranking (2)
TOWN OF BOULDER JUNCTION
TOWN ROAD REDEVELOPMENT PLAN
| PLAN |  |  |  | Length |  | SURFACE TYPE |  |  |  |  | RATING |  |  |  | WORK SCOPE
TYPE | PHASE | ROAD NAME | Primary Access Road | Secondary Access Road | ER | TR | Gravel | Chip | Asphalt | Seal Coated or Resurfaced |  | Traffic | Occupancy | Condition | Score | Surface | Expansion | Bridge / Culvert | Safety | Drainage | WORKSCOPE COMMENTS
TR | 1 | Allen Road | CTY M North | High Lake Road |  | 0.68 |  | 0.68 |  | 1975, 1990 |  | 5 | 5 | 5 | 15 | N | BL |  |  | X | minor shoulder grading for drainage | upgrade to asphalt, widen 8' for Bike lanes (White Deer Loop)
TR | 1 | Fishtrap Lake Road | CTY M North, High-FT Lake Rd | XX |  | 2.04 |  | 2.04 |  | 72,73,75,82,86 |  | 5 | 5 | 5 | 15 | A/N | TO? |  | X |  | shoulder work, veg removal, start asphalt, go to New Road | Do we want all or % as Asphalt??? Shown with asphalt to trail corner
TR | 1 | Newcomb Lane | CTY K West | XX |  | 3.5 |  | 3.5 |  | 78,80,83,88,92 |  | 5 | 5 | 5 | 15 | A |  | X | X | X
TR | 1 | North Creek Road | CTY M South | CTY H |  | 4.57 |  | 4.57 |  | 75, 76, 87, 92 |  | 5 | 5 | 5 | 15 | A | BL/BT | X | X | X | possible 2 new culverts, shave some veg from corners, some shoulder work for drainage, widen? | Possible width increase for Bike Route, Cost share with DNR
TR | 1 | Kern Lane | CTY m South | North Creek Road |  | 1.1 |  | 1.1 |  |  |  | 3 | 4 | 5 | 12 | C |  |  |  |  | with Trout Lane, and Sunset
TR | 1 | Concora Road | Old K | XX |  | 0.8 |  | 0.8 |  |  |  | 3 | 3 | 5 | 11 | C
TR | 1 | High Lake Road (after Ridge) | [5 empty] | 1.3 |  |  |  | 3 | 3 | 5 | 11
TR | 1 | Old K Road | CTY M, Main Street | CTYK East |  | 2.79 |  | 2.79 |  | 1969, 1991 |  | 3 | 3 | 5 | 11 | [5 empty] | asphalt to Concora, chip to K | widen 8' for bike loop (Asphalt??)
TR | 1 | Harmony Point Lane | US 51 North | between M and H |  | 0.6 |  | 0.6 |  | 1974, 1982 |  | 2 | 3 | 5 | 10 | [6 empty] | narrow road
TR | 1 | Shore Drive | CTY K West | Newcomb Lane |  | 1.03 |  | 1.03 |  | 1991 |  | 2 | 3 | 5 | 10 | C | TO |  |  |  | with Newcomb , look at turn around space
TR | 1 | Fallon Road | CTY K West | XX |  | 2.08 |  | 2.08 |  | 1984, 1986 |  | 5 | 5 | 4 | 14
TR | 1 | Island Lake Road | US 51 North | XX |  | 1.28 |  | 1.28 |  | 1987 |  | 4 | 5 | 4 | 13
TR | 1 | Big Muskellunge Road | CTY M South | XX |  | 2.7 | 1.2 | 1 | 0.5 | 1976 |  | 5 | 3 | 4 | 12
TR | 1 | Shamrock Lane | CTY K West | Highland Drive |  | 0.4 |  | 0.4 |  |  |  | 3 | 4 | 4 | 11
TR | 1 | Bakken Road (East) | CTY H | HWY 51 N |  | 1.07 |  | 1.07 |  | 67,68 |  | 3 | 3 | 4 | 10 | [6 empty] | Asphalt upgrade??
TR | 1 | Highland Drive | CTY K West | CTY M North |  | 0.28 |  | 0.28 |  | 1976, 1990 |  | 3 | 3 | 4 | 10 | [6 empty] | Upgrade for Bike Loop and Event Bypass support
TR | 1 | Wool Lake Lane | CTY K West | XX |  | 0.76 |  | 0.76 |  | 1967, 1972, 1983 |  | 3 | 3 | 4 | 10
Ph1 | 17 | Total Roads Total Mileage |  |  |  |  | 1.2 | 25.28 | 0.5 |  |  | 28.85%
TR | 2 | Lucas Lane | CTY K West | XX |  | 0.15 |  | 0.15 |  | 1971 |  | 2 | 2 | 5 | 9 | [6 empty] | paved to start of campground
TR | 2 | Cattail Cove Lane | CTY K West | XX |  | 0.75 |  | 0.75 |  | 1992 |  | 1 | 1 | 5 | 7
TR | 2 | Major Road | CTY M North | Dairymen's Road |  | 0.5 |  | 0.5 |  | 1973 |  | 1 | 1 | 5 | 7 | [6 empty] | road to nowhere, pave only if benefit to Dairymen's
TR | 2 | North Oswego Lake Road | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road |  | 0.24 | 0.24 |  |  | 1991 |  | 1 | 1 | 5 | 7
TR | 2 | Sherry Drive | CTY M North, High-FT Lake Rd | High Lake Road |  | 0.05 |  | 0.05 |  |  |  | 1 | 1 | 5 | 7
TR | 2 | Spruce Drive | CTY M North, High-FT Lake Rd | High Lake Road |  | 0.22 |  | 0.22 |  |  |  | 1 | 1 | 5 | 7 | [6 empty] | create turn-arounds at each end
TR | 2 | Keego Road | CTY K West | XX |  | 1.25 |  | 1.25 |  | 1984 |  | 2 | 2 | 4 | 8
TR | 2 | Little Rice Lane | CTY M North | XX |  | 0.28 |  | 0.28 |  |  |  | 2 | 2 | 4 | 8
TR | 2 | Boulder Lane | CTY M North | XX |  | 0.4 |  | 0.4 |  |  |  | 1 | 3 | 4 | 8
TR | 2 | Rintlemen | CTY K West | Fallon Road |  | 0.6 |  | 0.6 |  |  |  | 2 | 2 | 4 | 8
TR | 2 | Stiloski Lane | CTY M North, High-FT Lake Rd | Fishtrap Road |  | 0.37 |  | 0.37 |  | 1975 |  | 1 | 2 | 4 | 7 | C/N |  |  |  |  | Elevate priotiy with Fishtrap
TR | 2 | Whitney Lake Road | CTY K West | XX |  | 1 | 0.1 | 0.9 |  |  |  | 1 | 2 | 4 | 7
TR | 2 | Airport Road (gravel) |  |  |  |  | 1 |  |  |  |  | 2 | 1 | 4 | 7
TR | 2 | Trout Lane | CTY M South, North Creek Rd | Kern lane |  | 0.2 |  | 0.2 |  |  |  | 1 | 2 | 4 | 7 | C |  |  |  |  | elevate priority with Kern Lane
TR | 2 | Sunset Lane | CTY M South, North Creek Rd | Kern lane, Trout lane |  | 0.3 | 0.3 |  |  |  |  | 1 | 2 | 4 | 7 | C | TO |  |  |  | elevate priority with Kern Lane, upgrade to chip seal, widen 1-2 ft | gravel, is this a town road? Pave it??
TR | 2 | High-Fishtrap Lake Road | CTY M North | XX |  | 1.1 |  |  | 1.1 |  |  | 5 | 5 | 3 | 13 | [6 empty] | asphalt for loop, add 8' to width
TR | 2 | Rudolph Lake Lane | CTY H | XX |  | 0.6 |  | 0.6 |  |  |  | 3 | 4 | 3 | 10
TR | 2 | Green Street | CTY M | Old K |  | 0.27 |  | 0.27 |  |  |  | 4 | 2 | 3 | 9
TR | 2 | Bakken Road (West) | CTY H | HWY 51 N |  | 2.15 |  | 2.15 |  |  |  | 3 | 3 | 3 | 9
TR | 2 | La Fave Road | US 51 North | Island Lake Road |  | 1.24 |  | 1.24 |  | 1970 |  | 3 | 3 | 3 | 9 | [6 empty] | Northwest segment only
TR | 2 | Arrowhead Drive | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road |  | 0.55 | 0.15 | 0.45 |  | 82, 88 |  | 2 | 3 | 3 | 8 | [6 empty] | turn around work
TR | 2 | Evergreen Lane | CTY K West | XX |  | 1.98 |  | 1.98 |  | 1974 |  | 3 | 2 | 3 | 8 | [6 empty] | check condition
TR | 2 | Nebish lake Road | CTY K West | XX |  | 1.97 | 1.97 |  |  |  |  | 4 | 1 | 3 | 8
TR | 2 | Mann Lake Road | CTY M South | XX |  | 0.75 |  | 0.75 |  | 1973, 1990 |  | 2 | 3 | 3 | 8 | [6 empty] | first .1m ok, no turn around
TR | 2 | Middle Gresham Lane | US 51 North (near H) | XX |  | 0.43 |  | 0.43 |  |  |  | 2 | 3 | 3 | 8
Ph2 | 25 | Total Roads Total Mileage |  |  |  |  | 3.76 | 13.54 | 1.1 |  |  | 19.67%
TR | 3 | Campo Fiesta Lane | CTY M South | North Creek Road |  | 0.13 |  | 0.13 |  |  |  | 1 | 1 | 4 | 6
TR | 3 | Dolittle Road | CTY M North | Boulder Lane |  | 0.15 |  | 0.15 |  |  |  | 1 | 1 | 4 | 6 | [6 empty] | make widening part of agreement with owners, doable
TR | 3 | Blue Heron Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead |  | 0.12 | 0.12 |  |  |  |  | 1 | 1 | 4 | 6
TR | 3 | White Deer Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead |  | 0.12 | 0.12 |  |  |  |  | 1 | 1 | 4 | 6
TR | 3 | East Fitzgerald Lane | US 51 N, Island lake Rd | Fitzgerald Lane |  | 0.11 |  | 0.11 |  |  |  | 1 | 1 | 4 | 6
TR | 3 | Fitzgerald Lane | US 51 North | Island Lake Road |  | 0.2 |  | 0.2 |  |  |  | 1 | 1 | 4 | 6
TR | 3 | Old 51 Road (Bakken Rd - Island Lake Rd) | CTY H, Bakken Rd (east) | US 51 N, Island Lake Rd |  | 1.8 | 1.8 |  |  | 1980 |  | 2 | 2 | 3 | 7 | [6 empty] | snowmobile %
TR | 3 | Glen Lake Road | CTY K West | Shamrock Road |  | 0.25 |  | 0.25 |  | 1988 |  | 1 | 3 | 3 | 7
TR | 3 | Dam Road | CTY M North | High-Fishtrap Lake Road |  | 0.8 | 0.8 |  |  |  |  | 3 | 1 | 3 | 7
TR | 3 | Nixon Lake Road | CTY K East | XX |  | 2.6 | 2.6 |  |  |  |  | 3 | 1 | 3 | 7 | [6 empty] | Seek cost share with DNR
TR | 3 | Old 51 Road (Town Line - Island Lake Rd) | US 51 North | Town Line Rd, Island lake Rd |  | 1.07 |  | 1.07 |  |  |  | 3 | 1 | 3 | 7
TR | 3 | Camp Manitowish Lane (East) | CTY K West | XX |  | 0.5 | 0.5 |  |  |  |  | 2 | 2 | 3 | 7 | [6 empty] | pave it since CMW will be carrying big tax bill
TR | 3 | Rustic Colony Lane | CTY M North | Airport Road |  | 0.27 |  | 0.27 |  |  |  | 1 | 3 | 3 | 7
TR | 3 | Nichols Lake Lane | CTY H | CTY K West |  | 0.63 |  | 0.63 |  |  |  | 2 | 1 | 3 | 6
TR | 3 | Pine Lane | US 51 North | Bakken Road (west) |  | 0.45 |  | 0.45 |  | 1984 |  | 1 | 2 | 3 | 6 | [6 empty] | no turn around
TR | 3 | Point Lane | CTY K West | Fallon Rd, Rintleman Rd |  | 0.25 | 0.25 |  |  |  |  | 1 | 2 | 3 | 6 | [6 empty] | Good condition, Consider Paving?
TR | 3 | South Shore Bay Lane | US 51 North | Island Lake Road |  | 0.15 | 0.15 |  |  |  |  | 1 | 2 | 3 | 6
Ph3 | 17 | Total Roads Total Mileage |  |  |  |  | 6.34 | 3.26 | 0 |  |  | 10.26%
TR | 4 | Senior Drive | CTY M, Park Street | Green Street |  | 0.2 |  | 0.2 |  |  |  | 1 | 1 | 3 | 5
TR | 4 | Charlotte Place Lane | US 51 North | XX |  | 0.25 |  | 0.25 |  |  |  | 1 | 1 | 3 | 5
TR | 4 | Red Fox Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead |  | 0.09 |  | 0.09 |  |  |  | 1 | 1 | 3 | 5
TR | 4 | En-Dah Win Lane | CTY K East | XX |  | 0.15 | 0.15 |  |  |  |  | 1 | 1 | 3 | 5 | [6 empty] | only pave to T
TR | 4 | Partridge Lane | CTY M North, High-FT Lake Rd | High Lake Road |  | 1.1 | 1.1 |  |  |  |  | 1 | 1 | 3 | 5
TR | 4 | Perch Lane | CTY M South (by N) |  |  | 0.23 | 0.23 |  |  |  |  | 1 | 1 | 3 | 5 | [6 empty] | no turn around
TR | 4 | Pinewood Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln |  | 0.12 | 0.12 |  |  |  |  | 1 | 1 | 3 | 5
TR | 4 | Birch Point Lane | CTY K West | Bear Lake Road |  | 0.19 | 0.19 |  |  |  |  | 1 | 1 | 3 | 5
TR | 4 | Halverson Lane | CTY M South | XX |  | 0.12 | 0.12 |  |  |  |  | 1 | 1 | 3 | 5
TR | 4 | White Birch Lane | CTY M North, High-FT Lake Rd | Osewgo-FT Lake Road |  | 0.45 | 0.45 |  |  |  |  | 1 | 1 | 3 | 5
TR | 4 | Street Lake Lane | CTY H | XX |  | 0.65 | 0.65 |  |  |  |  | 1 | 1 | 3 | 5 | [6 empty] | do we want to pave??
TR | 4 | Balsam Lane | US 51 North | Bakken Road (west) |  | 0.35 | 0.35 |  |  |  |  | 1 | 1 | 3 | 5 | [6 empty] | no turn around
TR | 4 | Bass Lake Road | CTY K West | Bear Lake Road |  | 0.41 | 0.41 |  |  |  |  | 1 | 1 | 3 | 5
TR | 4 | Kassien Lane | US 51 North | Island Lake Road |  | 0.54 |  | 0.54 |  |  |  | 1 | 1 | 3 | 5
TR | 4 | Pine Shores Lane | US 51 North | Bakken Road (west) |  | 0.06 | 0.06 |  |  |  |  | 1 | 1 | 3 | 5
Ph4 | 15 | Total Roads Total Mileage |  |  |  |  | 3.83 | 1.08 | 0 |  |  | 5.25%
TR | 5 | Keego Road East | CTY K West, Bear lake Road | Keego Road |  | 1.31 | 1.31 |  |  |  |  | 1 | 0.5 | 5 | 6.5
TR | 5 | Old Flambeau Road | CTY H?? | Bakken Rd ?? |  | 0.74 | 0.74 |  |  |  |  | 0.5 | 1 | 5 | 6.5 | [6 empty] | No signs, looks like snowmobile trail, barely a road
TR | 5 | Allequash Lake Road | CTY M South | XX |  | 0.94 |  | 0.94 |  |  |  | 2 | 0.5 | 4 | 6.5
TR | 5 | Day Lake Road | North Creek Road | US 51 North |  | 2.91 | 2.91 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | [6 empty] | Basic work, not full gravel work up
TR | 5 | Day Lake Landing Road | Day Lake Road | XXX |  | 0.22 | 0.22 |  |  |  |  | 1 | 0.5 | 3 | 4.5
TR | 5 | Boat Landing Road (Island lake) | US 51 North | Island Lake Road |  | 0.5 | 0.5 |  |  |  |  | 1 | 0.5 | 3 | 4.5
TR | 5 | Marsh Road | CTY M South | CTY K West |  | 1.04 | 1.04 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | [5 empty] | possible pave option, bike bypass, truck bypass | Create Bike bypass for through riders, better use of events
TR | 5 | Vandercook Road | CTY M South | XX |  | 0.08 | 0.08 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | [6 empty] | trapped between Arbor Vitae roads, snowmobile trail 100%
TR | 5 | High Lake Road (FT to Ridge) | CTY M North, High-FT Lake Rd | Allen Road |  | 3.8 |  |  | 2.5 | 1972, 1983 |  | 5 | 5 | 2 | 12 | [6 empty] | Between Allen and Ridge is okay, Chip ridge to end, asphalt loop leg
TR | 5 | Airport Road (paved) | CTY M North | Dairymen's Road |  | 2.45 |  |  | 1.45 | 1969, 1984 |  | 5 | 5 | 2 | 12 | [6 empty] | Pave 1 mi of gravel, denote "bike share", (Airport Loop)
TR | 5 | Oswego-Fishtrap Lake Road | CTY M North, High-FT Lake Rd | Fishtrap Road |  | 1.9 |  | 1.9 |  |  |  | 4 | 5 | 2 | 11
TR | 5 | Dairymens Road | CTY M North | XX |  | 1.55 |  | 1.55 |  | 1973, 1988 |  | 4 | 5 | 2 | 11 | [6 empty] | Asphalt to benefit Dairymens and Bike loop, widen 8'
TR | 5 | South Town Line | US 51 North | XX |  | 1.36 |  | 1.36 |  | 1976, 1988 |  | 4 | 5 | 2 | 11
TR | 5 | North Town Line Rd (Town Road 116) | US 51 North | Le Fave Rd, Island Lake Rd |  | 1 |  | 1 |  | 1991 |  | 4 | 4 | 2 | 10
TR | 5 | Ben Bendrick Drive (Lake Shore Drive) | CTY M South | XX |  | 1.7 |  |  | 1.7 |  |  | 4 | 3 | 2 | 9
TR | 5 | High Pines Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln |  | 1.1 |  | 1.1 |  | 1978 |  | 3 | 4 | 2 | 9 | [6 empty] | needs improved turn around area
TR | 5 | Grahl Lane | CTY H | XX |  | 0.43 | 0.43 |  |  |  |  | 3 | 2 | 2 | 7
TR | 5 | Clear View Drive | CTY K West | Fallon Road |  | 0.34 | 0.34 |  |  |  |  | 3 | 2 | 2 | 7 | [6 empty] | good condition, consider paving all or part
TR | 5 | Platinum Lane | CTY H | Grahl Lane |  | 0.23 | 0.23 |  |  |  |  | 2 | 2 | 2 | 6
TR | 5 | Rocky Reef Lane | CTY M South | CTY N West |  | 0.54 |  | 0.54 |  | 1982, 1992 |  | 2 | 2 | 2 | 6 | [6 empty] | poor turn around area
TR | 5 | Camp Manitowish Lane (West) | CTY K West | XX |  | 0.5 |  | 0.5 |  |  |  | 2 | 2 | 2 | 6
TR | 5 | Town Road 119 (Clear View) | CTY K West, Fallon Rd | Clear View Drive |  | 0.14 | 0.25 |  |  |  |  | 2 | 2 | 2 | 6
TR | 5 | Annes Place | Old K | Green Street |  | 0.14 |  | 0.14 |  |  |  | 2 | 1 | 2 | 5
TR | 5 | Center Street | CTY M South, Park Street | Marsh Rd, Ada, Blueberry |  | 0.31 |  | 0.31 |  |  |  | 2 | 1 | 2 | 5
TR | 5 | Church Street | Old K | Green Street |  | 0.14 |  | 0.14 |  |  |  | 2 | 1 | 2 | 5
TR | 5 | Blueberry Lane | Main Street, CTY K West | Center Street |  | 0.25 |  | 0.25 |  |  |  | 2 | 1 | 2 | 5
TR | 5 | Little Crooked Lane | CTY K West | Bear Lake Road |  | 0.38 | 0.38 |  |  |  |  | 1 | 2 | 2 | 5
TR | 5 | Birchwood Lane | CTY M North | Airport Road |  | 0.36 |  | 0.36 |  | 1984 |  | 1 | 2 | 2 | 5
TR | 5 | Ada Street | CTY M | Main Street |  | 0.25 |  | 0.25 |  |  | <10 | 1 | 1 | 2 | 4
TR | 5 | Blaisdell Street | Main Street, CTY K West | Ada, Blueberry |  | 0.17 |  | 0.17 |  |  |  | 1 | 1 | 2 | 4
TR | 5 | Community Street | CTY K West | Blaisdell Street |  | 0.2 |  | 0.2 |  |  |  | 1 | 1 | 2 | 4
TR | 5 | Reible Court | Old K | XX |  | 0.12 |  | 0.12 |  |  |  | 1 | 1 | 2 | 4
TR | 5 | Maple Lake Road | CTY K West | XX |  | 0.35 | 0.35 |  |  |  |  | 1 | 1 | 2 | 4
TR | 5 | West Big Lake Road (lane) | CTY K West | XX |  | 1.04 | 1.04 |  |  |  |  | 1 | 1 | 2 | 4 | [6 empty] | one house, why is this a town road?
TR | 5 | Birch Drive | CTY M North, High-FT Lake Rd | High Lake Road |  | 0.25 | 0.25 |  |  |  |  | 1 | 1 | 2 | 4
TR | 5 | River lane | CTY K West | XX |  | 0.2 | 0.2 |  |  |  |  | 1 | 1 | 2 | 4
TR | 5 | South Rudolph Lake Lane | CTY H | Rudolph Lake Lane |  | 0.26 | 0.26 |  |  | 1987 |  | 1 | 1 | 2 | 4
TR | 5 | Round Lake Road | CTY K West | Bear Lake Road |  | 0.1 |  | 0.1 |  |  |  | 1 | 0.5 | 2 | 3.5
TR | 5 | Jag Lake Road | CTY H | XX |  | 0.08 | 0.08 |  |  |  |  | 1 | 0.5 | 2 | 3.5 | [6 empty] | boat landing
TR | 5 | Ridge Lane | CTY M North, High-FT Lake Rd | High Lake Rd |  | 1.2 | 0.3 | 0.9 |  | 1983 |  | 3 | 4 | 1 | 8
TR | 5 | Bear Lake Road | CTY K West | XX |  | 3.26 |  |  | 3.26 | 1971, 1974, 1986 | 2015 | 3 | 3 | 1 | 7 | [6 empty] | repaved with asphalt in 2015
TR | 5 | Town Hall Road | Around Community Building |  |  | 0.12 |  |  | 0.12 | 1987 |  | 4 | 1 | 1 | 6
TR | 5 | Good Life Lane | CTY M North | Airport Road |  | 0.44 |  |  | 0.44 |  |  | 1 | 1 | 1 | 3
TR | 5 | Cemetary Road | CTY K West | XX |  | 0.18 |  | 0.18 |  |  |  | 1 | 0.5 | 1 | 2.5
TR |  | Old 51 East Hoffman Road |  | 0.26 | [10 empty] | 0
TR |  | Old 51 Old H |  | 1.17 | [10 empty] | 0
TR |  | Round Lake Road (Presque Isle) | CTY K West | Bear Lake Road |  | 1.25 |  | 1.25 | [6 empty] | 0
TR |  | Town Road 127 |  |  |  | 0.1 | [8 empty] | 0
TR |  | Town Road 133 |  |  |  | 0.15 | X | [7 empty] | 0
Ph5 | 55 | Total Roads Total Mileage |  |  |  |  | 10.91 | 13.26 | 9.47 |  |  | 35.97%
0
|  |  |  | TOTAL MILES | 0 | 93.62 | 26.04 | 56.42 | 11.07 | 0 | 0 | 100% | [8 empty] | TOTAL ESTIMATED COST
[8 empty] | Town Road Mileage | 93.53
[9 empty] | 99.9% |  |  |  |  | 64.03% | Percent of Town Roads receiving roadwork
COLOR KEY
|  | 1 | Recently Updated, Or in Good Condition - No work planned
|  | 2 | Paved Road, repaving planned, same surface
|  | 3 | Paved Road, repaving planned, new surface
|  | 4 | Existing Gravel Road, planned upgrade to pavement
|  | 5 | Existing Gravel Road, general grading and gravel
|  | 6 | Existing Gravel Road/Fire Road - No Plans
NOTES:
| 1 | what about cost of markings, lines, signs?
| 2 | what about easements costs for bike lanes, turn arounds, widening?
| 3 | what about engineering costs for widening, turn arounds, general improvements
| 4 | any bridge or culvert work to include?
| 5 | need to identify roads, mileage for potential cost share
6
7
8
9

## Roads-AlphaSort
TOWN OF BOULDER JUNCTION
TOWN ROAD REDEVELOPMENT PLAN
| PLAN |  |  |  | Length |  | SURFACE TYPE |  |  |  |  | RESURFACE PLAN |  |  | Estimated
TYPE | CAT | ROAD NAME | Primary Access Road | Secondary Access Road | ER | TR | Gravel | Chip | Asphalt | Seal Coated or Resurfaced |  | Gravel | Chip | Asphalt | RESURFACE COST | COMMENTS
ER | 0 | Abe Le Fave Trail | US 51 N, Island lake Rd | Le Fave Rd | 0.15
TR | 1 | Ada Street | CTY M | Main Street |  | 0.25 |  | 0.25 |  |  | <10 |  | 0 |  | 0
TR | 4 | Airport Road | CTY M North | Dairymen's Road |  | 2.45 | 1 |  | 1.45 | 1969, 1984 |  | 0 | 1 | 0 | 60000 | Pave 1 mi of gravel, denote "bike share", (Airport Loop)
TR | 3 | Allen Road | CTY M North | High Lake Road |  | 0.68 |  | 0.68 |  | 1975, 1990 |  |  | 0 | 0.68 | 158100 | upgrade to asphalt, widen 8' for Bike lanes (White Deer Loop)
TR | 2 | Allequash Lake Road | CTY M South | XX |  | 0.94 |  | 0.94 |  |  |  |  | 0.94 |  | 89300
TR | 2 | Annes Place | Old K | Green Street |  | 0.14 |  | 0.14 |  |  |  |  | 0.14 |  | 13300
ER | 0 | Arbutus Court | CTY M North | XX
ER | 0 | Arneders Lane | CTY M North | High Lake Road | 0.15
TR | 2 | Arrowhead Drive | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road |  | 0.55 | 0.15 | 0.45 |  | 82, 88 |  |  | 0.6 |  | 51750
ER | 0 | Back Country lane | US 51 N, Airport Rd | Rustic Colony Lane
TR | 2 | Bakken Road (East) | CTY H | HWY 51 N |  | 1.07 |  | 1.07 |  | 67,68 |  |  | 1.07 |  | 101650 | Asphalt upgrade??
TR | 1 | Bakken Road (West) | CTY H | HWY 51 N |  | 2.15 |  | 2.15 |  |  |  |  | 0 |  | 0
TR | 4 | Balsam Lane | US 51 North | Bakken Road (west) |  | 0.35 | 0.35 | [5 empty] | 0.35 |  | 21000 | no turn around
TR | 5 | Bass Lake Road | CTY K West | Bear Lake Road |  | 0.41 | 0.41 |  |  |  |  | 0.41 |  |  | 16400
ER | 0 | Bays End | CTY K West, Highland Drive | Shamrock, Island Point | 0.1
ER | 0 | Bayshore Trail
ER | 0 | Beach View Trail | Old K | Concora Road | 0.05
TR | 1 | Bear Lake Road | CTY K West | XX |  | 3.26 |  |  | 3.26 | 1971, 1974, 1986 | 2015 |  |  | 0 | 0
ER | 0 | Bearwalk Lane | CTY M North | Airport Road
ER | 0 | Belden lane | CTY M North | Boulder Lane | 0.2
TR | 1 | Ben Bendrick Drive (Lake Shore Drive) | CTY M South | XX |  | 1.7 |  |  | 1.7 |  |  |  |  | 0 | 0
ER | 0 | Best Fishes Lane | CTY M South | North Creek Road | 0.43
TR | 4 | Big Muskellunge Road | CTY M South | XX |  | 2.7 | 1.2 | 1 | 0.5 | 1976 |  |  | 2.2 |  | 167000
TR | 6 | Birch Drive | CTY M North, High-FT Lake Rd | High Lake Road |  | 0.25 | 0.25 |  |  |  |  | 0 |  |  | 0
TR | 5 | Birch Point Lane | CTY K West | Bear Lake Road |  | 0.19 | 0.19 |  |  |  |  | 0.19 |  |  | 7600
TR | 1 | Birchwood Lane | CTY M North | Airport Road |  | 0.36 |  | 0.36 |  | 1984 |  |  | 0 |  | 0
TR | 1 | Blaisdell Street | Main Street, CTY K West | Ada, Blueberry |  | 0.17 |  | 0.17 |  |  |  |  | 0 |  | 0
TR | 4 | Blue Heron Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead |  | 0.12 | 0.12 | [5 empty] | 0.12 |  | 7200
TR | 1 | Blueberry Lane | Main Street, CTY K West | Center Street |  | 0.25 |  | 0.25 |  |  |  |  | 0 |  | 0
TR | 5 | Boat Landing Road (Island lake) | US 51 North | Island Lake Road |  | 0.5 | 0.5 |  |  |  |  | 0.5 |  |  | 20000
ER | 0 | Bog Trail | US 51 North | XX
TR | 2 | Boulder Lane | CTY M North | XX |  | 0.4 |  | 0.4 |  |  |  |  | 0.4 |  | 38000
ER | 0 | Boulder Ridge trail | CTY M North | XX | 0.2
ER | 0 | Brenner Trail | CTY K West | XX | 0.34
ER | 0 | Brouwer Trail | CTY M North, Airport Rd | Rustic Colony Lane | 0.15
TR | 4 | Camp Manitowish Lane (East) | CTY K West | XX |  | 0.5 | 0.5 | [5 empty] | 0.5 |  | 30000 | pave it since CMW will be carrying big tax bill
TR | 1 | Camp Manitowish Lane (West) | CTY K West | XX |  | 0.5 |  | 0.5 |  |  |  |  | 0 |  | 0
ER | 0 | Camp Osoha Lane | CTY M South | Big Muskellunge Rd | 0.16
TR | 2 | Campo Fiesta Lane | CTY M South | North Creek Road |  | 0.13 |  | 0.13 |  |  |  |  | 0.13 |  | 12350
ER | 0 | Campo Fiesta Lane (Extension) | CTY M South | North Creek Road |  |  | X
ER | 0 | Canon Hill Circle | CTY N West | XX
ER | 0 | Carmies Trail | CTY M South | North Creek Road | 0.3
TR | 2 | Cattail Cove Lane | CTY K West | XX |  | 0.75 |  | 0.75 |  | 1992 |  |  | 0.75 |  | 71250
TR | 1 | Cemetary Road | CTY K West | XX |  | 0.18 |  | 0.18 |  |  |  |  | 0 |  | 0
TR | 1 | Center Street | CTY M South, Park Street | Marsh Rd, Ada, Blueberry |  | 0.31 |  | 0.31 |  |  |  |  | 0 |  | 0
TR | 2 | Charlotte Place Lane | US 51 North | XX |  | 0.25 |  | 0.25 |  |  |  |  | 0.25 |  | 23750
TR | 2 | Church Street | Old K | Green Street |  | 0.14 |  | 0.14 |  |  |  |  | 0.14 |  | 13300
TR | 6 | Clear View Drive | CTY K West | Fallon Road |  | 0.34 | 0.34 |  |  |  |  | 0 |  |  | 0 | good condition, consider paving all or part
ER | 0 | Cliffs Trail | CTY M North | Fishtrap Road | 0.2
ER | 0 | Coach Lane | US 51 North | Island Lake Road | 0.1
TR | 1 | Community Street | CTY K West | Blaisdell Street |  | 0.2 |  | 0.2 |  |  |  |  | 0 |  | 0
TR | 2 | Concora Road | Old K | XX |  | 0.8 |  | 0.8 |  |  |  |  | 0.8 |  | 76000
ER | 0 | Concora Road (extension) |  |  | 0.28
ER |  | Copp Lane
ER | 0 | Coreen lane | CTY M North
ER | 0 | Crooked Trail | CTY K West | Evergreen Lane | 0.5
TR | 3 | Dairymens Road | CTY M North | XX |  | 1.55 |  | 1.55 |  | 1973, 1988 |  |  |  | 1.55 | 360375 | Asphalt to benefit Dairymens and Bike loop, widen 8'
TR | 5 | Dam Road | CTY M North | High-Fishtrap Lake Road |  | 0.8 | 0.8 |  |  |  |  | 0.8 |  |  | 32000
ER | 0 | Darren Road | CTY H | XX
TR | 1 | Day Lake Landing Road | Day Lake Road | XXX |  | 0.22 | 0.22 |  |  |  |  | 0 |  |  | 0
TR | 5 | Day Lake Road | North Creek Road | US 51 North |  | 2.91 | 2.91 |  |  |  |  | 2.91 |  |  | 58200 | Basic work, not full gravel work up
TR | 2 | Dolittle Road | CTY M North | Boulder Lane |  | 0.15 |  | 0.15 |  |  |  |  | 0.15 |  | 14250 | make widening part of agreement with owners, doable
ER | 0 | Dr Kate Trail | CTY K West | Newcomb Lane | 0.2
ER | 0 | Drake Lane (Dairyman's) | CTY M North | Dairymen's Road
ER | 0 | Drewsen Lane | CTY K West, Wool Lake Ln | Ray Berch Lane | 0.2
ER | 0 | Eagle Resort Trail | US 51 North | Middle Gresham Lane
ER | 0 | Eagles Post Trail | CTY M North, High-FT Lake Rd | Fishtrap Road
TR | 2 | East Fitzgerald Lane | US 51 N, Island lake Rd | Fitzgerald Lane |  | 0.11 |  | 0.11 |  |  |  |  | 0.11 |  | 10450
ER | 0 | Elizabeth Lake Lane | CTY M North | XX
TR | 4 | En-Dah Win Lane | CTY K East | XX |  | 0.15 | 0.15 | [5 empty] | 0.1 |  | 6000 | only pave to T
TR | 2 | Evergreen Lane | CTY K West | XX |  | 1.98 |  | 1.98 |  | 1974 |  |  | 1.98 |  | 188100 | check condition
ER | 0 | Evergreen Lodge Lane | CTY K West | Evergreen Lane | 0.05
TR | 3 | Fallon Road | CTY K West | XX |  | 2.08 |  | 2.08 |  | 1984, 1986 |  |  |  | 2.08 | 322400
ER |  | Field Lane
ER | 0 | Filbey Trail | CTY K West | Evergreen Lane
TR | 3 | Fishtrap Lake Road | CTY M North, High-FT Lake Rd | XX |  | 2.04 |  | 2.04 |  | 72,73,75,82,86 |  |  | 0.64 | 1.4 | 255400 | Do we want all or % as Asphalt??? Shown with asphalt to trail corner
ER | 0 | Fishtrap Resort Lane | CTY M North, High-FT Lake Rd | Fishtrap Road
TR | 2 | Fitzgerald Lane | US 51 North | Island Lake Road |  | 0.2 |  | 0.2 |  |  |  |  | 0.2 |  | 19000
ER | 0 | Fox Trail | CTY K West | Newcomb Lane | [11 empty] | is this a TOWN ROAD
TR | 2 | Glen Lake Road | CTY K West | Shamrock Road |  | 0.25 |  | 0.25 |  | 1988 |  |  | 0.25 |  | 23750
TR | 1 | Good Life Lane | CTY M North | Airport Road |  | 0.44 |  |  | 0.44 |  |  |  |  | 0 | 0
ER | 0 | Goodwille Trail | US 51 N, Island lake Rd | Le Fave Road
TR | 3 | Grahl Lane | CTY H | XX |  | 0.43 | 0.43 | [5 empty] | 0.43 |  | 25800
ER | 0 | Grassy Lake Lane | CTY M North | XX | 0.1
ER | 0 | Grassy Lake Lane | CTY M North | XX | 0.3
TR | 2 | Green Street | CTY M | Old K |  | 0.27 |  | 0.27 |  |  |  |  | 0.27 |  | 25650
ER |  | Gresham Creek Trail
TR | 5 | Halverson Lane | CTY M South | XX |  | 0.12 | 0.12 |  |  |  |  | 0.12 |  |  | 4800
TR | 2 | Harmony Point Lane | US 51 North | between M and H |  | 0.6 |  | 0.6 |  | 1974, 1982 |  |  | 0.6 |  | 57000 | narrow road
ER | 0 | Harrington Lane | CTY K West | Whitney Lake Road | 0.25
ER | 0 | Headwaters Trail | Cty M North | XX | 0.14
ER | 0 | Hidden Bay Lane | CTY K West, Highland Drive | Shamrock Lane | 0.09
ER | 0 | Hideaway Bay Trail |  |  | 0.16
TR | 2 | High Lake Road | CTY M North, High-FT Lake Rd | Allen Road |  | 3.8 |  |  | 3.8 | 1972, 1983 |  |  | 1.1 | 0.7 | 267250 | Between Allen and Ridge is okay, Chip ridge to end, asphalt loop leg
TR | 2 | High Pines Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln |  | 1.1 |  | 1.1 |  | 1978 |  |  | 1.1 |  | 104500 | needs improved turn around area
ER | 0 | High Pines Lane (extension) | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln | 0.33
TR | 2 | High-Fishtrap Lake Road | CTY M North | XX |  | 1.1 |  |  | 1.1 |  |  |  |  | 1.1 | 255750 | asphalt for loop, add 8' to width
TR | 3 | Highland Drive | CTY K West | CTY M North |  | 0.28 |  | 0.28 |  | 1976, 1990 |  |  |  | 0.28 | 43400 | Upgrade for Bike Loop and Event Bypass support
ER | 0 | Hoag Circle | CTY K West, Highland Drive | Shamrock Lane | 0.1
ER | 0 | Home Lake Lane (Dairyman's) | CTY M North | Dairymen's Road
TR | 2 | Island Lake Road | US 51 North | XX |  | 1.28 |  | 1.28 |  | 1987 |  |  | 1.28 |  | 121600
ER | 0 | Island Point Lane | CTY K West, Highland Drive | Shamrock Lane
TR | 6 | Jag Lake Road | CTY H | XX |  | 0.08 | 0.08 |  |  |  |  | 0 |  |  | 0
ER | 0 | John Lane
ER | 0 | Junction Lane
ER | 0 | June Bug Circle | CTY M North | High Lake Road | 0.1
TR | 1 | Kassien Lane | US 51 North | Island Lake Road |  | 0.54 |  | 0.54 |  |  |  |  | 0 |  | 0
ER | 0 | Keego Lake Road (Keego extension) | CTY K West | Keego Road | 0.1
TR | 2 | Keego Road | CTY K West | XX |  | 1.25 |  | 1.25 |  | 1984 |  |  | 1.25 |  | 118750
TR | 6 | Keego Road East | CTY K West, Bear lake Road | Keego Road |  | 1.31 | 1.31 |  |  |  |  | 0 |  |  | 0
TR | 2 | Kern Lane | CTY m South | North Creek Road |  | 1.1 |  | 1.1 |  |  |  |  | 1.1 |  | 104500
TR | 2 | La Fave Road | US 51 North | Island Lake Road |  | 1.24 |  | 1.24 |  | 1970 |  |  | 0.25 |  | 23750 | Northwest segment only
ER | 0 | Labrador trail | CTY M South | North Creek Road | 0.3
TR | 4 | Little Crooked Lane | CTY K West | Bear Lake Road |  | 0.38 | 0.38 | [5 empty] | 0.38 |  | 22800
ER | 0 | Little John Lake Trail | CTY M South | CTY N East | 0.05
TR | 2 | Little Rice Lane | CTY M North | XX |  | 0.28 |  | 0.28 |  |  |  |  | 0.28 |  | 26600
ER | 0 | Lone Tree Trail | CTY M North | High Lake Road | 0.1
ER | 0 | Lost Canoe Trail | CTY K East | XX
TR | 2 | Lucas Lane | CTY K West | XX |  | 0.15 |  | 0.15 |  | 1971 |  |  | 0.15 |  | 14250 | paved to start of campground
TR | 2 | Major Road | CTY M North | Dairymen's Road |  | 0.5 |  | 0.5 |  | 1973 |  |  | 0.5 |  | 47500 | road to nowhere, pave only if benefit to Dairymen's
TR | 2 | Mann Lake Road | CTY M South | XX |  | 0.75 |  | 0.75 |  | 1973, 1990 |  |  | 0.65 |  | 61750 | first .1m ok, no turn around
TR | 5 | Maple Lake Road | CTY K West | XX |  | 0.35 | 0.35 |  |  |  |  | 0.35 |  |  | 14000
TR | 4 | Marsh Road | CTY M South | CTY K West |  | 1.04 | 1.04 | [5 empty] | 1.04 |  | 62400 | Create Bike bypass for through riders, better use of events
TR | 2 | Middle Gresham Lane | US 51 North (near H) | XX |  | 0.43 |  | 0.43 |  |  |  |  | 0.43 |  | 40850
ER | 0 | Milo Trail | CTY K East | XX | 0.1
ER | 0 | Modrusani Trail | CTY M South | North Creek Road | 0.3
ER | 0 | Muskie Mack Trail | CTY N East | XX | 0.11
ER |  | Musky Lodge Lane
ER | 0 | Natures Way Road | CTY H, baaken Rd, Island lake Rd | Old 51 (Bakken-Island Lake) | 0.3
TR | 5 | Nebish lake Road | CTY K West | XX |  | 1.97 | 1.97 |  |  |  |  | 1.97 |  |  | 78800
ER | 0 | Nelson Lake Lane | US 51 North | Bakken Road (west)
TR | 3 | Newcomb Lane | CTY K West | XX |  | 3.5 |  | 3.5 |  | 78,80,83,88,92 |  |  |  | 3.5 | 542500
TR | 1 | Nichols Lake Lane | CTY H | CTY K West |  | 0.63 |  | 0.63 |  |  |  |  | 0 |  | 0
TR | 5 | Nixon Lake Road | CTY K East | XX |  | 2.6 | 2.6 |  |  |  |  | 2.6 |  |  | 104000 | Seek cost share with DNR
TR | 3 | North Creek Road | CTY M South | CTY H |  | 4.57 |  | 4.57 |  | 75, 76, 87, 92 |  |  |  | 4.57 | 708350 | Possible width increase for Bike Route, Cost share with DNR
TR | 5 | North Oswego Lake Road | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road |  | 0.24 | 0.24 |  |  | 1991 |  | 0.24 |  |  | 9600
ER | 0 | North Shore Pines Lane | Cty H | XX | 0.44
TR | 1 | North Town Line Rd (Town Road 116) | US 51 North | Le Fave Rd, Island Lake Rd |  | 1 |  | 1 |  | 1991 |  |  | 0 |  | 0
TR | 0 | Old 51 East Hoffman Road |  | 0.26
TR | 0 | Old 51 Old H |  | 1.17
TR | 5 | Old 51 Road (Bakken Rd - Island Lake Rd) | CTY H, Bakken Rd (east) | US 51 N, Island Lake Rd |  | 1.8 | 1.8 |  |  | 1980 |  | 1.8 |  |  | 72000 | snowmobile %
TR | 1 | Old 51 Road (Town Line - Island Lake Rd) | US 51 North | Town Line Rd, Island lake Rd |  | 1.07 |  | 1.07 |  |  |  |  | 0 |  | 0
TR | 6 | Old Flambeau Road | CTY H?? | Bakken Rd ?? |  | 0.74 | 0.74 |  |  |  |  | 0 |  |  | 0 | No signs, looks like snowmobile trail, barely a road
TR | 2 | Old K Road | CTY M, Main Street | CTYK East |  | 2.79 |  | 2.79 |  | 1969, 1991 |  |  | 2.79 |  | 397575 | widen 8' for bike loop (Asphalt??)
TR | 1 | Oswego-Fishtrap Lake Road | CTY M North, High-FT Lake Rd | Fishtrap Road |  | 1.9 |  | 1.9 |  |  |  |  | 0 |  | 0 | make all or % asphalt ???
ER | 0 | Owls Lane | CTY K West | Camp Manitowish ln - East | 0.2
TR | 4 | Partridge Lane | CTY M North, High-FT Lake Rd | High Lake Road |  | 1.1 | 1.1 | [5 empty] | 1.1 |  | 66000
ER | 0 | Pat Lin Lane | US 51 North | Bakken Road (west)
ER | 0 | Patterson Place |  |  | 0.2
ER | 0 | Patterson Place |  |  | 0.12
TR | 4 | Perch Lane | CTY M South (by N) |  |  | 0.23 | 0.23 | [5 empty] | 0.23 |  | 13800 | no turn around
TR | 2 | Pine Lane | US 51 North | Bakken Road (west) |  | 0.45 |  | 0.45 |  | 1984 |  |  | 0.45 |  | 42750 | no turn around
TR | 5 | Pine Shores Lane | US 51 North | Bakken Road (west) |  | 0.06 | 0.06 |  |  |  |  | 0.06 |  |  | 2400
ER | 0 | Pine Shores Lane (extension) |  |  | 0.09
TR | 4 | Pinewood Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln |  | 0.12 | 0.12 | [5 empty] | 0.12 |  | 7200
ER | 0 | Pinewood Lane (extension) | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln | 0.15 |  | X
ER | 0 | Piney Road (Dairyman's) | CTY M North | Dairymen's Road
TR | 4 | Platinum Lane | CTY H | Grahl Lane |  | 0.23 | 0.23 | [5 empty] | 0.23 |  | 13800
TR | 6 | Point Lane | CTY K West | Fallon Rd, Rintleman Rd |  | 0.25 | 0.25 |  |  |  |  | 0 |  |  | 0 | Good condition, Consider Paving?
ER | 0 | Porter Trail | CTY M North, High-FT Lake Rd | Fishtrap Road
ER | 0 | Princess Pine Lane | CTY M South | North Creek Road | 0.5
ER | 0 | R.E.S.Lane | CTY H | Rudolph Lake Lane | 0.75
ER |  | Raven Retreat Trail
ER | 0 | Ray Berch lane | CTY K West | Wool Lake Lane | 0.2
TR | 2 | Red Fox Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead |  | 0.09 |  | 0.09 |  |  |  |  | 0.09 |  | 8550
TR | 2 | Reible Court | Old K | XX |  | 0.12 |  | 0.12 |  |  |  |  | 0.12 |  | 11400
ER | 0 | Rice Bay Lane | CTY K West | Fallon Road | 0.38
TR | 5 | Ridge Lane | CTY M North, High-FT Lake Rd | High Lake Rd |  | 1.2 | 0.3 | 0.9 |  | 1983 |  | 0.3 | 0 |  | 12000
TR | 2 | Rintlemen | CTY K West | Fallon Road |  | 0.6 |  | 0.6 |  |  |  |  | 0.6 |  | 57000
ER | 0 | Ritzke Trail | CTY H | XX | 0.1
TR | 6 | River lane | CTY K West | XX |  | 0.2 | 0.2 |  |  |  |  | 0 |  |  | 0
ER | 0 | River Run Lane | CTY K West | XX | 0.75
Er |  | Riverstone Drive
TR | 1 | Rocky Reef Lane | CTY M South | CTY N West |  | 0.54 |  | 0.54 |  | 1982, 1992 |  |  | 0 |  | 0 | poor turn around area
TR | 1 | Round Lake Road | CTY K West | Bear Lake Road |  | 0.1 |  | 0.1 |  |  |  |  | 0 |  | 0
TR | 1 | Round Lake Road (Presque Isle) | CTY K West | Bear Lake Road |  | 1.25 |  | 1.25 |  |  |  |  | 0 |  | 0
TR | 2 | Rudolph Lake Lane | CTY H | XX |  | 0.6 |  | 0.6 |  |  |  |  | 0.6 |  | 57000
TR | 6 | Rudolph Lake Lane (South) | CTY H | Rudolph Lake Lane |  | 0.26 | 0.26 |  |  | 1987 |  | 0 |  |  | 0
TR | 1 | Rustic Colony Lane | CTY M North | Airport Road |  | 0.27 |  | 0.27 |  |  |  |  | 0 |  | 0
ER |  | Ryan Road
ER | 0 | Sandy Bank Lane | CTY K West, Newcomb Ln | Shore Drive | 0.1
ER | 0 | Sarah Jane Lane | US 51 N, Island lake Rd | Le Fave Rd, Abe Le Fave Tr | 0.15
ER | 0 | Schuenemann Trail | CTY H | XX | 0.48
ER | 0 | Sea Wolf Trail | CTY K West | Bear Lake Road | 0.6
TR | 1 | Senior Drive | CTY M, Park Street | Green Street |  | 0.2 |  | 0.2 |  |  |  |  | 0 |  | 0
ER | 0 | Shalimar Lane | CTY H, North Creek Road | Wilson Lane | 0.1
TR | 2 | Shamrock Lane | CTY K West | Highland Drive |  | 0.4 |  | 0.4 |  |  |  |  | 0.4 |  | 38000
ER | 0 | Shamrock lane (extension) | CTY K West | Highland Drive | 0.22
ER | 0 | Shelter Bay Trail | CTY M North | Fishtrap Road | 0.1
TR | 2 | Sherry Drive | CTY M North, High-FT Lake Rd | High Lake Road |  | 0.05 |  | 0.05 |  |  |  |  | 0.05 |  | 4750
ER | 0 | Shoemaker Trail | CTY H, Rudolph Lake Ln | R.E.S Lane | 0.6
TR | 2 | Shore Drive | CTY K West | Newcomb Lane |  | 1.03 |  | 1.03 |  | 1991 |  |  | 1.03 |  | 97850
ER | 0 | Six Point Lane | CTY M North | Airport Road
TR |  | South Rudolph Lake Lane | CTY H | Rudolph Lake Lane
TR | 4 | South Shore Bay Lane | US 51 North | Island Lake Road |  | 0.15 | 0.15 | [5 empty] | 0.15 |  | 9000
TR | 1 | South Town Line | US 51 North | XX |  | 1.36 |  | 1.36 |  | 1976, 1988 |  |  | 0 |  | 0
TR | 2 | Spruce Drive | CTY M North, High-FT Lake Rd | High Lake Road |  | 0.22 |  | 0.22 |  |  |  |  | 0.22 |  | 20900 | create turn-arounds at each end
TR | 2 | Stiloski Lane | CTY M North, High-FT Lake Rd | Fishtrap Road |  | 0.37 |  | 0.37 |  | 1975 |  |  | 0.37 |  | 35150
ER | 0 | Stiloski Lane (Extension) | CTY M North, High-FT Lake Rd | Fishtrap Road | 0.23 |  | X
ER | 0 | Stone Gate Lane | US 51 North | XX
ER | 0 | Stonehaven | CTY K West | Bear Lake Road
TR | 6 | Street Lake Lane | CTY H | XX |  | 0.65 | 0.65 |  |  |  |  | 0 |  |  | 0 | do we want to pave??
ER | 0 | Summer Bay Trail | CTY M North, High-FT Lake Rd | High Lake, Ridge Ln, High Pines | 0.75
TR | 4 | Sunset Lane | CTY M South, North Creek Rd | Kern lane, Trout lane |  | 0.3 | 0.3 | [5 empty] | 0.3 |  | 18000 | gravel, is this a town road? Pave it??
ER | 0 | Swanson Trail
ER | 0 | Taylor Timber Trail | CTY M North, High-FT Lake Rd | High Lake, Ridge Ln, High Pines | 0.6
ER | 0 | The Narrows Trail | CTY M North, High-FT Lake Rd | Fishtrap Road, Stiloski Ln | 0.42
ER | 0 | Timber Oak Trail
ER | 0 | Totem Trail | CTY M South, North Creek Rd | Princess Pine Lane | 0.08
TR | 1 | Town Hall Road | Around Community Building |  |  | 0.12 |  |  | 0.12 | 1987 |  |  |  | 0 | 0
TR |  | Town Road 119 | CTY K West, Fallon Rd | Clear View Drive |  | 0.14
TR |  | Town Road 127 |  |  |  | 0.1
TR |  | Town Road 133 |  |  |  | 0.15 | X
TR | 2 | Trout Lane | CTY M South, North Creek Rd | Kern lane |  | 0.2 |  | 0.2 |  |  |  |  | 0.2 |  | 19000
TR | 6 | Vandercook Road | CTY M South | XX |  | 0.08 | 0.08 |  |  |  |  | 0 |  |  | 0 | trapped between Arbor Vitae roads, snowmobile trail 100%
ER | 0 | Vanny Trail | US 51 North | Jolin Lane
ER | 0 | Wee Pines Trail | US 51 North | XX
TR | 5 | West Big Lake Road | CTY K West | XX |  | 1.04 | 1.04 |  |  |  |  | 1.04 |  |  | 41600
TR | 5 | White Birch Lane | CTY M North, High-FT Lake Rd | Osewgo-FT Lake Road |  | 0.45 | 0.45 |  |  |  |  | 0.45 |  |  | 18000
TR | 4 | White Deer Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead |  | 0.12 | 0.12 | [5 empty] | 0.12 |  | 7200
ER | 0 | White Sand Trail | Old K | Concora Road | 0.05 |  |  | 0.05 |  |  |  |  | 0.05 |  | 4750
TR | 2 | Whitney Lake Road | CTY K West | XX |  | 1 | 0.1 | 0.9 |  |  |  |  | 1 |  | 91500
ER | 0 | Wildcat Road | CTY M North | XX | [11 empty] | assume Presque Ilse handles this road
ER | 0 | Wildwood Lane | CTY K West, CTY M North | Highland Drive | 0.4
ER | 0 | Williams Lane | US 51 North | XX
ER | 0 | Wilson Lane | CTY H | North Creek Road | 0.3
ER | 0 | Windy Shores Drive | CTY M South, North Creek Rd | Princess Pine Lane | 0.1
ER | 0 | Wittigs Point Lane | CTY M North, High-FT Lake Rd | Fishtrap Road
ER | 0 | Wolf Lake lane (Dairyman's) | CTY M North | Dairymen's Road
TR | 2 | Wool Lake Lane | CTY K West | XX |  | 0.76 |  | 0.76 |  | 1967, 1972, 1983 |  |  | 0.76 |  | 72200
|  |  |  | TOTAL MILES | 15.85 | 93.62 | 25.79 | 55.17 | 12.37 |  |  | 13.74 | 34.61 | 15.86 | 6393400 | TOTAL ESTIMATED COST
[8 empty] | Town Road Mileage | 93.33 |  |  | Gravel | Chip | Asphalt
[9 empty] | 99.69% |  |  |  |  | 68.59% | Percent of Town Roads receiving roadwork
COLOR KEY
|  | 1 | Recently Updated, Or in Good Condition - No work planned
|  | 2 | Paved Road, repaving planned, same surface
|  | 3 | Paved Road, repaving planned, new surface
|  | 4 | Existing Gravel Road, planned upgrade to pavement
|  | 5 | Existing Gravel Road, general grading and gravel
|  | 6 | Existing Gravel Road/Fire Road - No Plans
PAVING COST PER MILE
|  |  |  | Existing Surface | GRAVEL | CHIP SEAL | ASPHALT
|  |  |  | GRAVEL | 40000 | 60000 | 155000
|  |  |  | CHIP SEAL | 0 | 95000 | 155000
|  |  |  | ASPHALT | 0 | 0 | 155000
NOTES:
| 1 | what about cost of markings, lines, signs?
| 2 | what about easements costs for bike lanes, turn arounds, widening?
| 3 | what about engineering costs for widening, turn arounds, general improvements
| 4 | any bridge or culvert work to include?
| 5 | need to identify roads, mileage for potential cost share
6
7
8
9

## StateList
New Rating |  | County - Municipal Code | Current Pavement Rating and Year | Surface |  |  | Units (F = Feet/ M = Miles) | On Route | At Route |  |  | Toward Route |  |  | Section Length
Pavement Rating | Rating Year |  |  | Type | Year | Width |  | Name (Includes prefix, name, type, suffix and extention) | At Municipal Location | Name (Includes prefix, name, type, suffix and extention) | At Offset | Toward Municipal Location | Name (Includes prefix, name, type, suffix and extention) | Toward Offset (Optional Field)
|  | 63004 |  | 40 | 2012 | 22 | F | Ada St |  | Center St | 0 |  | Blaisdell St | 0 | 581
|  | 63004 |  | 40 | 2012 | 22 | F | Ada St |  | Blaisdell St | 0 |  | CTH K / Main St | 0 | 739
|  | 63004 | 7 (2013) | 55 | 1970 | 18 | F | Airport Rd |  | CTH M / High Lake Rd | 0 |  | Good Life Ln | 0 | 1447
|  | 63004 | 7 (2013) | 55 | 1970 | 18 | F | Airport Rd |  | Good Life Ln | 0 |  | Rustic Coloney Ln | 0 | 1510
|  | 63004 | 7 (2013) | 55 | 1970 | 18 | F | Airport Rd |  | Rustic Coloney Ln | 0 |  | Birch Wood Dr | 0 | 158
|  | 63004 | 7 (2013) | 55 | 1970 | 18 | F | Airport Rd |  | Birch Wood Dr | 0 |  | Dairymens Rd | 0 | 4699
|  | 63004 | 1 (2011) | 40 | 1974 | 24 | F | Airport Rd |  | Birch Wood Dr | 4699 |  | Dairymens Rd | 0 | 5122
|  | 63004 | 2 (2013) | 57 | 1970 | 20 | F | Allen Rd |  | CTH M | 0 |  | High Lake Rd | 0 | 3590
|  | 63004 | 3 (2013) | 57 | 1983 | 20 | F | Allequash Lake Rd |  | CTH M | 0 |  | Termini | 0 | 4963
|  | 63004 | 2 (2013) | 55 | 1973 | 20 | F | Annes Pl |  | Old K Rd | 0 |  | Church St / Green St | 0 | 739
|  | 63004 | 2 (2013) | 55 | 1990 | 18 | F | Arrowhead Dr |  | Oswego Fish Trap Lake Rd | 0 |  | White Deer Ln | 0 | 1426
|  | 63004 | 2 (2013) | 55 | 1990 | 18 | F | Arrowhead Dr |  | White Deer Ln | 0 |  | Blue Heron Ln | 0 | 475
|  | 63004 | 2 (2013) | 55 | 1990 | 18 | F | Arrowhead Dr |  | Blue Heron Ln | 0 |  | Red Fox Ln | 0 | 528
|  | 63004 | 2 (2013) | 55 | 1990 | 18 | F | Arrowhead Dr |  | Red Fox Ln | 0 |  | Termini | 0 | 475
|  | 63004 | 4 (2013) | 55 | 2002 | 22 | F | Bakken Rd |  | Town Line Rd | 0 |  | Pine Shores Ln / TN RD 147 | 0 | 2535
|  | 63004 | 4 (2013) | 57 | 2002 | 22 | F | Bakken Rd |  | Town Line Rd | 2535 |  | Pine Shores Ln / TN RD 147 | 0 | 1214
|  | 63004 | 4 (2013) | 57 | 2002 | 22 | F | Bakken Rd |  | Pine Shores Ln / TN RD 147 | 0 |  | Pine Ln | 0 | 2904
|  | 63004 | 4 (2013) | 57 | 2002 | 22 | F | Bakken Rd |  | Pine Ln | 0 |  | Balsam Rd | 0 | 528
|  | 63004 | 4 (2013) | 57 | 2002 | 22 | F | Bakken Rd |  | Balsam Rd | 0 |  | USH 51 | 0 | 4330
|  | 63004 | 4 (2013) | 55 | 2002 | 22 | F | Bakken Rd |  | USH 51 | 0 |  | Old 51 Rd (2) | 0 | 950
|  | 63004 | 2 (2013) | 35 | 1970 | 16 | F | Balsam Rd |  | Bakken Rd | 0 |  | Termini | 0 | 1426
|  | 63004 | 2 (2013) | 30 | 1970 | 16 | F | Bass Lake Rd |  | Bear Lake Rd | 0 |  | Termini | 0 | 2165
|  | 63004 | 1 (2013) | 55 | 1972 | 22 | F | Bear Lake Rd |  | CTH K | 0 |  | Keego Rd E | 0 | 6864
|  | 63004 | 1 (2013) | 55 | 1970 | 20 | F | Bear Lake Rd |  | Keego Rd E | 0 |  | Bass Lake Rd | 0 | 211
|  | 63004 | 10 (2013) | 55 | 1970 | 20 | F | Bear Lake Rd |  | Bass Lake Rd | 0 |  | Round Lake Rd | 0 | 2429
|  | 63004 | 10 (2013) | 55 | 1970 | 20 | F | Bear Lake Rd |  | Round Lake Rd | 0 |  | Little Crooked Ln | 0 | 3749
|  | 63004 | 10 (2013) | 55 | 1970 | 20 | F | Bear Lake Rd |  | Little Crooked Ln | 0 |  | Birch Point Ln | 0 | 1056
|  | 63004 | 2 (2011) | 35 | 1970 | 16 | F | Bear Lake Rd |  | Birch Point Ln | 0 |  | Termini | 0 | 2904
|  | 63004 | 2 (2013) | 35 | 1970 | 16 | F | W Big Lake Ln |  | CTH K | 0 |  | Termini | 0 | 5491
|  | 63004 | 2 (2013) | 52 | 1994 | 22 | F | Big Muskellunge Lake Rd |  | CTH M | 0 |  | Nh State Forest Rd | 0 | 2323
|  | 63004 | 2 (2013) | 52 | 1974 | 18 | F | Big Muskellunge Lake Rd |  | CTH M | 2323 |  | Nh State Forest Rd | 0 | 317
|  | 63004 | 2 (2013) | 52 | 1974 | 18 | F | Big Muskellunge Lake Rd |  | Nh State Forest Rd | 0 |  | N Muskellunge Lake Rd / Starrett Rd / Big Muskellunge Lake Rd | 0 | 5438
|  | 63004 | 2 (2013) | 35 | 1970 | 20 | F | Big Muskellunge Lake Rd |  | Nh State Forest Rd | 5438 |  | N Muskellunge Lake Rd / Starrett Rd / Big Muskellunge Lake Rd | 0 | 2429
|  | 63004 | 2 (2013) | 40 | 2000 | 20 | F | Birch Dr |  | High Lake Rd | 0 |  | Termini | 0 | 1320
|  | 63004 | 2 (2013) | 35 | 1970 | 16 | F | Birch Point Ln |  | Bear Lake Rd | 0 |  | Termini | 0 | 1003
|  | 63004 | 7 (2013) | 55 | 2004 | 20 | F | Birch Wood Dr |  | Airport Rd | 0 |  | Termini | 0 | 1901
|  | 63004 |  | 40 | 2012 | 22 | F | Blaisdell St |  | Community St | 0 |  | Blueberry Ln | 0 | 422
|  | 63004 |  | 40 | 2012 | 22 | F | Blaisdell St |  | Blueberry Ln | 0 |  | Ada St | 0 | 475
|  | 63004 | 2 (2013) | 35 | 1973 | 16 | F | Blue Heron Ln |  | Arrowhead Dr | 0 |  | Termini | 0 | 634
|  | 63004 |  | 40 | 2012 | 22 | F | Blueberry Ln |  | Center St | 0 |  | Blaisdell St | 0 | 634
|  | 63004 |  | 40 | 2012 | 22 | F | Blueberry Ln |  | Blaisdell St | 0 |  | CTH K / Main St | 0 | 686
|  | 63004 | 1 (2013) | 55 | 1970 | 20 | F | Boulder Ln |  | CTH M | 0 |  | Termini | 0 | 2112
|  | 63004 | 9 (2013) | 55 | 2009 | 18 | F | Camp Manitowish Ln |  | CTH K | 0 |  | Camp Manitowish Ln E | 0 | 2112
|  | 63004 | 9 (2013) | 55 | 2009 | 18 | F | Camp Manitowish Ln E |  | CTH K | 0 |  | Camp Manitowish Ln | 0 | 2059
|  | 63004 | 2 (2013) | 55 | 1977 | 16 | F | Campo Fiesta Ln |  | Termini | 1214 |  | N Creek Rd | 0 | 845
|  | 63004 | 1 (2013) | 55 | 1970 | 16 | F | Cat Tail Cove Ln |  | CTH K | 0 |  | Termini | 0 | 3960
|  | 63004 | 10 (2014) | 70 | 2014 | 22 | F | Cemetery Rd |  | CTH K | 0 |  | Termini | 0 | 634
|  | 63004 |  | 40 | 2012 | 22 | F | Center St |  | Community St | 370 |  | Blueberry Ln | 0 | 422
|  | 63004 |  | 40 | 2012 | 22 | F | Center St |  | Blueberry Ln | 0 |  | Ada St | 0 | 475
|  | 63004 |  | 40 | 2012 | 22 | F | Center St |  | Ada St | 0 |  | CTH K / CTH M / Park St | 0 | 686
|  | 63004 | 2 (2013) | 55 | 1987 | 20 | F | Charlotte Pl Ln |  | Termini | 0 |  | USH 51 | 0 | 1426
Church Street
|  | 63004 | 1 (2013) | 35 | 1979 | 20 | F | Clear View Dr |  | Fallon Rd | 0 |  | TN RD 119 | 0 | 1426
|  | 63004 | 1 (2013) | 35 | 1979 | 20 | F | Clear View Dr |  | TN RD 119 | 0 |  | Termini | 0 | 370
|  | 63004 |  | 40 | 2012 | 22 | F | Community St |  | CTH K / Main St | 0 |  | Blaisdell St | 0 | 686
|  | 63004 |  | 40 | 2012 | 22 | F | Community St |  | Blaisdell St | 0 |  | Center St | 0 | 370
|  | 63004 | 3 (2013) | 55 | 1970 | 18 | F | Concora Rd |  | Old K Rd | 0 |  | Forest Rd | 0 | 4224
|  | 63004 | 3 (2013) | 55 | 1970 | 20 | F | N Creek Rd |  | CTH H | 0 |  | Day Lake Rd | 0 | 3274
|  | 63004 | 3 (2013) | 55 | 1970 | 20 | F | N Creek Rd |  | Day Lake Rd | 0 |  | Wilson Ln | 0 | 5227
|  | 63004 | 3 (2013) | 55 | 1970 | 20 | F | N Creek Rd |  | Wilson Ln | 0 |  | Kern Ln | 0 | 8870
|  | 63004 | 3 (2013) | 55 | 1977 | 16 | F | N Creek Rd |  | Kern Ln | 0 |  | Princess Pine Ln | 0 | 422
|  | 63004 | 2 (2013) | 55 | 1977 | 16 | F | N Creek Rd |  | Princess Pine Ln | 0 |  | Campo Fiesta Ln | 0 | 4699
|  | 63004 | 2 (2013) | 55 | 1977 | 20 | F | N Creek Rd |  | Campo Fiesta Ln | 0 |  | CTH K / CTH M | 0 | 1742
|  | 63004 | 5 (2013) | 55 | 1998 | 22 | F | Dairymens Rd |  | CTH M | 0 |  | Airport Rd | 0 | 5122
|  | 63004 | 5 (2013) | 55 | 1998 | 20 | F | Dairymens Rd |  | Airport Rd | 0 |  | Major Rd | 0 | 1267
|  | 63004 | 5 (2013) | 55 | 1998 | 20 | F | Dairymens Rd |  | Major Rd | 0 |  | Major Rd | 0 | 1690
|  | 63004 | 5 (2013) | 55 | 1998 | 20 | F | Dairymens Rd |  | Major Rd | 0 |  | Termini | 0 | 475
|  | 63004 | 1 (2013) | 35 | 1970 | 24 | F | Dam Rd |  | High Lake Rd | 0 |  | Termini | 0 | 4224
|  | 63004 | 1 (2013) | 30 | 1970 | 14 | F | Day Lake Landing Rd |  | Day Lake Rd | 0 |  | Termini | 0 | 1162
|  | 63004 | 1 (2013) | 30 | 1983 | 14 | F | Day Lake Rd |  | Bardon Rd / Day Lake Rd | 5069 |  | Day Lake Landing Rd | 0 | 11774
|  | 63004 | 1 (2013) | 30 | 1983 | 14 | F | Day Lake Rd |  | Day Lake Landing Rd | 0 |  | N Creek Rd | 0 | 3802
Dolittle Road
En-Dah Win Lane
|  | 63004 | 1 (2011) | 40 | 2006 | 22 | F | Evergreen Ln |  | CTH K | 0 |  | Termini | 0 | 7814
|  | 63004 | 8 (2013) | 55 | 2006 | 18 | F | Evergreen Ln |  | CTH K | 7814 |  | Termini | 0 | 2165
|  | 63004 | 8 (2013) | 55 | 2006 | 12 | F | Evergreen Ln |  | CTH K | 9979 |  | Termini | 0 | 475
|  | 63004 | 3 (2013) | 55 | 1995 | 20 | F | Fallon Rd |  | CTH K | 0 |  | Clear View Dr | 0 | 1056
|  | 63004 | 3 (2013) | 55 | 1995 | 20 | F | Fallon Rd |  | Clear View Dr | 0 |  | Rintleman Rd | 0 | 2059
|  | 63004 | 3 (2013) | 55 | 1995 | 18 | F | Fallon Rd |  | Rintleman Rd | 0 |  | Clear Lake Rd / Golf Rd / Fallon Rd | 0 | 4963
|  | 63004 | 3 (2013) | 55 | 1995 | 22 | F | Fallon Rd |  | Rintleman Rd | 4963 |  | Clear Lake Rd / Golf Rd / Fallon Rd | 0 | 2904
|  | 63004 | 3 (2013) | 55 | 1973 | 18 | F | Fish Trap Rd |  | Termini | 475 |  | Stiloski Ln | 0 | 4224
|  | 63004 | 3 (2013) | 55 | 1973 | 18 | F | Fish Trap Rd |  | Stiloski Ln | 0 |  | Oswego Fish Trap Lake Rd | 0 | 4013
|  | 63004 | 9 (2013) | 55 | 2009 | 22 | F | Fish Trap Rd |  | Oswego Fish Trap Lake Rd | 0 |  | High Lake Rd | 0 | 2534
E Fitzgerald Ln
|  | 63004 | 9 (2013) | 55 | 2009 | 18 | F | Fitzgerald Ln |  | Lafave Rd / S Shore Bay Ln | 0 |  | Island Lake Rd | 0 | 53
|  | 63004 | 9 (2013) | 55 | 2009 | 18 | F | Fitzgerald Ln |  | Island Lake Rd | 0 |  | Termini | 0 | 1214
|  | 63004 | 1 (2013) | 35 | 2009 | 16 | F | Fitzgerald Ln |  | Island Lake Rd | 1214 |  | Termini | 0 | 581
|  | 63004 | 1 (2013) | 35 | 1990 | 16 | F | Fox Trl |  | Newcomb Ln | 0 |  | Termini | 0 | 792
|  | 63004 | 2 (2013) | 55 | 1994 | 20 | F | Glen Lake Rd |  | Shamrock Rd | 0 |  | Shamrock Rd | 0 | 1320
|  | 63004 |  | 40 | 2007 | 20 | F | Good Life Ln |  | Airport Rd | 0 |  | Termini | 0 | 2230
|  | 63004 | 1 (2013) | 35 | 1973 | 22 | F | Grahl Ln |  | CTH H / N Shore Pines Ln | 0 |  | Platinum Ln / Termini | 0 | 2270
|  | 63004 | 2 (2013) | 55 | 1973 | 20 | F | Green St |  | CTH K / CTH M / Park St | 0 |  | Annes Pl | 0 | 370
|  | 63004 | 2 (2013) | 55 | 1973 | 20 | F | Green St |  | Annes Pl | 0 |  | Senior Dr | 0 | 53
|  | 63004 | 2 (2013) | 55 | 1973 | 20 | F | Green St |  | Senior Dr | 0 |  | Old K Rd | 0 | 1003
|  | 63004 | 7 (2013) | 55 | 1998 | 18 | F | Halvorson Ln |  | CTH M | 0 |  | Termini | 0 | 2376
|  | 63004 | 3 (2013) | 55 | 1970 | 18 | F | Harmony Point Ln |  | USH 51 | 0 |  | Termini | 0 | 3168
|  | 63004 | 3 (2013) | 52 | 1995 | 20 | F | High Lake Rd |  | Airport Rd / CTH M | 0 |  | Dam Rd | 0 | 4699
|  | 63004 | 3 (2013) | 52 | 1995 | 20 | F | High Lake Rd |  | Dam Rd | 0 |  | Fish Trap Rd / Fishtrap Lake Rd | 0 | 1373
|  | 63004 | 9 (2013) | 55 | 2010 | 20 | F | High Lake Rd |  | Fish Trap Rd / Fishtrap Lake Rd | 0 |  | Allen Rd | 0 | 4013
|  | 63004 | 9 (2013) | 55 | 2010 | 20 | F | High Lake Rd |  | Allen Rd | 0 |  | Partridge Ln | 0 | 6389
|  | 63004 | 9 (2013) | 55 | 2011 | 20 | F | High Lake Rd |  | Partridge Ln | 0 |  | Ridge Ln / High Lake Rd | 0 | 2218
|  | 63004 | 9 (2013) | 55 | 2011 | 20 | F | High Lake Rd |  | Ridge Ln / High Lake Rd | 0 |  | Sherry Ln / High Lake Rd | 0 | 1637
|  | 63004 | 9 (2013) | 55 | 2011 | 20 | F | High Lake Rd |  | Ridge Ln / High Lake Rd | 3326 |  | Sherry Ln / High Lake Rd | 0 | 1743
|  | 63004 | 9 (2013) | 55 | 2011 | 20 | F | High Lake Rd |  | Sherry Ln / High Lake Rd | 0 |  | Birch Dr | 0 | 528
|  | 63004 | 9 (2013) | 55 | 2011 | 20 | F | High Lake Rd |  | Birch Dr | 0 |  | Termini | 0 | 1214
|  | 63004 | 2 (2013) | 55 | 1970 | 20 | F | High Pines Ln |  | Ridge Ln | 0 |  | Pinewood Ln | 0 | 1478
|  | 63004 | 2 (2013) | 55 | 1979 | 18 | F | High Pines Ln |  | Pinewood Ln | 0 |  | Termini | 0 | 4330
|  | 63004 | 2 (2013) | 55 | 1973 | 18 | F | Highland Dr |  | Shamrock Rd | 0 |  | Wildwood Ln | 0 | 317
|  | 63004 | 2 (2013) | 55 | 1973 | 18 | F | Highland Dr |  | Wildwood Ln | 0 |  | CTH M | 0 | 1426
|  | 63004 | 2 (2013) | 55 | 1971 | 16 | F | Island Lake Rd |  | Fitzgerald Ln | 0 |  | Old 51 Rd (2) | 0 | 2693
|  | 63004 | 2 (2013) | 52 | 1980 | 18 | F | Island Lake Rd |  | Kassien Ln / Old 51 Rd (2) | 0 |  | Old 51 Rd (2) | 0 | 2587
|  | 63004 | 2 (2013) | 52 | 1980 | 18 | F | Island Lake Rd |  | Old 51 Rd (2) | 0 |  | USH 51 | 0 | 1478
|  | 63004 | 1 (2013) | 35 | 1970 | 18 | F | Jag Lake Rd |  | CTH H | 0 |  | Termini | 0 | 422
|  | 63004 | 1 (2013) | 35 | 1970 | 20 | F | Kassien Ln |  | Island Lake Rd / Old 51 Rd (2) | 0 |  | Termini | 0 | 2851
|  | 63004 | 1 (2013) | 52 | 1970 | 20 | F | Keego Rd |  | Termini | 422 |  | Keego Rd E | 0 | 3432
|  | 63004 | 1 (2013) | 52 | 1970 | 20 | F | Keego Rd |  | Keego Rd E | 0 |  | CTH K | 0 | 3538
|  | 63004 | 1 (2013) | 30 | 1970 | 16 | F | Keego Rd E |  | Keego Rd | 0 |  | Bear Lake Rd | 0 | 6917
|  | 63004 | 1 (2013) | 55 | 1970 | 20 | F | Kern Ln |  | N Creek Rd | 0 |  | Trout Ln | 0 | 4699
|  | 63004 | 1 (2013) | 55 | 1970 | 18 | F | Kern Ln |  | Trout Ln | 0 |  | Termini | 0 | 1320
|  | 63004 | 3 (2013) | 55 | 2009 | 18 | F | Lafave Rd |  | Dump Rd / Town Line Rd | 528 |  | Fitzgerald Ln / S Shore Bay Ln | 0 | 6547
|  | 63004 | 7 (2013) | 55 | 1998 | 18 | F | Lake Shore Dr |  | CTH M | 0 |  | CTH M | 0 | 8976
|  | 63004 | 1 (2013) | 35 | 1973 | 18 | F | Little Crooked Ln |  | Bear Lake Rd | 0 |  | Termini | 0 | 2112
Little Rice Lane
|  | 63004 | 1 (2013) | 55 | 1972 | 18 | F | Lucas Ln |  | Termini | 528 |  | CTH K | 0 | 1162
|  | 63004 | 1 (2013) | 55 | 1974 | 18 | F | Major Rd |  | Dairymens Rd | 3010 |  | Dairymens Rd | 0 | 2376
|  | 63004 | 2 (2013) | 55 | 1972 | 16 | F | Mann Lake Rd |  | CTH M | 0 |  | Termini | 0 | 3960
|  | 63004 | 1 (2013) | 30 | 1970 | 8 | F | Maple Lake Rd |  | CTH K | 0 |  | Termini | 0 | 1742
Marsh Road (TR116)
|  | 63004 | 2 (2013) | 55 | 1970 | 20 | F | Middle Gresham Ln |  | USH 51 | 0 |  | Termini | 0 | 2270
|  | 63004 | 1 (2013) | 35 | 1981 | 18 | F | Nebish Lake Rd |  | CTH M | 0 |  | Starrett Rd / Nebish Lake Rd | 0 | 10402
|  | 63004 | 2 (2013) | 57 | 1980 | 20 | F | Newcomb Ln |  | CTH K | 0 |  | Shore Dr | 0 | 17213
|  | 63004 | 1 (2013) | 55 | 1990 | 20 | F | Newcomb Ln |  | Shore Dr | 0 |  | Fox Trl | 0 | 950
|  | 63004 | 1 (2013) | 55 | 1990 | 20 | F | Newcomb Ln |  | Fox Trl | 0 |  | Termini | 0 | 686
|  | 63004 | 3 (2013) | 55 | 1979 | 20 | F | Nichols Lake Rd |  | CTH H | 0 |  | Nichols Lake Ln / TN RD 127 | 0 | 1848
|  | 63004 | 3 (2013) | 55 | 1979 | 20 | F | Nichols Lake Rd |  | Nichols Lake Ln / TN RD 127 | 0 |  | Termini | 0 | 1478
|  | 63004 | 1 (2013) | 35 | 1970 | 18 | F | Nixon Lake Rd |  | CTH K | 0 |  | Forest Rd | 0 | 6178
|  | 63004 | 1 (2013) | 35 | 1970 | 18 | F | Nixon Lake Rd |  | Forest Rd | 0 |  | Camp 2 Rd / Nixon Lake Rd | 0 | 7550
|  | 63004 | 2 (2013) | 55 | 1977 | 20 | F | Old 51 Rd (2) |  | Town Line Rd / Twin Pines Rd | 0 |  | USH 51 | 0 | 792
|  | 63004 | 3 (2013) | 55 | 1980 | 18 | F | Old 51 Rd (2) |  | USH 51 | 0 |  | Island Lake Rd | 0 | 4488
|  | 63004 | 3 (2013) | 55 | 1980 | 18 | F | Old 51 Rd (2) |  | Island Lake Rd | 0 |  | Island Lake Rd / Kassien Ln | 0 | 106
|  | 63004 | 1 (2013) | 35 | 1970 | 18 | F | Old 51 Rd (2) |  | Island Lake Rd | 0 |  | Hoffman Rd E / Old 51 Rd E | 0 | 2640
|  | 63004 | 1 (2013) | 35 | 1970 | 18 | F | Old 51 Rd (2) |  | Hoffman Rd E / Old 51 Rd E | 0 |  | Bakken Rd | 0 | 7867
|  | 63004 | 3 (2013) | 55 | 1979 | 20 | F | Old 51 Rd (2) |  | Bakken Rd | 0 |  | Old Flambeau Rd | 0 | 2482
|  | 63004 | 3 (2013) | 55 | 1979 | 20 | F | Old 51 Rd (2) |  | Old Flambeau Rd | 0 |  | CTH H | 0 | 2746
|  | 63004 | 1 (2013) | 35 | 1970 | 20 | F | Old 51 Rd E |  | Old 51 Rd (2) | 0 |  | Termini | 0 | 1373
|  | 63004 | 1 (2013) | 30 | 1986 | 8 | F | Old Flambeau Rd |  | CTH H | 0 |  | Old 51 Rd (2) | 0 | 3907
|  | 63004 | 2 (2013) | 70 | 2007 | 38 | F | Old K Rd |  | CTH K / CTH M / Main St / Park St | 0 |  | Annes Pl | 0 | 370
|  | 63004 | 7 (2013) | 70 | 2007 | 38 | F | Old K Rd |  | Annes Pl | 0 |  | Reible Ct / Rieble Ct | 0 | 211
|  | 63004 | 7 (2013) | 70 | 2007 | 38 | F | Old K Rd |  | Reible Ct / Rieble Ct | 0 |  | Church St / Green St | 0 | 158
|  | 63004 | 7 (2013) | 70 | 2007 | 38 | F | Old K Rd |  | Church St / Green St | 0 |  | Concora Rd | 0 | 211
|  | 63004 | 7 (2013) | 55 | 1998 | 20 | F | Old K Rd |  | Church St / Green St | 211 |  | Concora Rd | 0 | 5280
|  | 63004 | 2 (2013) | 55 | 1970 | 18 | F | Old K Rd |  | Concora Rd | 0 |  | CTH K | 0 | 8606
|  | 63004 | 8 (2013) | 55 | 2009 | 20 | F | Oswego Fish Trap Lake Rd |  | Fish Trap Rd / Fishtrap Lake Rd | 0 |  | Arrowhead Dr | 0 | 2112
|  | 63004 | 8 (2013) | 55 | 2009 | 20 | F | Oswego Fish Trap Lake Rd |  | Arrowhead Dr | 0 |  | Oswego Fish Trap Lake Rd Private | 0 | 370
|  | 63004 | 8 (2013) | 55 | 2009 | 20 | F | Oswego Fish Trap Lake Rd |  | Oswego Fish Trap Lake Rd Private | 0 |  | White Birch Ln | 0 | 1373
|  | 63004 | 8 (2013) | 55 | 2009 | 20 | F | Oswego Fish Trap Lake Rd |  | White Birch Ln | 0 |  | N Oswego Lake Rd | 0 | 1690
|  | 63004 | 8 (2013) | 55 | 2009 | 20 | F | Oswego Fish Trap Lake Rd |  | N Oswego Lake Rd | 0 |  | Termini | 0 | 4594
|  | 63004 | 10 (2013) | 55 | 1971 | 16 | F | N Oswego Lake Rd |  | Oswego Fish Trap Lake Rd | 0 |  | Termini | 0 | 1267
|  | 63004 | 1 (2011) | 35 | 1970 | 20 | F | Partridge Ln |  | High Lake Rd | 0 |  | Termini | 0 | 5808
|  | 63004 | 1 (2013) | 35 | 1974 | 16 | F | Perch Ln |  | CTH M | 0 |  | Termini | 0 | 1214
|  | 63004 | 1 (2013) | 55 | 1973 | 20 | F | Pine Ln |  | Bakken Rd | 0 |  | Termini | 0 | 2746
|  | 63004 | 1 (2013) | 35 | 1970 | 16 | F | Pine Shores Ln |  | Bakken Rd / TN RD 147 | 0 |  | Termini | 0 | 317
|  | 63004 | 1 (2013) | 35 | 1970 | 18 | F | Pinewood Ln |  | Termini | 0 |  | High Pines Ln | 0 | 634
|  | 63004 | 1 (2013) | 35 | 1973 | 22 | F | Platinum Ln |  | CTH H / Grahl Ln | 2270 |  | Termini | 0 | 1215
|  | 63004 | 1 (2013) | 35 | 1970 | 14 | F | Point Ln |  | Rintleman Rd | 0 |  | Termini | 0 | 1320
Red Fox Lane
|  | 63004 | 2 (2013) | 55 | 1974 | 20 | F | Reible Ct |  | Old K Rd | 0 |  | Termini | 0 | 634
|  | 63004 | 10 (2013) | 55 | 2010 | 20 | F | Ridge Ln |  | High Lake Rd | 0 |  | High Pines Ln | 0 | 4858
|  | 63004 | 3 (2013) | 50 | 2011 | 20 | F | Ridge Ln |  | High Pines Ln | 0 |  | Termini | 0 | 2218
|  | 63004 | 3 (2013) | 35 | 1970 | 18 | F | Rintleman Rd |  | Clear Lake Rd / Rintleman Rd | 3326 |  | Point Ln | 0 | 1109
|  | 63004 | 3 (2013) | 35 | 1970 | 18 | F | Rintleman Rd |  | Point Ln | 0 |  | Fallon Rd | 0 | 2059
|  | 63004 | 1 (2013) | 35 | 1983 | 16 | F | River Ln |  | CTH K | 0 |  | Termini | 0 | 1056
|  | 63004 | 2 (2013) | 55 | 1973 | 18 | F | Rocky Reef Ln |  | CTH N | 0 |  | Termini | 0 | 2851
|  | 63004 | 1 (2011) | 35 | 1970 | 16 | F | Round Lake Rd |  | Bear Lake Rd | 0 |  | Termini / Round Lake Rd | 0 | 528
|  | 63004 | 2 (2013) | 55 | 1972 | 20 | F | Rudolph Lake Ln |  | CTH H | 0 |  | S Rudolph Lake Ln | 0 | 2165
|  | 63004 | 2 (2013) | 55 | 1972 | 20 | F | Rudolph Lake Ln |  | S Rudolph Lake Ln | 0 |  | Res Ln | 0 | 792
|  | 63004 | 2 (2013) | 35 | 1983 | 8 | F | S Rudolph Lake Ln |  | Rudolph Lake Ln | 0 |  | Termini | 0 | 1373
|  | 63004 | 6 (2013) | 55 | 2004 | 20 | F | Rustic Coloney Ln |  | Airport Rd | 0 |  | Rustic Colony Ln | 0 | 422
|  | 63004 | 1 (2013) | 55 | 2004 | 20 | F | Rustic Coloney Ln |  | Rustic Colony Ln | 0 |  | Termini | 0 | 1162
|  | 63004 | 3 (2013) | 35 | 1993 | 22 | F | Senior Dr |  | Church St / Green St | 0 |  | Termini | 0 | 792
|  | 63004 | 2 (2013) | 55 | 1970 | 20 | F | Shamrock Rd |  | CTH K / Main St | 0 |  | Highland Dr | 0 | 475
|  | 63004 | 2 (2013) | 55 | 1970 | 20 | F | Shamrock Rd |  | Highland Dr | 0 |  | Glen Lake Rd | 0 | 581
|  | 63004 | 2 (2013) | 55 | 1970 | 20 | F | Shamrock Rd |  | Glen Lake Rd | 0 |  | Glen Lake Rd | 0 | 1214
|  | 63004 | 5 (2013) | 40 | 2000 | 20 | F | Sherry Ln |  | High Lake Rd | 0 |  | Spruce Dr | 0 | 370
|  | 63004 | 2 (2013) | 57 | 1983 | 12 | F | S Shore Bay Ln |  | Fitzgerald Ln / Lafave Rd | 0 |  | Termini | 0 | 792
|  | 63004 | 2 (2013) | 55 | 1991 | 20 | F | Shore Dr |  | Termini | 0 |  | Newcomb Ln | 0 | 5438
|  | 63004 | 1 (2013) | 40 | 2000 | 20 | F | Spruce Dr |  | Termini | 0 |  | Sherry Ln | 0 | 792
|  | 63004 | 1 (2013) | 40 | 2000 | 20 | F | Spruce Dr |  | Sherry Ln | 0 |  | Termini | 0 | 37
|  | 63004 | 1 (2013) | 55 | 1970 | 20 | F | Stiloski Ln |  | Fish Trap Rd / Fishtrap Lake Rd | 0 |  | Stiloski Rd | 0 | 1954
|  | 63004 | 3 (2013) | 35 | 1979 | 20 | F | Street Lake Rd |  | CTH H | 0 |  | Termini | 0 | 3432
|  | 63004 | 3 (2013) | 55 | 1970 | 18 | F | Sunset Ln |  | Trout Ln | 739 |  | Termini | 0 | 53
|  | 63004 | 3 (2013) | 35 | 1970 | 14 | F | Sunset Ln |  | Trout Ln | 792 |  | Termini | 0 | 2006
|  | 63004 | 1 (2013) | 35 | 1970 | 16 | F | TN RD 116 |  | CTH K / Main St | 0 |  | CTH K / CTH M / Park St | 0 | 5280
|  | 63004 | 1 (2013) | 35 | 1979 | 20 | F | TN RD 119 |  | Clear View Dr | 0 |  | Termini | 0 | 739
|  | 63004 | 1 (2013) | 35 | 1972 | 12 | F | TN RD 127 |  | Nichols Lake Rd | 0 |  | Termini | 0 | 528
|  | 63004 | 1 (2013) | 35 | 1999 | 22 | F | TN RD 146 |  | CTH M | 0 |  | CTH B / Wildcat Rd | 0 | 1584
|  | 63004 | 2 (2013) | 35 | 1999 | 20 | F | TN RD 147 |  | Bakken Rd / Pine Shores Ln | 0 |  | Termini | 0 | 528
|  | 63004 | 3 (2013) | 55 | 1970 | 20 | F | Town Hall Rd |  | CTH K / CTH M / Park St | 0 |  | CTH K / CTH M / Park St | 0 | 634
|  | 63004 | 10 (2013) | 70 | 2012 | 20 | F | Town Line Rd |  | Dump Rd / Town Line Rd | 1003 |  | USH 51 / Town Line Rd | 0 | 1531
|  | 63004 | 10 (2013) | 70 | 2012 | 20 | F | Town Line Rd |  | Pine Ln / Town Line Rd | 528 | 63016 | Lavigne Rd | 0 | 950
|  | 63004 | 10 (2013) | 70 | 2012 | 20 | F | Town Line Rd | 63016 | Lavigne Rd | 0 |  | Bakken Rd | 0 | 581
|  | 63004 | 10 (2013) | 70 | 2012 | 20 | F | Town Line Rd |  | Bakken Rd | 0 | 63016 | Alder Lake Rd | 0 | 3221
|  | 63004 | 10 (2013) | 55 | 1970 | 16 | F | Town Line Rd | 63016 | Alder Lake Rd | 0 |  | Termini | 0 | 845
|  | 63004 | 2 (2013) | 55 | 1970 | 18 | F | Trout Ln |  | Kern Ln | 0 |  | Sunset Ln / Termini | 0 | 739
|  | 63004 | 2 (2013) | 35 | 1970 | 14 | F | Vandercook Rd |  | CTH M / Vandercook Rd | 3485 |  | Buckhorn Rd / Vandercook Rd | 0 | 422
|  | 63004 | 2 (2013) | 35 | 1970 | 16 | F | White Birch Ln |  | Oswego Fish Trap Lake Rd | 0 |  | Termini | 0 | 2376
|  | 63004 | 2 (2013) | 35 | 1973 | 16 | F | White Deer Ln |  | Arrowhead Dr | 0 |  | Termini | 0 | 264
|  | 63004 | 5 (2013) | 55 | 2004 | 16 | F | Whitney Lake Ln |  | CTH K | 0 |  | Termini | 0 | 5438
|  | 63004 | 2 (2013) | 55 | 1979 | 20 | F | Wool Lake Ln |  | CTH K | 0 |  | Termini | 0 | 4013
[15 empty] | 477469 | FT
[15 empty] | 90.4297 | MILES

## Roads-Ranking Weighted
TOWN OF BOULDER JUNCTION
TOWN ROAD REDEVELOPMENT PLAN
| PLAN |  |  |  | Length |  |  | SURFACE TYPE | [5 empty] | RATING |  |  |  | Work Scope |  | Extra Work
TYPE | CAT | ROAD NAME | Primary Access Road | Secondary Access Road | ER | TR | Gravel | Chip | Asphalt | Seal Coated or Resurfaced |  | Traffic | Occupancy | Condition | Score | Weighted | Surface | Engrg | Extra | Description | COMMENTS
TR | 3 | Allen Road | CTY M North | High Lake Road |  | 0.68 |  | 0.68 |  | 1975, 1990 |  | 5 | 5 | 5 | 15 | 125 |  |  |  |  | upgrade to asphalt, widen 8' for Bike lanes (White Deer Loop)
TR | 3 | Fishtrap Lake Road | CTY M North, High-FT Lake Rd | XX |  | 2.04 |  | 2.04 |  | 72,73,75,82,86 |  | 5 | 5 | 5 | 15 | 125 |  |  |  |  | Do we want all or % as Asphalt??? Shown with asphalt to trail corner
TR | 3 | Newcomb Lane | CTY K West | XX |  | 3.5 |  | 3.5 |  | 78,80,83,88,92 |  | 5 | 5 | 5 | 15 | 125
TR | 3 | North Creek Road | CTY M South | CTY H |  | 4.57 |  | 4.57 |  | 75, 76, 87, 92 |  | 5 | 5 | 5 | 15 | 125 |  |  |  |  | Possible width increase for Bike Route, Cost share with DNR
TR | 3 | Fallon Road | CTY K West | XX |  | 2.08 |  | 2.08 |  | 1984, 1986 |  | 5 | 5 | 4 | 14 | 100
TR | 2 | Island Lake Road | US 51 North | XX |  | 1.28 |  | 1.28 |  | 1987 |  | 4 | 5 | 4 | 13 | 80
TR | 2 | High-Fishtrap Lake Road | CTY M North | XX |  | 1.1 |  |  | 1.1 |  |  | 5 | 5 | 3 | 13 | 75 |  |  |  |  | asphalt for loop, add 8' to width
TR | 4 | Big Muskellunge Road | CTY M South | XX |  | 2.7 | 1.2 | 1 | 0.5 | 1976 |  | 5 | 3 | 4 | 12 | 60
TR | 2 | Kern Lane | CTY m South | North Creek Road |  | 1.1 |  | 1.1 |  |  |  | 3 | 4 | 5 | 12 | 60
TR | 4 | Airport Road (paved) | CTY M North | Dairymen's Road |  | 2.45 |  |  | 1.45 | 1969, 1984 |  | 5 | 5 | 2 | 12 | 50 |  |  |  |  | Pave 1 mi of gravel, denote "bike share", (Airport Loop)
TR | 2 | High Lake Road (FT to Ridge) | CTY M North, High-FT Lake Rd | Allen Road |  | 3.8 |  |  | 2.5 | 1972, 1983 |  | 5 | 5 | 2 | 12 | 50 |  |  |  |  | Between Allen and Ridge is okay, Chip ridge to end, asphalt loop leg
TR | 2 | Shamrock Lane | CTY K West | Highland Drive |  | 0.4 |  | 0.4 |  |  |  | 3 | 4 | 4 | 11 | 48
TR | 2 | Concora Road | Old K | XX |  | 0.8 |  | 0.8 |  |  |  | 3 | 3 | 5 | 11 | 45
TR | 2 | High Lake Road (after Ridge) | [5 empty] | 1.3 |  |  |  | 3 | 3 | 5 | 11 | 45
TR | 2 | Old K Road | CTY M, Main Street | CTYK East |  | 2.79 |  | 2.79 |  | 1969, 1991 |  | 3 | 3 | 5 | 11 | 45 |  |  |  |  | widen 8' for bike loop (Asphalt??)
TR | 3 | Dairymens Road | CTY M North | XX |  | 1.55 |  | 1.55 |  | 1973, 1988 |  | 4 | 5 | 2 | 11 | 40 |  |  |  |  | Asphalt to benefit Dairymens and Bike loop, widen 8'
TR | 1 | Oswego-Fishtrap Lake Road | CTY M North, High-FT Lake Rd | Fishtrap Road |  | 1.9 |  | 1.9 |  |  |  | 4 | 5 | 2 | 11 | 40
TR | 1 | South Town Line | US 51 North | XX |  | 1.36 |  | 1.36 |  | 1976, 1988 |  | 4 | 5 | 2 | 11 | 40
TR | 2 | Bakken Road (East) | CTY H | HWY 51 N |  | 1.07 |  | 1.07 |  | 67,68 |  | 3 | 3 | 4 | 10 | 36 |  |  |  |  | Asphalt upgrade??
TR | 3 | Highland Drive | CTY K West | CTY M North |  | 0.28 |  | 0.28 |  | 1976, 1990 |  | 3 | 3 | 4 | 10 | 36 |  |  |  |  | Upgrade for Bike Loop and Event Bypass support
TR | 2 | Rudolph Lake Lane | CTY H | XX |  | 0.6 |  | 0.6 |  |  |  | 3 | 4 | 3 | 10 | 36
TR | 2 | Wool Lake Lane | CTY K West | XX |  | 0.76 |  | 0.76 |  | 1967, 1972, 1983 |  | 3 | 3 | 4 | 10 | 36
TR | 1 | North Town Line Rd (Town Road 116) | US 51 North | Le Fave Rd, Island Lake Rd |  | 1 |  | 1 |  | 1991 |  | 4 | 4 | 2 | 10 | 32
TR | 2 | Harmony Point Lane | US 51 North | between M and H |  | 0.6 |  | 0.6 |  | 1974, 1982 |  | 2 | 3 | 5 | 10 | 30 |  |  |  |  | narrow road
TR | 2 | Shore Drive | CTY K West | Newcomb Lane |  | 1.03 |  | 1.03 |  | 1991 |  | 2 | 3 | 5 | 10 | 30
TR | 1 | Bakken Road (West) | CTY H | HWY 51 N |  | 2.15 |  | 2.15 |  |  |  | 3 | 3 | 3 | 9 | 27
TR | 2 | La Fave Road | US 51 North | Island Lake Road |  | 1.24 |  | 1.24 |  | 1970 |  | 3 | 3 | 3 | 9 | 27 |  |  |  |  | Northwest segment only
TR | 1 | Ben Bendrick Drive (Lake Shore Drive) | CTY M South | XX |  | 1.7 |  |  | 1.7 |  |  | 4 | 3 | 2 | 9 | 24
TR | 2 | Green Street | CTY M | Old K |  | 0.27 |  | 0.27 |  |  |  | 4 | 2 | 3 | 9 | 24
TR | 2 | High Pines Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln |  | 1.1 |  | 1.1 |  | 1978 |  | 3 | 4 | 2 | 9 | 24 |  |  |  |  | needs improved turn around area
TR | 2 | Lucas Lane | CTY K West | XX |  | 0.15 |  | 0.15 |  | 1971 |  | 2 | 2 | 5 | 9 | 20 |  |  |  |  | paved to start of campground
TR | 2 | Arrowhead Drive | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road |  | 0.55 | 0.15 | 0.45 |  | 82, 88 |  | 2 | 3 | 3 | 8 | 18 |  |  |  |  | turn around work
TR | 2 | Evergreen Lane | CTY K West | XX |  | 1.98 |  | 1.98 |  | 1974 |  | 3 | 2 | 3 | 8 | 18 |  |  |  |  | check condition
TR | 2 | Mann Lake Road | CTY M South | XX |  | 0.75 |  | 0.75 |  | 1973, 1990 |  | 2 | 3 | 3 | 8 | 18 |  |  |  |  | first .1m ok, no turn around
TR | 2 | Middle Gresham Lane | US 51 North (near H) | XX |  | 0.43 |  | 0.43 |  |  |  | 2 | 3 | 3 | 8 | 18
TR | 2 | Keego Road | CTY K West | XX |  | 1.25 |  | 1.25 |  | 1984 |  | 2 | 2 | 4 | 8 | 16
TR | 2 | Little Rice Lane | CTY M North | XX |  | 0.28 |  | 0.28 |  |  |  | 2 | 2 | 4 | 8 | 16
TR | 2 | Rintlemen | CTY K West | Fallon Road |  | 0.6 |  | 0.6 |  |  |  | 2 | 2 | 4 | 8 | 16
TR | 2 | Boulder Lane | CTY M North | XX |  | 0.4 |  | 0.4 |  |  |  | 1 | 3 | 4 | 8 | 12
TR | 4 | Camp Manitowish Lane (East) | CTY K West | XX |  | 0.5 | 0.5 |  |  |  |  | 2 | 2 | 3 | 7 | 12 |  |  |  |  | pave it since CMW will be carrying big tax bill
TR | 6 | Clear View Drive | CTY K West | Fallon Road |  | 0.34 | 0.34 |  |  |  |  | 3 | 2 | 2 | 7 | 12 |  |  |  |  | good condition, consider paving all or part
TR | 3 | Grahl Lane | CTY H | XX |  | 0.43 | 0.43 |  |  |  |  | 3 | 2 | 2 | 7 | 12
TR | 5 | Nebish lake Road | CTY K West | XX |  | 1.97 | 1.97 |  |  |  |  | 4 | 1 | 3 | 8 | 12
TR | 5 | Old 51 Road (Bakken Rd - Island Lake Rd) | CTY H, Bakken Rd (east) | US 51 N, Island Lake Rd |  | 1.8 | 1.8 |  |  | 1980 |  | 2 | 2 | 3 | 7 | 12 |  |  |  |  | snowmobile %
TR | 5 | Ridge Lane | CTY M North, High-FT Lake Rd | High Lake Rd |  | 1.2 | 0.3 | 0.9 |  | 1983 |  | 3 | 4 | 1 | 8 | 12
TR | 1 | Bear Lake Road | CTY K West | XX |  | 3.26 |  |  | 3.26 | 1971, 1974, 1986 | 2015 | 3 | 3 | 1 | 7 | 9 |  |  |  |  | repaved with asphalt in 2015
TR | 5 | Dam Road | CTY M North | High-Fishtrap Lake Road |  | 0.8 | 0.8 |  |  |  |  | 3 | 1 | 3 | 7 | 9
TR | 2 | Glen Lake Road | CTY K West | Shamrock Road |  | 0.25 |  | 0.25 |  | 1988 |  | 1 | 3 | 3 | 7 | 9
TR | 5 | Nixon Lake Road | CTY K East | XX |  | 2.6 | 2.6 |  |  |  |  | 3 | 1 | 3 | 7 | 9 |  |  |  |  | Seek cost share with DNR
TR | 1 | Old 51 Road (Town Line - Island Lake Rd) | US 51 North | Town Line Rd, Island lake Rd |  | 1.07 |  | 1.07 |  |  |  | 3 | 1 | 3 | 7 | 9
TR | 1 | Rustic Colony Lane | CTY M North | Airport Road |  | 0.27 |  | 0.27 |  |  |  | 1 | 3 | 3 | 7 | 9
TR | 4 | Airport Road (gravel) |  |  |  |  | 1 |  |  |  |  | 2 | 1 | 4 | 7 | 8
TR | 1 | Camp Manitowish Lane (West) | CTY K West | XX |  | 0.5 |  | 0.5 |  |  |  | 2 | 2 | 2 | 6 | 8
TR | 4 | Platinum Lane | CTY H | Grahl Lane |  | 0.23 | 0.23 |  |  |  |  | 2 | 2 | 2 | 6 | 8
TR | 1 | Rocky Reef Lane | CTY M South | CTY N West |  | 0.54 |  | 0.54 |  | 1982, 1992 |  | 2 | 2 | 2 | 6 | 8 |  |  |  |  | poor turn around area
TR | 2 | Stiloski Lane | CTY M North, High-FT Lake Rd | Fishtrap Road |  | 0.37 |  | 0.37 |  | 1975 |  | 1 | 2 | 4 | 7 | 8
TR | 4 | Sunset Lane | CTY M South, North Creek Rd | Kern lane, Trout lane |  | 0.3 | 0.3 |  |  |  |  | 1 | 2 | 4 | 7 | 8 |  |  |  |  | gravel, is this a town road? Pave it??
TR |  | Town Road 119 (Clear View) | CTY K West, Fallon Rd | Clear View Drive |  | 0.14 | 0.25 |  |  |  |  | 2 | 2 | 2 | 6 | 8
TR | 2 | Trout Lane | CTY M South, North Creek Rd | Kern lane |  | 0.2 |  | 0.2 |  |  |  | 1 | 2 | 4 | 7 | 8
TR | 2 | Whitney Lake Road | CTY K West | XX |  | 1 | 0.1 | 0.9 |  |  |  | 1 | 2 | 4 | 7 | 8
TR | 1 | Nichols Lake Lane | CTY H | CTY K West |  | 0.63 |  | 0.63 |  |  |  | 2 | 1 | 3 | 6 | 6
TR | 2 | Pine Lane | US 51 North | Bakken Road (west) |  | 0.45 |  | 0.45 |  | 1984 |  | 1 | 2 | 3 | 6 | 6 |  |  |  |  | no turn around
TR | 6 | Point Lane | CTY K West | Fallon Rd, Rintleman Rd |  | 0.25 | 0.25 |  |  |  |  | 1 | 2 | 3 | 6 | 6 |  |  |  |  | Good condition, Consider Paving?
TR | 4 | South Shore Bay Lane | US 51 North | Island Lake Road |  | 0.15 | 0.15 |  |  |  |  | 1 | 2 | 3 | 6 | 6
TR | 2 | Cattail Cove Lane | CTY K West | XX |  | 0.75 |  | 0.75 |  | 1992 |  | 1 | 1 | 5 | 7 | 5
TR | 2 | Major Road | CTY M North | Dairymen's Road |  | 0.5 |  | 0.5 |  | 1973 |  | 1 | 1 | 5 | 7 | 5 |  |  |  |  | road to nowhere, pave only if benefit to Dairymen's
TR | 5 | North Oswego Lake Road | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road |  | 0.24 | 0.24 |  |  | 1991 |  | 1 | 1 | 5 | 7 | 5
TR | 2 | Sherry Drive | CTY M North, High-FT Lake Rd | High Lake Road |  | 0.05 |  | 0.05 |  |  |  | 1 | 1 | 5 | 7 | 5
TR | 2 | Spruce Drive | CTY M North, High-FT Lake Rd | High Lake Road |  | 0.22 |  | 0.22 |  |  |  | 1 | 1 | 5 | 7 | 5 |  |  |  |  | create turn-arounds at each end
TR | 2 | Allequash Lake Road | CTY M South | XX |  | 0.94 |  | 0.94 |  |  |  | 2 | 0.5 | 4 | 6.5 | 4
TR | 2 | Annes Place | Old K | Green Street |  | 0.14 |  | 0.14 |  |  |  | 2 | 1 | 2 | 5 | 4
TR | 1 | Birchwood Lane | CTY M North | Airport Road |  | 0.36 |  | 0.36 |  | 1984 |  | 1 | 2 | 2 | 5 | 4
TR | 4 | Blue Heron Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead |  | 0.12 | 0.12 |  |  |  |  | 1 | 1 | 4 | 6 | 4
TR | 1 | Blueberry Lane | Main Street, CTY K West | Center Street |  | 0.25 |  | 0.25 |  |  |  | 2 | 1 | 2 | 5 | 4
TR | 2 | Campo Fiesta Lane | CTY M South | North Creek Road |  | 0.13 |  | 0.13 |  |  |  | 1 | 1 | 4 | 6 | 4
TR | 1 | Center Street | CTY M South, Park Street | Marsh Rd, Ada, Blueberry |  | 0.31 |  | 0.31 |  |  |  | 2 | 1 | 2 | 5 | 4
TR | 2 | Church Street | Old K | Green Street |  | 0.14 |  | 0.14 |  |  |  | 2 | 1 | 2 | 5 | 4
TR | 2 | Dolittle Road | CTY M North | Boulder Lane |  | 0.15 |  | 0.15 |  |  |  | 1 | 1 | 4 | 6 | 4 |  |  |  |  | make widening part of agreement with owners, doable
TR | 2 | East Fitzgerald Lane | US 51 N, Island lake Rd | Fitzgerald Lane |  | 0.11 |  | 0.11 |  |  |  | 1 | 1 | 4 | 6 | 4
TR | 2 | Fitzgerald Lane | US 51 North | Island Lake Road |  | 0.2 |  | 0.2 |  |  |  | 1 | 1 | 4 | 6 | 4
TR | 4 | Little Crooked Lane | CTY K West | Bear Lake Road |  | 0.38 | 0.38 |  |  |  |  | 1 | 2 | 2 | 5 | 4
TR | 1 | Town Hall Road | Around Community Building |  |  | 0.12 |  |  | 0.12 | 1987 |  | 4 | 1 | 1 | 6 | 4
TR | 4 | White Deer Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead |  | 0.12 | 0.12 |  |  |  |  | 1 | 1 | 4 | 6 | 4
TR | 4 | Balsam Lane | US 51 North | Bakken Road (west) |  | 0.35 | 0.35 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  |  |  |  | no turn around
TR | 5 | Bass Lake Road | CTY K West | Bear Lake Road |  | 0.41 | 0.41 |  |  |  |  | 1 | 1 | 3 | 5 | 3
TR | 5 | Birch Point Lane | CTY K West | Bear Lake Road |  | 0.19 | 0.19 |  |  |  |  | 1 | 1 | 3 | 5 | 3
TR | 2 | Charlotte Place Lane | US 51 North | XX |  | 0.25 |  | 0.25 |  |  |  | 1 | 1 | 3 | 5 | 3
TR | 4 | En-Dah Win Lane | CTY K East | XX |  | 0.15 | 0.15 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  |  |  |  | only pave to T
TR | 5 | Halverson Lane | CTY M South | XX |  | 0.12 | 0.12 |  |  |  |  | 1 | 1 | 3 | 5 | 3
TR | 1 | Kassien Lane | US 51 North | Island Lake Road |  | 0.54 |  | 0.54 |  |  |  | 1 | 1 | 3 | 5 | 3
TR | 4 | Partridge Lane | CTY M North, High-FT Lake Rd | High Lake Road |  | 1.1 | 1.1 |  |  |  |  | 1 | 1 | 3 | 5 | 3
TR | 4 | Perch Lane | CTY M South (by N) |  |  | 0.23 | 0.23 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  |  |  |  | no turn around
TR | 5 | Pine Shores Lane | US 51 North | Bakken Road (west) |  | 0.06 | 0.06 |  |  |  |  | 1 | 1 | 3 | 5 | 3
TR | 4 | Pinewood Lane | CTY M North, High-FT Lake Rd | High Lake Rd, Ridge Ln |  | 0.12 | 0.12 |  |  |  |  | 1 | 1 | 3 | 5 | 3
TR | 2 | Red Fox Lane | CTY M North, High-FT Lake Rd | Oswego-FT Lake Road, Arrowhead |  | 0.09 |  | 0.09 |  |  |  | 1 | 1 | 3 | 5 | 3
TR | 1 | Senior Drive | CTY M, Park Street | Green Street |  | 0.2 |  | 0.2 |  |  |  | 1 | 1 | 3 | 5 | 3
TR | 6 | Street Lake Lane | CTY H | XX |  | 0.65 | 0.65 |  |  |  |  | 1 | 1 | 3 | 5 | 3 |  |  |  |  | do we want to pave??
TR | 5 | White Birch Lane | CTY M North, High-FT Lake Rd | Osewgo-FT Lake Road |  | 0.45 | 0.45 |  |  |  |  | 1 | 1 | 3 | 5 | 3
TR | 6 | Keego Road East | CTY K West, Bear lake Road | Keego Road |  | 1.31 | 1.31 |  |  |  |  | 1 | 0.5 | 5 | 6.5 | 2.5
TR | 6 | Old Flambeau Road | CTY H?? | Bakken Rd ?? |  | 0.74 | 0.74 |  |  |  |  | 0.5 | 1 | 5 | 6.5 | 2.5 |  |  |  |  | No signs, looks like snowmobile trail, barely a road
TR | 1 | Ada Street | CTY M | Main Street |  | 0.25 |  | 0.25 |  |  | <10 | 1 | 1 | 2 | 4 | 2
TR | 6 | Birch Drive | CTY M North, High-FT Lake Rd | High Lake Road |  | 0.25 | 0.25 |  |  |  |  | 1 | 1 | 2 | 4 | 2
TR | 1 | Blaisdell Street | Main Street, CTY K West | Ada, Blueberry |  | 0.17 |  | 0.17 |  |  |  | 1 | 1 | 2 | 4 | 2
TR | 1 | Community Street | CTY K West | Blaisdell Street |  | 0.2 |  | 0.2 |  |  |  | 1 | 1 | 2 | 4 | 2
TR | 5 | Maple Lake Road | CTY K West | XX |  | 0.35 | 0.35 |  |  |  |  | 1 | 1 | 2 | 4 | 2
TR | 2 | Reible Court | Old K | XX |  | 0.12 |  | 0.12 |  |  |  | 1 | 1 | 2 | 4 | 2
TR | 6 | River lane | CTY K West | XX |  | 0.2 | 0.2 |  |  |  |  | 1 | 1 | 2 | 4 | 2
TR | 6 | South Rudolph Lake Lane | CTY H | Rudolph Lake Lane |  | 0.26 | 0.26 |  |  | 1987 |  | 1 | 1 | 2 | 4 | 2
TR | 5 | West Big Lake Road (lane) | CTY K West | XX |  | 1.04 | 1.04 |  |  |  |  | 1 | 1 | 2 | 4 | 2 |  |  |  |  | one house, why is this a town road?
TR | 5 | Boat Landing Road (Island lake) | US 51 North | Island Lake Road |  | 0.5 | 0.5 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5
TR | 1 | Day Lake Landing Road | Day Lake Road | XXX |  | 0.22 | 0.22 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5
TR | 5 | Day Lake Road | North Creek Road | US 51 North |  | 2.91 | 2.91 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 |  |  |  |  | Basic work, not full gravel work up
TR | 4 | Marsh Road | CTY M South | CTY K West |  | 1.04 | 1.04 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 |  |  |  |  | Create Bike bypass for through riders, better use of events
TR | 6 | Vandercook Road | CTY M South | XX |  | 0.08 | 0.08 |  |  |  |  | 1 | 0.5 | 3 | 4.5 | 1.5 |  |  |  |  | trapped between Arbor Vitae roads, snowmobile trail 100%
TR | 1 | Good Life Lane | CTY M North | Airport Road |  | 0.44 |  |  | 0.44 |  |  | 1 | 1 | 1 | 3 | 1
TR | 6 | Jag Lake Road | CTY H | XX |  | 0.08 | 0.08 |  |  |  |  | 1 | 0.5 | 2 | 3.5 | 1 |  |  |  |  | boat landing
TR | 1 | Round Lake Road | CTY K West | Bear Lake Road |  | 0.1 |  | 0.1 |  |  |  | 1 | 0.5 | 2 | 3.5 | 1
TR | 1 | Cemetary Road | CTY K West | XX |  | 0.18 |  | 0.18 |  |  |  | 1 | 0.5 | 1 | 2.5 | 0.5
TR | 0 | Old 51 East Hoffman Road |  | 0.26 | [10 empty] | 0
TR | 0 | Old 51 Old H |  | 1.17 | [10 empty] | 0
TR | 1 | Round Lake Road (Presque Isle) | CTY K West | Bear Lake Road |  | 1.25 |  | 1.25 | [6 empty] | 0
TR |  | Town Road 127 |  |  |  | 0.1 | [8 empty] | 0
TR |  | Town Road 133 |  |  |  | 0.15 | X | [7 empty] | 0
0
0
|  |  |  | TOTAL MILES | 0 | 92.94 | 26.04 | 56.42 | 11.07 | [10 empty] | 0 | TOTAL ESTIMATED COST
[8 empty] | Town Road Mileage | 93.53
COLOR KEY
|  | 1 | Recently Updated, Or in Good Condition - No work planned |  |  |  | Recently Updated, Or in Good Condition - No work planned
|  | 2 | Paved Road, repaving planned, same surface |  |  |  | Paved Road, repaving planned, same surface
|  | 3 | Paved Road, repaving planned, new surface |  |  |  | Paved Road, repaving planned, new surface
|  | 4 | Existing Gravel Road, planned upgrade to pavement |  |  |  | Existing Gravel Road, planned upgrade to pavement
|  | 5 | Existing Gravel Road, general grading and gravel |  |  |  | Existing Gravel Road, general grading and gravel
|  | 6 | Existing Gravel Road/Fire Road - No Plans |  |  |  | Existing Gravel Road/Fire Road - No Plans
PAVING COST PER MILE
|  |  |  | Existing Surface | Gravel | Chip Seal | Asphalt
|  |  |  | GRAVEL | 40000 | 60000 | 155000
|  |  |  | CHIP SEAL | 40000 | 95000 | 155000
|  |  |  | ASPHALT | 40000 | 95000 | 155000
NOTES:
| 1 | what about cost of markings, lines, signs?
| 2 | what about easements costs for bike lanes, turn arounds, widening?
| 3 | what about engineering costs for widening, turn arounds, general improvements
| 4 | any bridge or culvert work to include?
| 5 | need to identify roads, mileage for potential cost share
6
7
8
9

## finance
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67
Loan 1 | 0 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
Loan 2 | [6 empty] | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
Loan 3 | [11 empty] | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
Loan 4 | [16 empty] | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
Loan 5 | [21 empty] | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
Loan 6 | [26 empty] | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
Loan 7 | [31 empty] | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
Loan 8 | [36 empty] | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
Loan 9 | [41 empty] | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
[47 empty] | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67
Loan 1 | 0 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000
Loan 2 | [25 empty] | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
Loan 3 | [35 empty] | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
Loan 4 | [46 empty] | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
Loan 5
Loan 6
Loan 7
Loan 8
Loan 9
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67
Maint Budget | 0 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
Loan 1 | 0 | 1250000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loan 2 | [6 empty] | 1250000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loan 3 | [11 empty] | 1250000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loan 4 | [16 empty] | 1250000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loan 5 | [21 empty] | 1250000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loan 6 | [26 empty] | 1250000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loan 7 | [31 empty] | 1250000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loan 8 | [36 empty] | 1250000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loan 9 | [41 empty] | 1250000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loan 10 | [46 empty] | 1250000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67
Maint Budget | 0 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
Loan 1 | 0 | 2000000 | 4000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loan 2 | [25 empty] | 1250000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loan 3 | [35 empty] | 1250000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
Loan 4 | [46 empty] | 1250000 | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loan 5
Loan 6
Loan 7